## List
PROJECT CONTROL GROUP (PCG) FORUM - CHANGE REQUEST (CR)
put your company logo here
[12 empty] | VENDOR NAME | : NOKIA
[12 empty] | No of PCG MOM | : 010/PCG-CR/8/2022 (Java)
Date of PCG MOM
CHANGE REQUEST
No | PCG Week Number | PCG Action Point Register No | CR No (from Indosat) | System Key | Network Header | Site Id Original | Site Name Original | Site id Actual | Site Name Actual | Region- Area | Project Type | SOW Original | SOW Actual | Project Manager Indosat | IPPID | Program Name | Project Name | PO No | PO Line item impacted | PO Number Actual | PO Amount Actual | Add Qty | Additional Value (USD) | Additional Value (IDR) | Reduc Qty | Reduction Value (USD) | Reduction Value (IDR) | CR Background
1 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW647736 | 1000736732 | 16SBY0094 | IN_APARTGRAHAFM_TM | 16SBY0095 | APARTGRAHAFM_TM | EJ | RAN | 2T2R L900_(10) + 2T2R L1800_(30) + 2T2R L2100_(15) | 2T2R L900_(10) + 2T2R L1800_(30) + 2T2R L2100_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 3950 | [8 empty] | refer to actual implementation of site
2 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW647748 | 1000736738 | 16SBY0188 | IN_CWS2_MI | 16SBY0189 | CWS2_MI | EJ | RAN | 2T2R L900_(10) + 4T4R L1800_(20) + 2T2R L2100_(15) | 2T2R L900_(10) + 4T4R L1800_(20) + 2T2R L2100_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 4070 | [8 empty] | refer to actual implementation of site
3 | PCG Week 30 - 2022 | 175 |  | 22NDXXXNW648637 | 1000735925 | 14SMG0215 | INDOSATSMG_EP | 14SMG0214 | IN_INDOSATSMG_TM | CJ | RAN | 1T1R L1800_(30) | 1T1R L1800_(30) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041339 | 8870 | [8 empty] | refer to actual implementation of site
4 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW648669 | 1000735926 | 15YOG0052 | HSANTIKAYGJ_EP | 15YOG0051 | IN_HSANTIKAYGJ_TM | CJ | RAN | 1T1R L1800_(30) | 1T1R L1800_(30) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041339 | 9190 | [8 empty] | refer to actual implementation of site
5 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW648817 | 1000710969 | 15SMN0248 | HOTELQUALITY_EP | 15SMN0247 | IN_HOTELQUALITY_TM | CJ | RAN | 1T1R L1800_(30) | 1T1R L1800_(30) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041339 | 9420 | [8 empty] | refer to actual implementation of site
6 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW648838 | 1000735929 | 15YOG0072 | NOVOTELYGY_EP | 15YOG0071 | IN_NOVOTELYGY_TM | CJ | RAN | 1T1R L1800_(30) | 1T1R L1800_(30) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041338 | 8940 | [8 empty] | refer to actual implementation of site
7 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW651419 | 1000736730 | 16SBY0348 | CENTRALPOIN_MI | 16SBY0347 | IN_CENTRALPOIN_MI | EJ | RAN | 1T1R L1800_(15) | 1T1R L1800_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 6850 | [8 empty] | refer to actual implementation of site
8 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW651420 | 1000736734 | 16SBY0318 | TUNJUNGAN_PLZ6_TB | 16SBY0319 | IN_TUNJUNGAN_PLZ6_TB | EJ | RAN | 1T1R L1800_(15) | 1T1R L1800_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 6860 | [8 empty] | refer to actual implementation of site
9 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW651457 | 1000736746 | 16SBY0561 | RSHAJI_MC | 16SBY0560 | IN_RSHAJI_MC | EJ | RAN | 1T1R L1800_(15) | 1T1R L1800_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 7230 | [8 empty] | refer to actual implementation of site
10 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW651493 | 1000736740 | 16SBY0241 | CITYTOMORROW_PW | 16SBY0240 | IN_CITYTOMORROW_PW | EJ | RAN | 1T1R L1800_(20) + 1T1R L2100_(10) | 1T1R L1800_(20) + 1T1R L2100_(10) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 7570 | [8 empty] | refer to actual implementation of site
11 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW651494 | 1000736742 | 16SBY0252 | SUTOS_MC | 16SBY0251 | IN_SUTOS_MC | EJ | RAN | 1T1R L1800_(20) | 1T1R L1800_(20) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 7580 | [8 empty] | refer to actual implementation of site
12 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW651986 | 1000735924 | 14SMG0077 | BANDARA_AHMAD_YANI_AT | 14SMG0076 | IN_BANDARA_AHMAD_YANI_AT | CJ | RAN | 1T5S L1800_(20) + 1T5S L2100_(10) | 1T5S L1800_(20) + 1T5S L2100_(10) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041338 | 3450 | [8 empty] | refer to actual implementation of site
13 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW654645 | 1000735927 | 14SMG0280 | IN_JAVAMALL_TM | 14SMG0281 | JAVAMALL_TM | CJ | RAN | 2T2R L900_(10) + 4T4R L1800_(20) + 2T2R L2100_(15) | 2T2R L900_(10) + 4T4R L1800_(20) + 2T2R L2100_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041338 | 8920 | [8 empty] | refer to actual implementation of site
14 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW654647 | 1000736743 | 16SBY0362 | IN_GRH_BUKOPIN_MI | 16SBY0360 | GRH_BUKOPIN_MI | EJ | RAN | 2T2R L900_(10) + 4T6S L1800_(30) + 4T6S L2100_(15) | 2T2R L900_(10) + 4T6S L1800_(30) + 4T6S L2100_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 4340 | [8 empty] | refer to actual implementation of site
15 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW654648 | 1000736727 | 16SBY0306 | IN_DARMOTRDCTR_TM | 16SBY0307 | DARMOTRDCTR_TM | EJ | RAN | 2T2R L900_(10) + 4T4R L1800_(20) + 2T2R L2100_(15) | 2T2R L900_(10) + 4T4R L1800_(20) + 2T2R L2100_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 4440 | [8 empty] | refer to actual implementation of site
16 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW654649 | 1000736735 | 16SBY0292 | IN_GIANTHYPER_TM | 16SBY0293 | GIANTHYPER_TM | EJ | RAN | 2T2R L1800_(20) | 2T2R L1800_(20) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 4420 | [8 empty] | refer to actual implementation of site
17 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW654651 | 1000735928 | 15YOG0034 | IN_RAMAI_MALL_TM | 15YOG0035 | RAMAI_MALL_TM | CJ | RAN | 2T2R L900_(10) + 4T4R L1800_(30) + 2T2R L2100_(25) | 2T2R L900_(10) + 4T4R L1800_(30) + 2T2R L2100_(25) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041338 | 8950 | [8 empty] | refer to actual implementation of site
18 | PCG Week 30 - 2022 | 176 |  | 22NDXXXNW657329 | 1000736725 | 16SBY0443 | IN_RSUD_DRSUTOMO_MI | 16SBY0444 | RSUD_DRSUTOMO_MI | EJ | RAN | 2T2R L900_(10) + 4T4R L1800_(20) + 2T2R L2100_(15) | 2T2R L900_(10) + 4T4R L1800_(20) + 2T2R L2100_(15) | Mochamad Ismail | I22.04.NE.ND.012.NW | Integration | AOP 2022 Integration Wo Battle-6 | 4000041375 | 6840 | [8 empty] | refer to actual implementation of site
[16 empty] | Approved Date : | [6 empty] | Approved Date :
|  | PT. Nokia Solution & Networks | [13 empty] | PT. Indosat Ooredoo- Planning Function | [6 empty] | PT. Indosat Ooredoo- Deployment Function
|  | ( Agus Kelana ) | [13 empty] | ( Yusuf Setiawan ) | [6 empty] | ( Ali Zaenal Abidin )
|  | Senior Rollout Manager | [13 empty] | Act VP-Head of RAN Planning & Engineering | [6 empty] | VP-Head of RAN/Access Java
Note on M8: Shinta, Nia (EXT - ID/Jakarta): from SOW detail on POIN mt1 (system key)