## Data
tambah
|  |  |  | Closing info | [5 empty] | Bulk | KK bulk |  |  | Phase Name MT |  |  | 2095820 |  |  | #REF! | [22 empty] | Endorse_baseline |  |  |  | RFC date |  |  |  | CR No (RELOC) | CR No (REDUCTION) | CR Status |  |  |  |  | Doc Type | [7 empty] | #REF! | #REF! | [7 empty] | SSAC CERTIFICATE Number | SSAC CERTIFICATE Link | [12 empty] | Remarks SVC only/MIX | PO SVC (SSAC) | PO SVC (PAC) | PO SVC (BAMS for PAC) | PO Mat (SSAC) | PO Mat (PAC) | PO Mat (BAMS for PAC) | [17 empty] | Punchlist | Link CA | NO NEED CA/NEED CA | SYSTEMKEY RELATED 44 CN | BAUT RELATED 44 CN | PO RELATED 44 CN | optim | [7 empty] | Booking Number | [7 empty] | NG,Reservation,CR Status | [15 empty] | NIR CW 22 > 90 (02 Jun 2023)
Filename | No | System_Key | Vendor_Unique_ID | Not Use | sow_ne | sow_group | Not Use | PO_No | Not Use | Not Use | Not Use | PO_Type | Project_Name | Project_Category | NE Type | NE_ID | Line_Item | Material_Number | Material_Description | PO_Qty | PO_Detail | Region | Province | Site_ID_A_PO | Site_Name_A_PO | Site_ID_B_PO | Site_Name_B_PO | Hop_ID_PO | Site_ID_A_Act | Site_Name_A_Act | Site_ID_B_Act | Site_Name_B_Act | Hop_ID_Act | Site_Detail | Site_Type | Scope_Of_Work_RAN | Old_Band | New_Band | Scope_Of_Work_Non_RAN | Details Information | Project_Details | OA_Baseline | ATP_Baseline | RF_Cluster | Imp_Cluster | OA_Actual | ATP_MCR | ATP_Actual | ATP_Endorse_Actual | Remark | Progress | PMP_No. | PMP_Submit | PMP_Approved | PMP_Remark | PMP | ATP_No | ATP_Type | ATP_Submit | ATP_Approved | ATP_Remark | ATP_PMIS | Currency | Unit_Price [Gross] A | Unit_Price [Nett] B | Total_PO [Gross] C=Qty*A | Total_PO [Nett] D=Qty*B | PO Value | BABT_No. | BABT_Submit_Date | BABT_Approved | BABT_Released | BABT_Remark | BABT | Services_MCR_Type | MCR Certificate_No | MCR_Exit_Date | BA_MCR_Submit | BA_MCR_Approved | BA_MCR_Released | MCR_Remark | MCR | Services_DC_Type | DC_No | DC_Submit | DC_Approved | DC_Link | DC_Remark | Not Use | Not Use | Not Use | Not Use | Not Use | Not Use | Not Use | Services_PAC_Type | PAC_No | PAC_Submit | PAC_Approved | PAC_Baseline | PAC_Remark | PAC | FAC_No. | FAC_Submit | FAC_Approved | FAC_Released | FAC_Remark | FAC | SO No | SO VALUE | SO REMARKS | SO | Not Use | Not Use | Not Use | Not Use | Not Use | Not Use | Not Use | BAUT SENT TO ISAT | BAUT RESUBMIT TO ISAT | BAMP SENT TO ISAT | BAMG SENT TO ISAT | NO COVER SHEET BAK/BAUT | BA NO ISAT BAK/BAUT | BAMP NO | BAHM/BAMHO NO | BAMG NO | BAPPO NO | KK NO. | BAST RECEIVED DATE | BAMP RECEIVED DATE | BAMG RECEIVED DATE | BAST NO | GI BACKEND NO | BAST NO BAMP | BAST NO BAMG | PROGRESS STATUS BABT | PROGRESS STATUS BAUT | PROGRESS STATUS BAMP | PROGRESS STATUS BAMG | BACKLOG | TOP BABT | TOP BAUT | TOP BAMP | TOP BAMG | BABT HO to LOG | BAST HO to LOG | BAMP HO to LOG | BAMG HO to LOG | Not Use | DPC Number | SMPID | pac_date | pacquarter | Progress SO BAUT by SOC
1.20 RAN Tomhawk Q1 - Expansion Actual | 393 | 23ND001NW030685 | 394055 |  | RAN only | Expansion | 4000042940_70 | 4000042940 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 70 | 1100000124 | 473096A - ABIA AirScale Capacity | 1 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 23444883 | 9284174 | 23444883 | 9284174 |  | 162013FDAUCAUCFPRJBABT2022 | 2022-12-06 | 2022-12-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1131046765 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001088870 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 394 | 23ND001NW030685 | 394056 |  | RAN only | Expansion | 4000042940_140 | 4000042940 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 140 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 4 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 561883.0003 | 222505.9999 | 2247532.0014 | 890023.9995 |  | 162139FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1131046765 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001114146 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 395 | 23ND001NW030685 | 394057 |  | RAN only | Expansion | 4000042940_90 | 4000042940 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 90 | 1100000126 | 473537A - FUTEY SM OD fiber LC OD-LC OD dual 80m | 2 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 766755 | 303635 | 1533510 | 607269.9999 |  | 162139FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1131046765 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001114146 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 396 | 23ND001NW030685 | 394058 |  | RAN only | Expansion | 4000042940_150 | 4000042940 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 150 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 480972.9999 | 190465.0001 | 10100432.997 | 3999765.0023 |  | 162205FDAUCAUCFPRJBABT2023REV | 2023-01-20 | 2023-01-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1131046765 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001115661 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 397 | 23ND001NW030685 | 394059 |  | RAN only | Expansion | 4000043049_20 | 4000043049 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 20 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 10576816.9998 | 10153744.0002 | 31730450.9995 | 30461232.0005 |  | 162192FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1131106752 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001114214 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 398 | 23ND001NW030685 | 394061 |  | RAN only | Expansion | 4000042941_80 | 4000042941 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 80 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 87917.9999 | 84401.0002 | 87917.9999 | 84401.0002 |  | 162172FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1131106460 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001114185 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 399 | 23ND001NW030685 | 394062 |  | RAN only | Expansion | 4000042941_170 | 4000042941 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 170 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 20 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 351672.0003 | 337605 | 7033440.006 | 6752100.0005 |  | 162172FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1131106460 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001114185 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 400 | 23ND001NW030685 | 394063 |  | RAN only | Expansion | 4000042941_160 | 4000042941 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 160 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 10 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 203164.0001 | 195037.0002 | 2031640.0007 | 1950370.002 |  | 162172FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1131106460 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001114185 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 485 | 23ND001NW030685 | 407013 |  | RAN only | Expansion | 4000042943_120 | 4000042943 |  |  | KKNo3495 | 5. SVC | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 120 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 61637486.0001 | 39090493.6212 | 61637486.0001 | 39090493.6212 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1130887495 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 486 | 23ND001NW030685 | 407014 |  | RAN only | Expansion | 4000042943_120 | 4000042943 |  |  | KKNo3495 | 5. SVC | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852800 | 120 | 4100000512 | BTSS323 - Antennas Swap (Antennas, Brackets & Jumpers) for Disposal without PIM testing 3 Sectors Site | 1 |  | EJ | EJ | 16GSK0093 | KEDAMEAN_EP |  |  |  | 16GSK0093 | KEDAMEAN_EP | [12 empty] | 2023-02-10 |  |  |  | 2023-03-17 |  | 2023-04-15 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 558AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-04-14 | 2023-04-14 |  |  | IDR | 17413273.9999 | 11043498.3706 | 17413273.9999 | 11043498.3706 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_17%20-Mar-2023_%20_AOP%202022%20RAN%20Tomahawk%20_%20_Capacity_%20_NOKIA_%20_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_014.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42943 SVC 30% | TOP PO 4_42943 SVC 85% | TOP PO 4_42943 SVC 55% | TOP PO 4_42940 HW 15%,PO 4_43049 IM 15%,PO 4_42941 IM 15% | TOP PO 4_42940 HW 40%,PO 4_43049 IM 40%,PO 4_42941 IM 40% | TOP PO 4_42940 HW 25%,PO 4_43049 IM 25%,PO 4_42941 IM 25% |  | AOP2022PAC053 | 2023-05-29 | 2023-05-29 | [9 empty] | 1130887495 | [5 empty] | NO NEED CA |  |  |  |  | 2023-04-14 |  | 2023-06-21 |  | 170638 | 170638FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0669507 | 2023-05-29 | 2023_Q2 PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17862 | 22NDXXXNW642994 | 166450 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001080725 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17887 | 22NDXXXNW642994 | 172378 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001079482 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17888 | 22NDXXXNW642994 | 173097 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17889 | 22NDXXXNW642994 | 173098 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17890 | 22NDXXXNW642994 | 173099 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17891 | 22NDXXXNW642994 | 173100 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17892 | 22NDXXXNW642994 | 173101 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17893 | 22NDXXXNW642994 | 173102 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17894 | 22NDXXXNW642994 | 173103 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17895 | 22NDXXXNW642994 | 173104 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17896 | 22NDXXXNW642994 | 173105 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130961103 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17897 | 22NDXXXNW642994 | 173106 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17898 | 22NDXXXNW642994 | 173107 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17899 | 22NDXXXNW642994 | 173108 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17900 | 22NDXXXNW642994 | 173109 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17901 | 22NDXXXNW642994 | 173110 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17902 | 22NDXXXNW642994 | 173111 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17903 | 22NDXXXNW642994 | 173112 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17904 | 22NDXXXNW642994 | 173113 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17905 | 22NDXXXNW642994 | 173114 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17906 | 22NDXXXNW642994 | 173115 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17907 | 22NDXXXNW642994 | 173116 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 17908 | 22NDXXXNW642994 | 173117 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1162 | 22NDXXXNW642994 | 215788 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3486 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704994 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161329FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1131007649 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044358 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18265 | 22NDXXXNW642994 | 335530 |  | RAN Only | Integration | 4000041336_860 | 4000041336 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 860 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129995609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041336 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18266 | 22NDXXXNW642994 | 335531 |  | RAN Only | Integration | 4000041336_860 | 4000041336 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 860 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129995609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041336 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18267 | 22NDXXXNW642994 | 335532 |  | RAN Only | Integration | 4000041336_860 | 4000041336 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 860 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129995609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041336 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18268 | 22NDXXXNW642994 | 335533 |  | RAN Only | Integration | 4000041336_860 | 4000041336 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 860 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129995609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041336 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18321 | 22NDXXXNW642994 | 419850 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704994 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02LMP0056 | KAMPUNG_SUKOREJO_MT |  |  |  | 02LMP0056 | KAMPUNG_SUKOREJO_MT | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1085AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15%,PO 4_41231 HW 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40%,PO 4_41231 HW 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25%,PO 4_41231 HW 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130954517 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | NEED CA | 22NDXXXNW642994 | 170726FDAUCAUCFPRJSSAC2023 | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF}&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence | 2023-05-06 |  | 2023-06-21 |  | 170726 | 170726FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055221 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0559057 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18348 | 22NDXXXNW638553 | 149123 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18349 | 22NDXXXNW638553 | 149124 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18350 | 22NDXXXNW638553 | 149125 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18351 | 22NDXXXNW638553 | 149126 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18352 | 22NDXXXNW638553 | 149127 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18353 | 22NDXXXNW638553 | 149128 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18354 | 22NDXXXNW638553 | 149129 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18355 | 22NDXXXNW638553 | 149130 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18356 | 22NDXXXNW638553 | 149131 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415109 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18357 | 22NDXXXNW638553 | 149132 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18358 | 22NDXXXNW638553 | 149133 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18359 | 22NDXXXNW638553 | 149134 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18360 | 22NDXXXNW638553 | 149135 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18361 | 22NDXXXNW638553 | 149136 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18362 | 22NDXXXNW638553 | 149137 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18363 | 22NDXXXNW638553 | 149138 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18364 | 22NDXXXNW638553 | 149139 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18365 | 22NDXXXNW638553 | 149140 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18366 | 22NDXXXNW638553 | 149141 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18367 | 22NDXXXNW638553 | 149142 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18368 | 22NDXXXNW638553 | 149143 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406284 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18447 | 22NDXXXNW639741 | 162425 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 3 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 750111.9999 | 297043.9995 | 2250335.9998 | 891131.9986 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415549 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18448 | 22NDXXXNW639741 | 162426 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 3 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 68561.9998 | 27151 | 205685.9995 | 81453.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415549 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18449 | 22NDXXXNW639741 | 162427 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415549 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18450 | 22NDXXXNW639741 | 162428 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415549 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18451 | 22NDXXXNW639741 | 162429 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 8 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 636323.0003 | 251983.9998 | 5090584.0022 | 2015871.9984 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415549 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18452 | 22NDXXXNW639741 | 162430 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 5 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 272589.9999 | 107946 | 1362949.9997 | 539730.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415549 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18453 | 22NDXXXNW639741 | 162431 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3486 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415549 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18454 | 22NDXXXNW639741 | 162432 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18455 | 22NDXXXNW639741 | 162433 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18456 | 22NDXXXNW639741 | 162434 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18457 | 22NDXXXNW639741 | 162435 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18458 | 22NDXXXNW639741 | 162436 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 15 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 34873.0002 | 33213.0004 | 523095.0027 | 498195.0057 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18459 | 22NDXXXNW639741 | 162437 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18460 | 22NDXXXNW639741 | 162438 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18461 | 22NDXXXNW639741 | 162439 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18462 | 22NDXXXNW639741 | 162440 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18463 | 22NDXXXNW639741 | 162441 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18464 | 22NDXXXNW639741 | 162442 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18465 | 22NDXXXNW639741 | 162443 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 180 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 136047.0003 | 129571.0003 | 24488460.0576 | 23322780.054 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18466 | 22NDXXXNW639741 | 162444 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18467 | 22NDXXXNW639741 | 162445 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3486 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18669 | 22NDXXXNW642572 | 186256 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18670 | 22NDXXXNW642572 | 186257 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18671 | 22NDXXXNW642572 | 186258 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18672 | 22NDXXXNW642572 | 186259 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18673 | 22NDXXXNW642572 | 186260 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18674 | 22NDXXXNW642572 | 186261 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18675 | 22NDXXXNW642572 | 186262 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18676 | 22NDXXXNW642572 | 186263 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18677 | 22NDXXXNW642572 | 186264 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18678 | 22NDXXXNW642572 | 186265 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131278926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18679 | 22NDXXXNW642572 | 186266 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18680 | 22NDXXXNW642572 | 186268 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055221 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18681 | 22NDXXXNW642572 | 186269 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18682 | 22NDXXXNW642572 | 186270 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18683 | 22NDXXXNW642572 | 186271 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18684 | 22NDXXXNW642572 | 186272 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18685 | 22NDXXXNW642572 | 186273 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18686 | 22NDXXXNW642572 | 186274 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18687 | 22NDXXXNW642572 | 186275 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18688 | 22NDXXXNW642572 | 186276 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18689 | 22NDXXXNW642572 | 186277 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18690 | 22NDXXXNW642572 | 186278 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131287783 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1195 | 22NDXXXNW638553 | 214647 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3486 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704136 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161329FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131416060 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044358 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1200 | 22NDXXXNW642572 | 215489 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3543 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704639 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161329FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131285782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044358 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18774 | 22NDXXXNW638553 | 332392 |  | RAN Only | Integration | 4000041335_2270 | 4000041335 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 2270 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416872 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18775 | 22NDXXXNW638553 | 332393 |  | RAN Only | Integration | 4000041335_2270 | 4000041335 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 2270 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416872 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18776 | 22NDXXXNW638553 | 332394 |  | RAN Only | Integration | 4000041335_2270 | 4000041335 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 2270 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416872 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18777 | 22NDXXXNW638553 | 332395 |  | RAN Only | Integration | 4000041335_2270 | 4000041335 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704136 | 2270 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01JHO0096 | LABUY_TB |  |  |  | 01JHO0096 | LABUY_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 227AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_013.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416872 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638553 | 170817FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170817 | 170817FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603071 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18782 | 22NDXXXNW639741 | 332634 |  | RAN Only | Integration | 4000041335_2920 | 4000041335 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 2920 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130011780 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18783 | 22NDXXXNW639741 | 332635 |  | RAN Only | Integration | 4000041335_2920 | 4000041335 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 2920 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130011780 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18784 | 22NDXXXNW639741 | 332636 |  | RAN Only | Integration | 4000041335_2920 | 4000041335 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 2920 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130011780 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18785 | 22NDXXXNW639741 | 332637 |  | RAN Only | Integration | 4000041335_2920 | 4000041335 |  |  | KKNo3486 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704201 | 2920 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130011780 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18807 | 22NDXXXNW642572 | 334238 |  | RAN Only | Integration | 4000041335_7300 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 7300 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130386264 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18808 | 22NDXXXNW642572 | 334239 |  | RAN Only | Integration | 4000041335_7300 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 7300 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130386264 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18809 | 22NDXXXNW642572 | 334240 |  | RAN Only | Integration | 4000041335_7300 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 7300 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130386264 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 18810 | 22NDXXXNW642572 | 334241 |  | RAN Only | Integration | 4000041335_7300 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704639 | 7300 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02RAP0020 | BAKARAN_BATU_RAP_MT |  |  |  | 02RAP0020 | BAKARAN_BATU_RAP_MT | [12 empty] | 2023-04-28 |  |  |  | 2023-03-15 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 730AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130386264 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642572 | 170849FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-06 |  | 2023-06-21 |  | 170849 | 170849FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614580 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 502 | 23ND001NW031313 | 405458 |  | RAN and PS | Expansion | 4000042924_20 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 20 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 3 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 816232.9994 | 323228.0003 | 2448698.9983 | 969684.001 |  | 162131FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114141 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 503 | 23ND001NW031313 | 405459 |  | RAN and PS | Expansion | 4000042924_40 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 40 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 3 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 74604.9994 | 29543.9994 | 223814.9981 | 88631.9981 |  | 162131FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114141 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 504 | 23ND001NW031313 | 405460 |  | RAN and PS | Expansion | 4000042924_50 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 50 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 246116 | 97462 | 984464 | 389847.9999 |  | 162131FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114141 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 505 | 23ND001NW031313 | 405461 |  | RAN and PS | Expansion | 4000042924_10 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 10 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 446321.0001 | 176742.9999 | 1338963.0003 | 530228.9997 |  | 162163FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114176 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 506 | 23ND001NW031313 | 405462 |  | RAN and PS | Expansion | 4000042924_70 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 70 | 1100000124 | 473096A - ABIA AirScale Capacity | 1 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 23444883 | 9284174 | 23444883 | 9284174 |  | 162131FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114141 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 507 | 23ND001NW031313 | 405463 |  | RAN and PS | Expansion | 4000042924_110 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 110 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 41106017.0006 | 16277982.9994 | 41106017.0006 | 16277982.9994 |  | 162163FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114176 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 508 | 23ND001NW031313 | 405464 |  | RAN and PS | Expansion | 4000042924_120 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 120 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 2 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 39050659.9999 | 15464061.0002 | 78101319.9998 | 30928122.0004 |  | 162009FDAUCAUCFPRJBABT2022 | 2022-12-06 | 2022-12-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001088866 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 509 | 23ND001NW031313 | 405465 |  | RAN and PS | Expansion | 4000042924_140 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 140 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 16 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 561883.0003 | 222505.9999 | 8990128.0054 | 3560095.9979 |  | 162131FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114141 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 510 | 23ND001NW031313 | 405466 |  | RAN and PS | Expansion | 4000042924_80 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 80 | 1100000126 | 473308A - FUFBF SM OD fiber LC OD-LC OD dual 50m | 8 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 489420 | 193810 | 3915359.9997 | 1550479.9998 |  | 162009FDAUCAUCFPRJBABT2022 | 2022-12-06 | 2022-12-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001088866 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 511 | 23ND001NW031313 | 405467 |  | RAN and PS | Expansion | 4000042924_150 | 4000042924 |  |  | KKNo3495 | 1. HW | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 150 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 57 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 480972.9999 | 190465.0001 | 27415460.9917 | 10856505.0063 |  | 162201FDAUCAUCFPRJBABT2023REV | 2023-01-20 | 2023-01-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131008570 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001115657 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 512 | 23ND001NW031313 | 405468 |  | RAN and PS | Expansion | 4000042925_20 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 20 | 1300000820 | CP2018IM01 - Basic RF Module | 3 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 77454.9999 | 74356.9998 | 232364.9998 | 223070.9993 |  | 162132FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114142 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 513 | 23ND001NW031313 | 405469 |  | RAN and PS | Expansion | 4000042925_120 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 120 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 2129397.9998 | 2044222.0004 | 2129397.9998 | 2044222.0004 |  | 162164FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114177 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 514 | 23ND001NW031313 | 405470 |  | RAN and PS | Expansion | 4000042925_30 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 30 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 15 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 37946.9998 | 36429.0002 | 569204.9967 | 546435.003 |  | 162132FDAUCAUCFPRJBABT2023REV | 2023-01-13 | 2023-01-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114142 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 515 | 23ND001NW031313 | 405471 |  | RAN and PS | Expansion | 4000042925_70 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 70 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 87917.9999 | 84401.0002 | 87917.9999 | 84401.0002 |  | 162164FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114177 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 516 | 23ND001NW031313 | 405472 |  | RAN and PS | Expansion | 4000042925_80 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 80 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 87917.9999 | 84401.0002 | 87917.9999 | 84401.0002 |  | 162164FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114177 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 517 | 23ND001NW031313 | 405473 |  | RAN and PS | Expansion | 4000042925_160 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 160 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 12 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 351672.0003 | 337605 | 4220064.0036 | 4051260.0003 |  | 162164FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114177 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 518 | 23ND001NW031313 | 405474 |  | RAN and PS | Expansion | 4000042925_150 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 150 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 6 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 203164.0001 | 195037.0002 | 1218984.0004 | 1170222.0012 |  | 162164FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114177 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 519 | 23ND001NW031313 | 405475 |  | RAN and PS | Expansion | 4000042925_110 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 110 | 1300000820 | CP5012MA22 - Mat 2x10 power cable and clamp for RRH | 150 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 111654.0003 | 107187.9999 | 16748100.045 | 16078199.979 |  | 162164FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114177 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 520 | 23ND001NW031313 | 405476 |  | RAN and PS | Expansion | 4000042925_130 | 4000042925 |  |  | KKNo3495 | 3. IM | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 130 | 1300000820 | MCB 63A - MCB 63A | 3 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 288583.9997 | 277041 | 865751.9992 | 831122.9999 |  | 162164FDAUCAUCFPRJBABT2023 | 2023-01-16 | 2023-01-25 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131107406 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001114177 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 524 | 23ND001NW031313 | 408235 |  | RAN and PS | Expansion | 4000042927_440 | 4000042927 |  |  | KKNo3495 | 5. SVC | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 440 | 4100000512 | SB28 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with Power System Expansion | 1 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 66663057.9999 | 42277711.3836 | 66663057.9999 | 42277711.3836 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131007604 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  |  | 1. RESERVATION DONE |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 525 | 23ND001NW031313 | 408236 |  | RAN and PS | Expansion | 4000042927_440 | 4000042927 |  |  | KKNo3495 | 5. SVC | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 440 | 4100000512 | BTSS457 - Equipment Delivery from Vendor warehouse or Customer warehouse to site (RRU/Filter/BBU/Module) | 1 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 3358778.9998 | 2130137.642 | 3358778.9998 | 2130137.642 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131007604 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  |  | 1. RESERVATION DONE |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.21 RAN Tomhawk Q1 - Expansion Forecast | 528 | 23ND001NW031313 | 421260 |  | RAN and PS | Expansion | 4000042926_50 | 4000042926 |  |  | KKNo3495 | 8. IM PS | RAN Tomhawk Q1 - Expansion Forecast | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 50 | 1100001720 | REC-Mdl-Eltek - Rectifier Module 3K FP2 | 2 |  | EJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 5548209 | 3357776.0003 | 11096418.0001 | 6715552.0006 |  | 162271FDAUCAUCFPRJBABT2023 | 2023-04-03 | 2023-04-05 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131364802 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001163788 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.20 RAN Tomhawk Q1 - Expansion Actual | 761 | 23ND001NW031313 | 421261 |  | RAN and PS | Expansion | 4000042938_20 | 4000042938 |  |  | KKNo3495 | 8. IM PS | RAN Tomhawk Q1 - Expansion Actual | AOP 2022 RAN Tomahawk Q1 Expansion | BTS | 1000852175 | 20 | 1300000173 | SDA10-48100 Q - SDA10-48100 Q | 2 |  | CJ | EJ | 16SBY0351 | KUTISARI_SELATAN_SBY_PL |  |  |  | 16SBY0351 | KUTISARI_SELATAN_SBY_PL | [12 empty] | 2023-02-10 |  |  |  | 2023-02-03 |  | 2023-02-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 374AOP2022TOMAQ1EXPNOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 16247809 | 14298072 | 32495617.9999 | 28596144 |  | 162274FDAUCAUCFPRJBABT2023 | 2023-04-03 | 2023-04-05 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_%20_3-February-2023_%20_AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion_%20_Capacity_NOKIA_EAST%20JAVA_BALI%20NUSRA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230306_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_42927 SVC 30% | TOP PO 4_42927 SVC 85% | TOP PO 4_42927 SVC 55% | TOP PO 4_42924 HW 15%,PO 4_42925 IM 15%,PO 4_42926 IM PS 15%,PO 4_42938 IM PS 15% | TOP PO 4_42924 HW 40%,PO 4_42925 IM 40%,PO 4_42926 IM PS 40%,PO 4_42938 IM PS 40% | TOP PO 4_42924 HW 25%,PO 4_42925 IM 25%,PO 4_42926 IM PS 25%,PO 4_42938 IM PS 25% |  | AOP2022PAC051 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131360879 |  |  |  | 1000852175 |  | NO NEED CA |  |  |  |  | 2023-05-06 |  | 2023-06-21 |  | 170831 | 170831FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3495AUCAUCDKK2023_NOK (DONE) | 2023-06-08 |  |  | 5001163821 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0669400 | 2023-05-19 | 2023_Q2 PAC P05 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 614 | 22NDXXXNW639741 | 423392 |  | RAN Only | Integration | 4000041252_110 | 4000041252 |  |  | KKNo3486 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000704201 | 110 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | EJ Area 12 | NS | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL |  |  |  | 02KBJ0065 | DOLAT_RAKYAT_KARO_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-05 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 292AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-06 | 2023-05-06 |  |  | IDR | 34114367.9999 | 13509289.7287 | 34114367.9999 | 13509289.7287 |  | 161319FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_010.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41252 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41252 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41252 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131416246 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639741 | 170822FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-06 |  | 2023-06-21 |  | 170822 | 170822FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3486AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001049539 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541652 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19019 | 22NDXXXNW643649 | 181695 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961214 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19020 | 22NDXXXNW643649 | 181696 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 6 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 516365.9998 | 204480.9996 | 3098195.9988 | 1226885.9976 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961214 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19021 | 22NDXXXNW643649 | 181697 |  | RAN Only | Integration | 4000041221_350 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 350 | 1100000126 | 473310A - FUFBH SM OD fiber LC OD-LC OD dual 100m | 3 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 909990 | 360356 | 2729969.9999 | 1081068 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961214 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19022 | 22NDXXXNW643649 | 181698 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 2 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 1272646.0006 | 503967.9996 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961214 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19023 | 22NDXXXNW643649 | 181699 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961214 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19024 | 22NDXXXNW643649 | 181700 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 18 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 7956197.9976 | 3150647.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961214 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19025 | 22NDXXXNW643649 | 181701 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130954484 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19026 | 22NDXXXNW643649 | 181702 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130954484 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19063 | 22NDXXXNW643649 | 335968 |  | RAN Only | Integration | 4000041336_2150 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 2150 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1129995401 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19064 | 22NDXXXNW643649 | 335969 |  | RAN Only | Integration | 4000041336_2150 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705123 | 2150 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0010 | SARAN_PADANG_TB |  |  |  | 02PMR0010 | SARAN_PADANG_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-05-09 |  | 2023-05-09 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1214AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2009-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1129995401 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643649 | 170963FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170963 | 170963FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541853 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1210 | 22ND012NW034036 | 106186 |  | RAN and PS | Integration, Expansion | 4000041234_200 | 4000041234 |  |  | KKNo3488 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 200 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297044.3519 | 750111.9999 | 297044.3519 |  | 161423FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131415319 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055225 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1211 | 22ND012NW034036 | 106187 |  | RAN and PS | Integration, Expansion | 4000041234_210 | 4000041234 |  |  | KKNo3488 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 210 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27150.5523 | 68561.9998 | 27150.5523 |  | 161423FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131415319 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055225 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1212 | 22ND012NW034036 | 106188 |  | RAN and PS | Integration, Expansion | 4000041234_220 | 4000041234 |  |  | KKNo3488 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 220 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89566.884 | 226179 | 89566.884 |  | 161423FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131415319 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055225 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1213 | 22ND012NW034036 | 106190 |  | RAN and PS | Integration, Expansion | 4000041234_330 | 4000041234 |  |  | KKNo3488 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 330 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34114367.9999 | 13509289.7287 | 34114367.9999 | 13509289.7287 |  | 161423FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131415319 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055225 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1214 | 22ND012NW034036 | 106191 |  | RAN and PS | Integration, Expansion | 4000041234_340 | 4000041234 |  |  | KKNo3488 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 340 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 2 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9078 | 1272646.0006 | 503967.8156 |  | 161472FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131415319 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058067 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1215 | 22ND012NW034036 | 106192 |  | RAN and PS | Integration, Expansion | 4000041234_260 | 4000041234 |  |  | KKNo3488 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 260 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 272589.9999 | 107945.6401 | 272589.9999 | 107945.6401 |  | 161423FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131415319 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055225 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1216 | 22ND012NW034036 | 106193 |  | RAN and PS | Integration, Expansion | 4000041234_360 | 4000041234 |  |  | KKNo3488 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 360 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 11 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036.356 | 4862120.9985 | 1925399.9155 |  | 161594FDAUCAUCFPRJBABT2022 | 2022-10-24 | 2022-10-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131415319 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001062256 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.4 AOP 2022 Capacity Expansion Antenna | 19 | 22ND012NW034036 | 106194 |  | RAN and PS | Integration, Expansion | 4000041631_10 | 4000041631 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion Antenna | AOP 2022 MOCN Expansion | BTS | 1000691327 | 10 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 9572951.0002 | 9572951.0002 | 28718853.0005 | 28718853.0005 |  | 161552FDAUCAUCFPRJBABT2022 | 2022-10-19 | 2022-10-26 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131407624 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001061313 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1217 | 22ND012NW034036 | 106195 |  | RAN and PS | Integration, Expansion | 4000041235_250 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 250 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 2408959 | 2312600.64 | 7226877 | 6937801.92 |  | 161322FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001049542 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1218 | 22ND012NW034036 | 106197 |  | RAN and PS | Integration, Expansion | 4000041235_270 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 270 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1878625.9204 | 1956902.0003 | 1878625.9204 |  | 161473FDAUCAUCFPRJBABT2022 | 2022-10-15 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058068 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1219 | 22ND012NW034036 | 106198 |  | RAN and PS | Integration, Expansion | 4000041235_190 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 190 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33478.0801 | 174365.0009 | 167390.4007 |  | 161512FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058993 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1220 | 22ND012NW034036 | 106199 |  | RAN and PS | Integration, Expansion | 4000041235_200 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 200 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 77564.16 | 80795.9997 | 77564.16 |  | 161473FDAUCAUCFPRJBABT2022 | 2022-10-15 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058068 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1221 | 22ND012NW034036 | 106200 |  | RAN and PS | Integration, Expansion | 4000041235_210 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 210 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 77564.16 | 80795.9997 | 77564.16 |  | 161473FDAUCAUCFPRJBABT2022 | 2022-10-15 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058068 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1222 | 22ND012NW034036 | 106201 |  | RAN and PS | Integration, Expansion | 4000041235_220 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 220 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 85623.0003 | 82198.08 | 85623.0003 | 82198.08 |  | 161473FDAUCAUCFPRJBABT2022 | 2022-10-15 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058068 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1223 | 22ND012NW034036 | 106202 |  | RAN and PS | Integration, Expansion | 4000041235_300 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 300 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 310257.5998 | 2585480.0012 | 2482060.7986 |  | 161512FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058993 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1224 | 22ND012NW034036 | 106203 |  | RAN and PS | Integration, Expansion | 4000041235_290 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 290 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 179238.7202 | 746828.0013 | 716954.8809 |  | 161512FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058993 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1225 | 22ND012NW034036 | 106205 |  | RAN and PS | Integration, Expansion | 4000041235_280 | 4000041235 |  |  | KKNo3488 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 280 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 254597.7599 | 265205.9998 | 254597.7599 |  | 161512FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1131406351 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058993 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1230 | 22ND012NW034036 | 302486 |  | RAN and PS | Integration, Expansion | 4000041471_210 | 4000041471 |  |  | KKNo3488 | 5. SVC | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 210 | 4100000512 | SB3 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with Power System Expansion | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 90128608 | 57159563.1933 | 90128608 | 57159563.1933 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1130489368 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1231 | 22ND012NW034036 | 302487 |  | RAN and PS | Integration, Expansion | 4000041471_210 | 4000041471 |  |  | KKNo3488 | 5. SVC | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691327 | 210 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 2 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 14871605.0002 | 9431571.8912 | 14871605.0002 | 9431571.8912 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1130489368 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.8 AOP 2022 Integration PS | 497 | 22ND012NW034036 | 370441 |  | RAN and PS | Integration, Expansion | 4000041406_210 | 4000041406 |  |  | KKNo3488 | 8. IM PS | AOP 2022 Integration PS | AOP 2022 MOCN Expansion | BTS | 1000691327 | 210 | 1300000173 | SDA10-48100 Q - SDA10-48100 Q | 1 |  | NS Area 1 | NS | 02STB0065 | TELUK_MEKU_MT |  |  |  | 02STB0065 | TELUK_MEKU_MT | [12 empty] | 2022-12-30 |  |  |  | 2023-03-13 |  | 2023-04-18 |  |  | Batch 3_035/PCG-CR/10/2022 | CR REDUCE DONE; CR RELOC NA |  | 1. RESERVATION DONE |  | 3561AOP2022MOCNEXPAREA2NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 15134518 | 13318376 | 15134518 | 13318376 |  | 161239FDAUCAUCFPRJBABT2022 | 2022-09-19 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_100%20sites_20230503.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41471 SVC 30% | TOP PO 4_41471 SVC 85% | TOP PO 4_41471 SVC 55% | TOP PO 4_41234 HW 15%,PO 4_41631 IM 15%,PO 4_41235 IM 15%,PO 4_41406 IM PS 15% | TOP PO 4_41234 HW 40%,PO 4_41631 IM 40%,PO 4_41235 IM 40%,PO 4_41406 IM PS 40% | TOP PO 4_41234 HW 25%,PO 4_41631 IM 25%,PO 4_41235 IM 25%,PO 4_41406 IM PS 25% |  | AOP2022PAC050 | 2023-05-19 | 2023-05-19 | [9 empty] | 1130805221 | [5 empty] | NO NEED CA |  |  |  |  | 2023-05-27 |  | 2023-06-21 |  | 170919 | 170919FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3488AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001048006 | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0609839 | 2023-05-19 | 2023_Q2 EXP PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19129 | 22NDXXXNW640182 | 150051 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19130 | 22NDXXXNW640182 | 150052 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19131 | 22NDXXXNW640182 | 150053 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19132 | 22NDXXXNW640182 | 150054 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19133 | 22NDXXXNW640182 | 150055 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19134 | 22NDXXXNW640182 | 150056 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19135 | 22NDXXXNW640182 | 150057 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19136 | 22NDXXXNW640182 | 150058 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19137 | 22NDXXXNW640182 | 150059 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129998411 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041221 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19138 | 22NDXXXNW640182 | 150060 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19139 | 22NDXXXNW640182 | 150061 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19140 | 22NDXXXNW640182 | 150062 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19141 | 22NDXXXNW640182 | 150063 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19142 | 22NDXXXNW640182 | 150064 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19143 | 22NDXXXNW640182 | 150065 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19144 | 22NDXXXNW640182 | 150066 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19145 | 22NDXXXNW640182 | 150067 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19146 | 22NDXXXNW640182 | 150068 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19147 | 22NDXXXNW640182 | 150069 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19148 | 22NDXXXNW640182 | 150070 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130085538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041222 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19191 | 22NDXXXNW640215 | 153517 |  | RAN Only | Integration, Relinquish | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19192 | 22NDXXXNW640215 | 153518 |  | RAN Only | Integration, Relinquish | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19193 | 22NDXXXNW640215 | 153519 |  | RAN Only | Integration, Relinquish | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19194 | 22NDXXXNW640215 | 153520 |  | RAN Only | Integration, Relinquish | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19195 | 22NDXXXNW640215 | 153521 |  | RAN Only | Integration, Relinquish | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19196 | 22NDXXXNW640215 | 153522 |  | RAN Only | Integration, Relinquish | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19197 | 22NDXXXNW640215 | 153523 |  | RAN Only | Integration, Relinquish | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19198 | 22NDXXXNW640215 | 153524 |  | RAN Only | Integration, Relinquish | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19199 | 22NDXXXNW640215 | 153525 |  | RAN Only | Integration, Relinquish | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445819 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19200 | 22NDXXXNW640215 | 153529 |  | RAN Only | Integration, Relinquish | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442563 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19201 | 22NDXXXNW640215 | 153530 |  | RAN Only | Integration, Relinquish | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442563 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19202 | 22NDXXXNW640215 | 153531 |  | RAN Only | Integration, Relinquish | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442563 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19203 | 22NDXXXNW640215 | 153533 |  | RAN Only | Integration, Relinquish | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442563 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19204 | 22NDXXXNW640215 | 153534 |  | RAN Only | Integration, Relinquish | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442563 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19205 | 22NDXXXNW640215 | 153535 |  | RAN Only | Integration, Relinquish | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442563 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19206 | 22NDXXXNW640215 | 153536 |  | RAN Only | Integration, Relinquish | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442563 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19207 | 22NDXXXNW640215 | 153537 |  | RAN Only | Integration, Relinquish | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442563 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19208 | 22NDXXXNW638475 | 157503 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 3 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 2250335.9998 | 891131.9986 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131414811 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19209 | 22NDXXXNW638475 | 157504 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131414811 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19210 | 22NDXXXNW638475 | 157505 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131414811 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19211 | 22NDXXXNW638475 | 157506 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131414811 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19212 | 22NDXXXNW638475 | 157507 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 10 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 6363230.0028 | 2519839.9981 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131414811 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19213 | 22NDXXXNW638475 | 157508 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 4 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 272589.9999 | 107946 | 1090359.9998 | 431784.0001 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131414811 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19214 | 22NDXXXNW638475 | 157509 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131414811 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19215 | 22NDXXXNW638475 | 157510 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19216 | 22NDXXXNW638475 | 157511 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19217 | 22NDXXXNW638475 | 157512 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19218 | 22NDXXXNW638475 | 157513 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19219 | 22NDXXXNW638475 | 157514 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 15 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 523095.0027 | 498195.0057 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19220 | 22NDXXXNW638475 | 157515 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19221 | 22NDXXXNW638475 | 157516 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19222 | 22NDXXXNW638475 | 157517 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19223 | 22NDXXXNW638475 | 157518 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19224 | 22NDXXXNW638475 | 157519 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19225 | 22NDXXXNW638475 | 157520 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19226 | 22NDXXXNW638475 | 157521 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 150 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 20407050.048 | 19435650.045 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19227 | 22NDXXXNW638475 | 157522 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 320 | 1300000820 | MCB 63A - MCB 63A | 3 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 795617.9995 | 757745.9993 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19228 | 22NDXXXNW638475 | 157523 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131406864 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19229 | 22NDXXXNW643093 | 158115 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130961197 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001079482 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19230 | 22NDXXXNW643093 | 158116 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130961197 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001080725 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19231 | 22NDXXXNW643093 | 158117 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 12 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 516365.9998 | 204480.9996 | 6196391.9976 | 2453771.9952 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130961197 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19232 | 22NDXXXNW643093 | 158118 |  | RAN Only | Integration | 4000041221_350 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 350 | 1100000126 | 473310A - FUFBH SM OD fiber LC OD-LC OD dual 100m | 6 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 909990 | 360356 | 5459939.9999 | 2162136 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130961197 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19233 | 22NDXXXNW643093 | 158119 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130961197 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19234 | 22NDXXXNW643093 | 158120 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19235 | 22NDXXXNW643093 | 158121 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19236 | 22NDXXXNW643093 | 158122 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19237 | 22NDXXXNW643093 | 158123 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19273 | 22NDXXXNW639890 | 164656 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19274 | 22NDXXXNW639890 | 164657 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19275 | 22NDXXXNW639890 | 164658 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19276 | 22NDXXXNW639890 | 164659 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19277 | 22NDXXXNW639890 | 164660 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19278 | 22NDXXXNW639890 | 164661 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19279 | 22NDXXXNW639890 | 164662 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19280 | 22NDXXXNW639890 | 164663 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19281 | 22NDXXXNW639890 | 164664 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19282 | 22NDXXXNW639890 | 164665 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19283 | 22NDXXXNW639890 | 164666 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19284 | 22NDXXXNW639890 | 164667 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19285 | 22NDXXXNW639890 | 164669 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19286 | 22NDXXXNW639890 | 164670 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19287 | 22NDXXXNW639890 | 164671 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19288 | 22NDXXXNW639890 | 164672 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19289 | 22NDXXXNW639890 | 164673 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19290 | 22NDXXXNW639890 | 164674 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19291 | 22NDXXXNW639890 | 164675 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19292 | 22NDXXXNW639890 | 164676 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19293 | 22NDXXXNW639890 | 164677 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19294 | 22NDXXXNW639890 | 164678 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3628 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131442606 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19295 | 22NDXXXNW639868 | 164925 |  | RAN Only | Integration, Expansion | 4000041221_240 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19296 | 22NDXXXNW639868 | 164926 |  | RAN Only | Integration, Expansion | 4000041221_260 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19297 | 22NDXXXNW639868 | 164927 |  | RAN Only | Integration, Expansion | 4000041221_270 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19298 | 22NDXXXNW639868 | 164928 |  | RAN Only | Integration, Expansion | 4000041221_230 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19299 | 22NDXXXNW639868 | 164929 |  | RAN Only | Integration, Expansion | 4000041221_280 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19300 | 22NDXXXNW639868 | 164930 |  | RAN Only | Integration, Expansion | 4000041221_400 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19301 | 22NDXXXNW639868 | 164931 |  | RAN Only | Integration, Expansion | 4000041221_420 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19302 | 22NDXXXNW639868 | 164932 |  | RAN Only | Integration, Expansion | 4000041221_320 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19303 | 22NDXXXNW639868 | 164933 |  | RAN Only | Integration, Expansion | 4000041221_380 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19304 | 22NDXXXNW639868 | 164934 |  | RAN Only | Integration, Expansion | 4000041221_440 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19305 | 22NDXXXNW639868 | 164935 |  | RAN Only | Integration, Expansion | 4000041222_330 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19306 | 22NDXXXNW639868 | 164936 |  | RAN Only | Integration, Expansion | 4000041222_290 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19307 | 22NDXXXNW639868 | 164937 |  | RAN Only | Integration, Expansion | 4000041222_200 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055221 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19308 | 22NDXXXNW639868 | 164938 |  | RAN Only | Integration, Expansion | 4000041222_310 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19309 | 22NDXXXNW639868 | 164939 |  | RAN Only | Integration, Expansion | 4000041222_220 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19310 | 22NDXXXNW639868 | 164940 |  | RAN Only | Integration, Expansion | 4000041222_230 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19311 | 22NDXXXNW639868 | 164941 |  | RAN Only | Integration, Expansion | 4000041222_270 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19312 | 22NDXXXNW639868 | 164942 |  | RAN Only | Integration, Expansion | 4000041222_280 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19313 | 22NDXXXNW639868 | 164943 |  | RAN Only | Integration, Expansion | 4000041222_360 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19314 | 22NDXXXNW639868 | 164944 |  | RAN Only | Integration, Expansion | 4000041222_350 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19315 | 22NDXXXNW639868 | 164945 |  | RAN Only | Integration, Expansion | 4000041222_300 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19316 | 22NDXXXNW639868 | 164946 |  | RAN Only | Integration, Expansion | 4000041222_320 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19317 | 22NDXXXNW639868 | 164947 |  | RAN Only | Integration, Expansion | 4000041222_190 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131407956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19345 | 22NDXXXNW650186 | 166872 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131277913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19346 | 22NDXXXNW650186 | 166873 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 6 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 516365.9998 | 204480.9996 | 3098195.9988 | 1226885.9976 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131277913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19347 | 22NDXXXNW650186 | 166874 |  | RAN Only | Integration | 4000041221_360 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 360 | 1100000126 | 473537A - FUTEY SM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 704643 | 279039 | 2113929 | 837117 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131277913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19348 | 22NDXXXNW650186 | 166875 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 2 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 1272646.0006 | 503967.9996 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131277913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19349 | 22NDXXXNW650186 | 166877 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 17 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 7514186.9978 | 2975611.9995 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131277913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19350 | 22NDXXXNW650186 | 166878 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131288978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19351 | 22NDXXXNW650186 | 166879 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131288978 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19383 | 22NDXXXNW653242 | 173186 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130808253 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19384 | 22NDXXXNW653242 | 173187 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 6 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 516365.9998 | 204480.9996 | 3098195.9988 | 1226885.9976 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130808253 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19385 | 22NDXXXNW653242 | 173188 |  | RAN Only | Integration | 4000041221_350 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 350 | 1100000126 | 473310A - FUFBH SM OD fiber LC OD-LC OD dual 100m | 3 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 909990 | 360356 | 2729969.9999 | 1081068 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130808253 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19386 | 22NDXXXNW653242 | 173189 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 2 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 1272646.0006 | 503967.9996 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130808253 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19387 | 22NDXXXNW653242 | 173190 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130808253 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19388 | 22NDXXXNW653242 | 173191 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3543 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 13 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 5746142.9983 | 2275467.9996 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130808253 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19389 | 22NDXXXNW653242 | 173192 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130785061 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19390 | 22NDXXXNW653242 | 173193 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3543 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130785061 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19395 | 22NDXXXNW642736 | 182368 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19396 | 22NDXXXNW642736 | 182369 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19397 | 22NDXXXNW642736 | 182370 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19398 | 22NDXXXNW642736 | 182371 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19399 | 22NDXXXNW642736 | 182372 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19400 | 22NDXXXNW642736 | 182373 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19401 | 22NDXXXNW642736 | 182374 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19402 | 22NDXXXNW642736 | 182375 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19403 | 22NDXXXNW642736 | 182376 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19404 | 22NDXXXNW642736 | 182377 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19405 | 22NDXXXNW642736 | 182378 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 19 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 8398208.9975 | 3325683.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346875 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19406 | 22NDXXXNW642736 | 182379 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055221 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19407 | 22NDXXXNW642736 | 182380 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19408 | 22NDXXXNW642736 | 182381 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19409 | 22NDXXXNW642736 | 182382 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19410 | 22NDXXXNW642736 | 182383 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19411 | 22NDXXXNW642736 | 182384 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19412 | 22NDXXXNW642736 | 182385 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19413 | 22NDXXXNW642736 | 182386 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19414 | 22NDXXXNW642736 | 182387 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19415 | 22NDXXXNW642736 | 182388 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19416 | 22NDXXXNW642736 | 182389 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044890 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19417 | 22NDXXXNW642688 | 182406 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19418 | 22NDXXXNW642688 | 182407 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19419 | 22NDXXXNW642688 | 182408 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19420 | 22NDXXXNW642688 | 182409 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19421 | 22NDXXXNW642688 | 182410 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19422 | 22NDXXXNW642688 | 182411 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19423 | 22NDXXXNW642688 | 182412 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19424 | 22NDXXXNW642688 | 182413 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19425 | 22NDXXXNW642688 | 182414 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040525 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19426 | 22NDXXXNW642688 | 182415 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19427 | 22NDXXXNW642688 | 182416 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157915 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19428 | 22NDXXXNW642688 | 182417 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19429 | 22NDXXXNW642688 | 182418 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19430 | 22NDXXXNW642688 | 182419 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055221 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19431 | 22NDXXXNW642688 | 182420 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19432 | 22NDXXXNW642688 | 182421 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19433 | 22NDXXXNW642688 | 182422 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19434 | 22NDXXXNW642688 | 182423 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19435 | 22NDXXXNW642688 | 182424 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19436 | 22NDXXXNW642688 | 182425 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19437 | 22NDXXXNW642688 | 182426 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19438 | 22NDXXXNW642688 | 182427 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19439 | 22NDXXXNW642688 | 182428 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19440 | 22NDXXXNW656130 | 182806 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001079482 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19441 | 22NDXXXNW656130 | 182807 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001080725 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19442 | 22NDXXXNW656130 | 182808 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 750111.9999 | 297043.9995 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19443 | 22NDXXXNW656130 | 182809 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 68561.9998 | 27151 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19444 | 22NDXXXNW656130 | 182810 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19445 | 22NDXXXNW656130 | 182811 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19446 | 22NDXXXNW656130 | 182812 |  | RAN Only | Integration | 4000041221_310 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 310 | 1100000124 | 473098A - AMIA AirScale Subrack | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 7289110 | 2886488 | 7289110 | 2886488 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19447 | 22NDXXXNW656130 | 182813 |  | RAN Only | Integration | 4000041221_370 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 370 | 1100000124 | 473764A - ASIB AirScale Common | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 30228098.9999 | 11970327 | 30228098.9999 | 11970327 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19448 | 22NDXXXNW656130 | 182814 |  | RAN Only | Integration | 4000041221_300 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 300 | 1100000124 | 473096A - ABIA AirScale Capacity | 3 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 21545691 | 8532093.9999 | 64637073.0001 | 25596281.9998 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19449 | 22NDXXXNW656130 | 182815 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19450 | 22NDXXXNW656130 | 182816 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 20 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 516365.9998 | 204480.9996 | 10327319.996 | 4089619.992 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19451 | 22NDXXXNW656130 | 182817 |  | RAN Only | Integration | 4000041221_340 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 340 | 1100000126 | 473308A - FUFBF SM OD fiber LC OD-LC OD dual 50m | 10 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 449774 | 178111 | 4497740.0005 | 1781109.9999 |  | 161989FDAUCAUCFPRJBABT2022 | 2022-12-07 | 2022-12-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001089583 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19452 | 22NDXXXNW656130 | 182818 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130722414 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19453 | 22NDXXXNW656130 | 182819 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 71181.0004 | 67792.9998 | 71181.0004 | 67792.9998 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055221 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19454 | 22NDXXXNW656130 | 182820 |  | RAN Only | Integration | 4000041222_210 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 210 | 1300000820 | CP2018IM03 - Basic System Module | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 206511.0001 | 196681 | 206511.0001 | 196681 |  | 161765FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-29 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001079445 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19455 | 22NDXXXNW656130 | 182821 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19456 | 22NDXXXNW656130 | 182822 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 5 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 368104.9987 | 350585.0017 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19457 | 22NDXXXNW656130 | 182823 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19458 | 22NDXXXNW656130 | 182824 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19459 | 22NDXXXNW656130 | 182825 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19460 | 22NDXXXNW656130 | 182826 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19461 | 22NDXXXNW656130 | 182827 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19462 | 22NDXXXNW656130 | 182828 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19463 | 22NDXXXNW656130 | 182829 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19464 | 22NDXXXNW656130 | 182830 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 50 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 6802350.016 | 6478550.015 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19465 | 22NDXXXNW656130 | 182831 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130671143 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19492 | 22NDXXXNW653167 | 184237 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705636 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 2 |  | NS Area 1 | NS | 02PMS0004 | SIBATU_MT |  |  |  | 02PMS0004 | SIBATU_MT | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2022-11-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1727AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 516365.9998 | 204480.9996 | 1032731.9996 | 408961.9992 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130437011 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653167 | 170945FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170945 | 170945FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599740 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19493 | 22NDXXXNW653167 | 184238 |  | RAN Only | Integration | 4000041221_360 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705636 | 360 | 1100000126 | 473537A - FUTEY SM OD fiber LC OD-LC OD dual 80m | 1 |  | NS Area 1 | NS | 02PMS0004 | SIBATU_MT |  |  |  | 02PMS0004 | SIBATU_MT | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2022-11-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1727AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 704643 | 279039 | 704643 | 279039 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130437011 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653167 | 170945FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170945 | 170945FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599740 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19494 | 22NDXXXNW653167 | 184239 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705636 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 6 |  | NS Area 1 | NS | 02PMS0004 | SIBATU_MT |  |  |  | 02PMS0004 | SIBATU_MT | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2022-11-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1727AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 2652065.9992 | 1050215.9998 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130437011 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653167 | 170945FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170945 | 170945FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599740 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19495 | 22NDXXXNW653167 | 184240 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705636 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMS0004 | SIBATU_MT |  |  |  | 02PMS0004 | SIBATU_MT | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2022-11-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1727AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130419352 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653167 | 170945FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170945 | 170945FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599740 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19500 | 22NDXXXNW653181 | 185371 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705649 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 2 |  | NS Area 1 | NS | 02PMS0065 | SPKRG_SARI_TB |  |  |  | 02PMS0065 | SPKRG_SARI_TB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 516365.9998 | 204480.9996 | 1032731.9996 | 408961.9992 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130846370 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653181 | 170943FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170943 | 170943FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001058062 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615137 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19501 | 22NDXXXNW653181 | 185372 |  | RAN Only | Integration | 4000041221_360 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705649 | 360 | 1100000126 | 473537A - FUTEY SM OD fiber LC OD-LC OD dual 80m | 1 |  | NS Area 1 | NS | 02PMS0065 | SPKRG_SARI_TB |  |  |  | 02PMS0065 | SPKRG_SARI_TB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 704643 | 279039 | 704643 | 279039 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130846370 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653181 | 170943FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170943 | 170943FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001055220 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615137 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19502 | 22NDXXXNW653181 | 185373 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705649 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 7 |  | NS Area 1 | NS | 02PMS0065 | SPKRG_SARI_TB |  |  |  | 02PMS0065 | SPKRG_SARI_TB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 3094076.9991 | 1225251.9998 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130846370 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653181 | 170943FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-27 |  | 2023-06-21 |  | 170943 | 170943FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615137 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19503 | 22NDXXXNW653181 | 185374 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705649 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMS0065 | SPKRG_SARI_TB |  |  |  | 02PMS0065 | SPKRG_SARI_TB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130845605 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653181 | 170943FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-27 |  | 2023-06-21 |  | 170943 | 170943FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615137 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19520 | 22NDXXXNW642701 | 190063 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 3 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 750111.9999 | 297043.9995 | 2250335.9998 | 891131.9986 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131346812 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19521 | 22NDXXXNW642701 | 190064 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 3 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 68561.9998 | 27151 | 205685.9995 | 81453.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131346812 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040523 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19522 | 22NDXXXNW642701 | 190065 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131346812 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040524 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19523 | 22NDXXXNW642701 | 190066 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131346812 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040522 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19524 | 22NDXXXNW642701 | 190067 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 8 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 636323.0003 | 251983.9998 | 5090584.0022 | 2015871.9984 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131346812 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19525 | 22NDXXXNW642701 | 190068 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 4 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 822312 | 325635.9999 | 3289247.9999 | 1302543.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131346812 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001047195 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19526 | 22NDXXXNW642701 | 190069 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131346812 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040526 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19527 | 22NDXXXNW642701 | 190070 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19528 | 22NDXXXNW642701 | 190071 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19529 | 22NDXXXNW642701 | 190072 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19530 | 22NDXXXNW642701 | 190073 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19531 | 22NDXXXNW642701 | 190074 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 15 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34873.0002 | 33213.0004 | 523095.0027 | 498195.0057 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19532 | 22NDXXXNW642701 | 190075 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040527 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19533 | 22NDXXXNW642701 | 190076 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19534 | 22NDXXXNW642701 | 190077 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19535 | 22NDXXXNW642701 | 190078 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19536 | 22NDXXXNW642701 | 190079 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19537 | 22NDXXXNW642701 | 190080 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19538 | 22NDXXXNW642701 | 190081 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 180 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 136047.0003 | 129571.0003 | 24488460.0576 | 23322780.054 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19539 | 22NDXXXNW642701 | 190082 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 320 | 1300000820 | MCB 63A - MCB 63A | 3 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 265205.9998 | 252581.9998 | 795617.9995 | 757745.9993 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131378851 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040530 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1307 | 22NDXXXNW639890 | 214849 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3628 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704254 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161329FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131447326 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044358 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1308 | 22NDXXXNW640182 | 214901 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704358 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161329FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129990559 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044358 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1309 | 22NDXXXNW642688 | 215593 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704755 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161329FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131144702 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044358 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1310 | 22NDXXXNW642736 | 215630 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704803 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161329FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131345800 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001044358 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19545 | 22NDXXXNW638475 | 332116 |  | RAN Only | Integration | 4000041335_1490 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 1490 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416426 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19546 | 22NDXXXNW638475 | 332117 |  | RAN Only | Integration | 4000041335_1490 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 1490 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416426 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19547 | 22NDXXXNW638475 | 332118 |  | RAN Only | Integration | 4000041335_1490 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 1490 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416426 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19548 | 22NDXXXNW638475 | 332119 |  | RAN Only | Integration | 4000041335_1490 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704058 | 1490 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416426 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19549 | 22NDXXXNW639868 | 332752 |  | RAN Only | Integration, Expansion | 4000041335_3230 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 3230 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130417183 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19550 | 22NDXXXNW639868 | 332753 |  | RAN Only | Integration, Expansion | 4000041335_3230 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 3230 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130417183 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19551 | 22NDXXXNW639868 | 332754 |  | RAN Only | Integration, Expansion | 4000041335_3230 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 3230 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130417183 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19552 | 22NDXXXNW639868 | 332755 |  | RAN Only | Integration, Expansion | 4000041335_3230 | 4000041335 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704232 | 3230 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KIS0114 | AIR_JOMAN_CM |  |  |  | 02KIS0114 | AIR_JOMAN_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 323AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130417183 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639868 | 170925FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170925 | 170925FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606247 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19557 | 22NDXXXNW639890 | 332839 |  | RAN Only | Integration | 4000041335_3450 | 4000041335 |  |  | KKNo3628 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 3450 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417478 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19558 | 22NDXXXNW639890 | 332840 |  | RAN Only | Integration | 4000041335_3450 | 4000041335 |  |  | KKNo3628 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 3450 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417478 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19559 | 22NDXXXNW639890 | 332841 |  | RAN Only | Integration | 4000041335_3450 | 4000041335 |  |  | KKNo3628 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 3450 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417478 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19560 | 22NDXXXNW639890 | 332842 |  | RAN Only | Integration | 4000041335_3450 | 4000041335 |  |  | KKNo3628 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704254 | 3450 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KIS0100 | DESA_SUBUR_MT |  |  |  | 02KIS0100 | DESA_SUBUR_MT | [12 empty] | 2022-10-28 |  |  |  | 2023-05-16 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 345AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2016-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417478 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639890 | 170928FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170928 | 170928FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606273 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19561 | 22NDXXXNW640182 | 333222 |  | RAN Only | Integration | 4000041335_4490 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 4490 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129951215 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041335 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19562 | 22NDXXXNW640182 | 333223 |  | RAN Only | Integration | 4000041335_4490 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 4490 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129951215 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041335 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19563 | 22NDXXXNW640182 | 333224 |  | RAN Only | Integration | 4000041335_4490 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 4490 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129951215 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041335 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19564 | 22NDXXXNW640182 | 333225 |  | RAN Only | Integration | 4000041335_4490 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704358 | 4490 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01KRB0027 | TANJUNG_SEUMANTOH_CM |  |  |  | 01KRB0027 | TANJUNG_SEUMANTOH_CM | [12 empty] | 2022-12-25 |  |  |  | 2022-12-16 |  | 2022-09-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 449AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_16-December-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1129951215 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640182 | 170938FDAUCAUCFPRJSSAC2023REV | 4000041335 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-05-28 |  | 2023-06-21 |  | 170938 | 170938FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0558888 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19565 | 22NDXXXNW640215 | 333332 |  | RAN Only | Integration, Relinquish | 4000041335_4820 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 4820 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19566 | 22NDXXXNW640215 | 333333 |  | RAN Only | Integration, Relinquish | 4000041335_4820 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 4820 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19567 | 22NDXXXNW640215 | 333334 |  | RAN Only | Integration, Relinquish | 4000041335_4820 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 4820 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19568 | 22NDXXXNW640215 | 333335 |  | RAN Only | Integration, Relinquish | 4000041335_4820 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 4820 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19581 | 22NDXXXNW642688 | 334671 |  | RAN Only | Integration | 4000041335_8460 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 8460 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415352 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19582 | 22NDXXXNW642688 | 334672 |  | RAN Only | Integration | 4000041335_8460 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 8460 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415352 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19583 | 22NDXXXNW642688 | 334673 |  | RAN Only | Integration | 4000041335_8460 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 8460 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415352 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19584 | 22NDXXXNW642688 | 334674 |  | RAN Only | Integration | 4000041335_8460 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704755 | 8460 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0051 | MANIK_REJO_MT |  |  |  | 02PMR0051 | MANIK_REJO_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-09 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 846AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415352 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642688 | 170968FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170968 | 170968FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614685 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19585 | 22NDXXXNW642701 | 334721 |  | RAN Only | Integration | 4000041335_8590 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 8590 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995079 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19586 | 22NDXXXNW642701 | 334722 |  | RAN Only | Integration | 4000041335_8590 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 8590 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995079 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19587 | 22NDXXXNW642701 | 334723 |  | RAN Only | Integration | 4000041335_8590 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 8590 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995079 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19588 | 22NDXXXNW642701 | 334724 |  | RAN Only | Integration | 4000041335_8590 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704768 | 8590 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995079 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19589 | 22NDXXXNW642736 | 334839 |  | RAN Only | Integration | 4000041335_8940 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 8940 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415042 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19590 | 22NDXXXNW642736 | 334840 |  | RAN Only | Integration | 4000041335_8940 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 8940 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415042 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19591 | 22NDXXXNW642736 | 334841 |  | RAN Only | Integration | 4000041335_8940 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 8940 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415042 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19592 | 22NDXXXNW643093 | 335858 |  | RAN Only | Integration | 4000041336_1750 | 4000041336 |  |  | KKNo3628 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 1750 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19593 | 22NDXXXNW643093 | 335859 |  | RAN Only | Integration | 4000041336_1750 | 4000041336 |  |  | KKNo3628 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 1750 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19594 | 22NDXXXNW643093 | 335860 |  | RAN Only | Integration | 4000041336_1750 | 4000041336 |  |  | KKNo3628 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 1750 | 4100000512 | BTSS454 - BBU/RRU/Filter/Module Dismantle for Redeployment | 1 |  | NS Area 1 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 5733695.0001 | 2010233.4669 | 5733695.0001 | 2010233.4669 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19617 | 22NDXXXNW653167 | 337341 |  | RAN Only | Integration | 4000041336_7280 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705636 | 7280 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMS0004 | SIBATU_MT |  |  |  | 02PMS0004 | SIBATU_MT | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2022-11-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1727AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130011104 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653167 | 170945FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170945 | 170945FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599740 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19618 | 22NDXXXNW653167 | 337342 |  | RAN Only | Integration | 4000041336_7280 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705636 | 7280 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMS0004 | SIBATU_MT |  |  |  | 02PMS0004 | SIBATU_MT | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2022-11-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1727AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130011104 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653167 | 170945FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170945 | 170945FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599740 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19622 | 22NDXXXNW653181 | 337374 |  | RAN Only | Integration | 4000041336_7410 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705649 | 7410 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMS0065 | SPKRG_SARI_TB |  |  |  | 02PMS0065 | SPKRG_SARI_TB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653181 | 170943FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170943 | 170943FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615137 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19623 | 22NDXXXNW653181 | 337375 |  | RAN Only | Integration | 4000041336_7410 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705649 | 7410 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMS0065 | SPKRG_SARI_TB |  |  |  | 02PMS0065 | SPKRG_SARI_TB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653181 | 170943FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170943 | 170943FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615137 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19628 | 22NDXXXNW653242 | 337434 |  | RAN Only | Integration | 4000041336_7660 | 4000041336 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 7660 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130385643 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19629 | 22NDXXXNW653242 | 337435 |  | RAN Only | Integration | 4000041336_7660 | 4000041336 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705674 | 7660 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02LMP0061 | SEI_BEJANGKAR_TB |  |  |  | 02LMP0061 | SEI_BEJANGKAR_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-03-31 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1765AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2031-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130385643 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW653242 | 170940FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170940 | 170940FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606841 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19630 | 22NDXXXNW650186 | 337483 |  | RAN Only | Integration | 4000041336_7840 | 4000041336 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 7840 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130386318 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19631 | 22NDXXXNW650186 | 337484 |  | RAN Only | Integration | 4000041336_7840 | 4000041336 |  |  | KKNo3543 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705692 | 7840 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KPN0042 | DESA_TELUKPANJI_ST |  |  |  | 02KPN0042 | DESA_TELUKPANJI_ST | [12 empty] | 2023-04-28 |  |  |  | 2023-04-10 |  | 2023-04-28 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1783AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230517_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130386318 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650186 | 170939FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170939 | 170939FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615157 | 2023-05-30 | 2023_Q2 INT plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19632 | 22NDXXXNW656130 | 337509 |  | RAN Only | Integration | 4000041336_7940 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 7940 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416116 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19633 | 22NDXXXNW656130 | 337510 |  | RAN Only | Integration | 4000041336_7940 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 7940 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416116 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19634 | 22NDXXXNW656130 | 337511 |  | RAN Only | Integration | 4000041336_7940 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705702 | 7940 | 4100000512 | BTSS454 - BBU/RRU/Filter/Module Dismantle for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0072 | MARIHAT_BRS_EB |  |  |  | 02PMR0072 | MARIHAT_BRS_EB | [12 empty] | 2022-11-18 |  |  |  | 2023-05-17 |  | 2023-03-03 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1793AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 5733695.0001 | 2010233.4669 | 5733695.0001 | 2010233.4669 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416116 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW656130 | 170937FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-05-27 |  | 2023-06-21 |  | 170937 | 170937FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-14 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615171 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19646 | 22NDXXXNW643093 | 419835 |  | RAN Only | Integration | 4000041367_80 | 4000041367 |  |  | KKNo3628 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705083 | 80 | 1100000124 | 473096A - ABIA AirScale Capacity | 2 |  | SS Area 4 | NS | 01SGI0026 | KOTA_BAKTI_MT |  |  |  | 01SGI0026 | KOTA_BAKTI_MT | [12 empty] | 2023-01-13 |  |  |  | 2023-05-17 |  | 2023-01-13 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1174AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 21838452 | 8648026.992 | 43676904 | 17296053.9839 |  | 161067FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2017-May-2023%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20%20Phase%202022%20MOCN%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230526_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130966478 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D8&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643093 | 170965FDAUCAUCFPRJSSAC2023 | 4000041367 |  | 2023-05-27 |  | 2023-06-21 |  | 170965 | 170965FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3628AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040531 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603349 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19648 | 22NDXXXNW642736 | 422737 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704803 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0049 | SIANTAR_KABANJAHE_PL |  |  |  | 02PMR0049 | SIANTAR_KABANJAHE_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-03-02 |  | 2023-02-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 894AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642736 | 170966FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-05-28 |  | 2023-06-21 |  | 170966 | 170966FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040528 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614708 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1319 | 22NDXXXNW642701 | 422884 |  | RAN Only | Integration | 4000041231_390 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704768 | 390 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34114367.9999 | 13509289.9993 | 34114367.9999 | 13509289.9993 |  | 161402FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131345754 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055144 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1320 | 22NDXXXNW642701 | 422885 |  | RAN Only | Integration | 4000041232_170 | 4000041232 |  |  | KKNo3688 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704768 | 170 | 1300000820 | CP2018IM01 - Basic RF Module | 3 |  | NS Area 1 | NS | 02SMS0007 | PINTUSONA_MT |  |  |  | 02SMS0007 | PINTUSONA_MT | [12 empty] | 2022-12-16 |  |  |  | 2023-03-14 |  | 2022-12-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 859AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 71181.0004 | 68333.7603 | 213543.0011 | 205001.2808 |  | 161806FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41232 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41232 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131394376 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642701 | 170967FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-28 |  | 2023-06-21 |  | 170967 | 170967FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001079471 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559041 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1321 | 22NDXXXNW638475 | 423247 |  | RAN Only | Integration | 4000041231_390 | 4000041231 |  |  | KKNo3543 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704058 | 390 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 1 | NS | 01NAD0099 | RUKOH2_PL |  |  |  | 01NAD0099 | RUKOH2_PL | [12 empty] | 2023-03-31 |  |  |  | 2023-04-04 |  | 2023-03-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 149AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 34114367.9999 | 13509289.9993 | 34114367.9999 | 13509289.9993 |  | 161402FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_005.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131415879 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638475 | 170915FDAUCAUCFPRJSSAC2023 |  |  | 2023-05-27 |  | 2023-06-21 |  | 170915 | 170915FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3543AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001055144 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603027 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19649 | 22NDXXXNW640215 | 423873 |  | RAN Only | Integration, Relinquish | 4000041367_190 | 4000041367 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704391 | 190 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | SS Area 4 | NS | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT |  |  |  | 01LNS0019 | PAYA_BUJOK_TEUNGOH_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-18 |  | 2023-01-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 482AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-25 | 2023-05-25 |  |  | IDR | 36374929 | 14404471.8846 | 36374929 | 14404471.8846 |  | 161068FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488758 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D7&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640215 | 170971FDAUCAUCFPRJSSAC2023 | 4000041367 |  | 2023-05-27 |  | 2023-06-21 |  | 170971 | 170971FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  | 5001040532 | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606388 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19730 | 22NDXXXNW642750 | 184982 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19731 | 22NDXXXNW642750 | 185110 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19732 | 22NDXXXNW642750 | 185111 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19733 | 22NDXXXNW642750 | 185112 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19734 | 22NDXXXNW642750 | 185113 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19735 | 22NDXXXNW642750 | 185114 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19736 | 22NDXXXNW642750 | 185115 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19737 | 22NDXXXNW642750 | 185116 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19738 | 22NDXXXNW642750 | 185117 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19739 | 22NDXXXNW642750 | 185118 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19740 | 22NDXXXNW642750 | 185119 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19741 | 22NDXXXNW642750 | 185120 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19742 | 22NDXXXNW642750 | 185121 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19743 | 22NDXXXNW642750 | 185122 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19744 | 22NDXXXNW642750 | 185123 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19745 | 22NDXXXNW642750 | 185124 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19746 | 22NDXXXNW642750 | 185125 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19747 | 22NDXXXNW642750 | 185126 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19748 | 22NDXXXNW642750 | 185127 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19749 | 22NDXXXNW642750 | 185128 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19750 | 22NDXXXNW642750 | 185129 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19751 | 22NDXXXNW642750 | 185130 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19752 | 22NDXXXNW642750 | 185375 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130961003 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041221 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1324 | 22NDXXXNW642750 | 215640 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704817 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131007589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV |  |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19757 | 22NDXXXNW642750 | 334886 |  | RAN Only | Integration | 4000041335_9080 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 9080 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130415967 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041335 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19758 | 22NDXXXNW642750 | 334887 |  | RAN Only | Integration | 4000041335_9080 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 9080 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130415967 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041335 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19759 | 22NDXXXNW642750 | 334888 |  | RAN Only | Integration | 4000041335_9080 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 9080 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130415967 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041335 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19760 | 22NDXXXNW642750 | 334889 |  | RAN Only | Integration | 4000041335_9080 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 9080 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130415967 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041335 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19761 | 22NDXXXNW642750 | 419771 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704817 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02PMS0052 | NAGA_PITA_PL |  |  |  | 02PMS0052 | NAGA_PITA_PL | [12 empty] | 2022-12-30 |  |  |  | 2023-05-23 |  | 2023-05-23 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 908AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-29 | 2023-05-29 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2023-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_007.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130958472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642750 | 170993FDAUCAUCFPRJSSAC2023REV | 4000041222 |  | 2023-05-29 |  | 2023-06-21 |  | 170993 | 170993FDAUCAUCFPRJSSAC2023REV |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614715 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1325 | 22ND012NW033957 | 110511 |  | RAN Only | Integration, Expansion | 4000041231_230 | 4000041231 |  |  | KKNo3644 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 230 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 750111.9999 | 297043.9995 |  | 161402FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596572 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1326 | 22ND012NW033957 | 110512 |  | RAN Only | Integration, Expansion | 4000041231_250 | 4000041231 |  |  | KKNo3644 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 250 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 68561.9998 | 27151 |  | 161402FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596572 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1327 | 22ND012NW033957 | 110513 |  | RAN Only | Integration, Expansion | 4000041231_260 | 4000041231 |  |  | KKNo3644 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 260 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161402FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596572 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1328 | 22ND012NW033957 | 110514 |  | RAN Only | Integration, Expansion | 4000041231_220 | 4000041231 |  |  | KKNo3644 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 220 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 410166 | 162426 |  | 161402FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596572 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1329 | 22ND012NW033957 | 110516 |  | RAN Only | Integration, Expansion | 4000041231_400 | 4000041231 |  |  | KKNo3644 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 400 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 2 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 1272646.0006 | 503967.9996 |  | 161451FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596572 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1330 | 22ND012NW033957 | 110517 |  | RAN Only | Integration, Expansion | 4000041231_360 | 4000041231 |  |  | KKNo3644 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 360 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 822312 | 325635.9999 |  | 161581FDAUCAUCFPRJBABT2022 | 2022-10-24 | 2022-10-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596572 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1331 | 22ND012NW033957 | 110518 |  | RAN Only | Integration, Expansion | 4000041231_420 | 4000041231 |  |  | KKNo3644 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 11 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 4862120.9985 | 1925395.9997 |  | 161581FDAUCAUCFPRJBABT2022 | 2022-10-24 | 2022-10-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596572 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1332 | 22ND012NW033957 | 110520 |  | RAN Only | Integration, Expansion | 4000041232_270 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 270 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1878625.9204 | 1956902.0003 | 1878625.9204 |  | 161452FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1333 | 22ND012NW033957 | 110521 |  | RAN Only | Integration, Expansion | 4000041232_190 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 190 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33478.0801 | 174365.0009 | 167390.4007 |  | 161504FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1334 | 22ND012NW033957 | 110522 |  | RAN Only | Integration, Expansion | 4000041232_200 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 200 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 77564.16 | 80795.9997 | 77564.16 |  | 161452FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1335 | 22ND012NW033957 | 110523 |  | RAN Only | Integration, Expansion | 4000041232_210 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 210 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 77564.16 | 80795.9997 | 77564.16 |  | 161452FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1336 | 22ND012NW033957 | 110524 |  | RAN Only | Integration, Expansion | 4000041232_220 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 220 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 82198.08 | 85623.0003 | 82198.08 |  | 161452FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1337 | 22ND012NW033957 | 110525 |  | RAN Only | Integration, Expansion | 4000041232_300 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 300 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 310257.5998 | 1292740.0006 | 1241030.3993 |  | 161330FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1338 | 22ND012NW033957 | 110526 |  | RAN Only | Integration, Expansion | 4000041232_290 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 290 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 179238.7202 | 373414.0007 | 358477.4404 |  | 161330FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1339 | 22ND012NW033957 | 110527 |  | RAN Only | Integration, Expansion | 4000041232_260 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 260 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 60 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 130605.1203 | 8162820.0192 | 7836307.2204 |  | 161330FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1340 | 22ND012NW033957 | 110528 |  | RAN Only | Integration, Expansion | 4000041232_280 | 4000041232 |  |  | KKNo3644 | 3. IM | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 280 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 254597.7599 | 265205.9998 | 254597.7599 |  | 161504FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581290 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 2. BABT RECEIVED; READY TO HO | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19850 | 22NDXXXNW640362 | 146152 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19851 | 22NDXXXNW640362 | 146153 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19852 | 22NDXXXNW640362 | 146154 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19853 | 22NDXXXNW640362 | 146155 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19854 | 22NDXXXNW640362 | 146156 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19855 | 22NDXXXNW640362 | 146157 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19856 | 22NDXXXNW640362 | 146158 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19857 | 22NDXXXNW640362 | 146159 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19858 | 22NDXXXNW640362 | 146160 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 18 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 7956197.9976 | 3150647.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131516666 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19859 | 22NDXXXNW640362 | 146161 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19860 | 22NDXXXNW640362 | 146162 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19861 | 22NDXXXNW640362 | 146163 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19862 | 22NDXXXNW640362 | 146164 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19863 | 22NDXXXNW640362 | 146165 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19864 | 22NDXXXNW640362 | 146166 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19865 | 22NDXXXNW640362 | 146167 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19866 | 22NDXXXNW640362 | 146168 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19867 | 22NDXXXNW640362 | 146169 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19868 | 22NDXXXNW640362 | 146170 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444589 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19888 | 22NDXXXNW640397 | 146533 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19889 | 22NDXXXNW640397 | 146534 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19890 | 22NDXXXNW640397 | 146535 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19891 | 22NDXXXNW640397 | 146536 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19892 | 22NDXXXNW640397 | 146537 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19893 | 22NDXXXNW640397 | 146538 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19894 | 22NDXXXNW640397 | 146539 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19895 | 22NDXXXNW640397 | 146540 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19896 | 22NDXXXNW640397 | 146541 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595733 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19897 | 22NDXXXNW640397 | 146542 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19898 | 22NDXXXNW640397 | 146543 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19899 | 22NDXXXNW640397 | 146544 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19900 | 22NDXXXNW640397 | 146545 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19901 | 22NDXXXNW640397 | 146546 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19902 | 22NDXXXNW640397 | 146547 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19903 | 22NDXXXNW640397 | 146548 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19904 | 22NDXXXNW640397 | 146549 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19905 | 22NDXXXNW640397 | 146550 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19906 | 22NDXXXNW640397 | 146551 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19907 | 22NDXXXNW640397 | 146552 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19908 | 22NDXXXNW640397 | 146553 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580431 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19909 | 22NDXXXNW640395 | 146824 |  | RAN Only | Integration, Expansion | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19910 | 22NDXXXNW640395 | 146825 |  | RAN Only | Integration, Expansion | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19911 | 22NDXXXNW640395 | 146826 |  | RAN Only | Integration, Expansion | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19912 | 22NDXXXNW640395 | 146827 |  | RAN Only | Integration, Expansion | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19913 | 22NDXXXNW640395 | 146828 |  | RAN Only | Integration, Expansion | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19914 | 22NDXXXNW640395 | 146829 |  | RAN Only | Integration, Expansion | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19915 | 22NDXXXNW640395 | 146830 |  | RAN Only | Integration, Expansion | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19916 | 22NDXXXNW640395 | 146831 |  | RAN Only | Integration, Expansion | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19917 | 22NDXXXNW640395 | 146832 |  | RAN Only | Integration, Expansion | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19918 | 22NDXXXNW640395 | 146833 |  | RAN Only | Integration, Expansion | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19919 | 22NDXXXNW640395 | 146834 |  | RAN Only | Integration, Expansion | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19920 | 22NDXXXNW640395 | 146835 |  | RAN Only | Integration, Expansion | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19921 | 22NDXXXNW640395 | 146836 |  | RAN Only | Integration, Expansion | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19922 | 22NDXXXNW640395 | 146837 |  | RAN Only | Integration, Expansion | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19923 | 22NDXXXNW640395 | 146838 |  | RAN Only | Integration, Expansion | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19924 | 22NDXXXNW640395 | 146839 |  | RAN Only | Integration, Expansion | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19925 | 22NDXXXNW640395 | 146840 |  | RAN Only | Integration, Expansion | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19926 | 22NDXXXNW640395 | 146841 |  | RAN Only | Integration, Expansion | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19927 | 22NDXXXNW640395 | 146842 |  | RAN Only | Integration, Expansion | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19928 | 22NDXXXNW640395 | 146843 |  | RAN Only | Integration, Expansion | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19929 | 22NDXXXNW640395 | 146844 |  | RAN Only | Integration, Expansion | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580483 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19930 | 22NDXXXNW640401 | 146845 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19931 | 22NDXXXNW640401 | 146846 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19932 | 22NDXXXNW640401 | 146847 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19933 | 22NDXXXNW640401 | 146848 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19934 | 22NDXXXNW640401 | 146849 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19935 | 22NDXXXNW640401 | 146850 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19936 | 22NDXXXNW640401 | 146851 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19937 | 22NDXXXNW640401 | 146852 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19938 | 22NDXXXNW640401 | 146853 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131488684 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19939 | 22NDXXXNW640401 | 146854 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19940 | 22NDXXXNW640401 | 146855 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19941 | 22NDXXXNW640401 | 146856 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19942 | 22NDXXXNW640401 | 146857 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19943 | 22NDXXXNW640401 | 146858 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19944 | 22NDXXXNW640401 | 146859 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19945 | 22NDXXXNW640401 | 146860 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19946 | 22NDXXXNW640401 | 146861 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19947 | 22NDXXXNW640401 | 146862 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19948 | 22NDXXXNW640401 | 146863 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19949 | 22NDXXXNW640401 | 146864 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19950 | 22NDXXXNW640401 | 146865 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445223 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19993 | 22NDXXXNW652485 | 147268 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 750111.9999 | 297043.9995 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131277848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19994 | 22NDXXXNW652485 | 147269 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 68561.9998 | 27151 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131277848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19995 | 22NDXXXNW652485 | 147270 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131277848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19996 | 22NDXXXNW652485 | 147271 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 410166 | 162426 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131277848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19997 | 22NDXXXNW652485 | 147272 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 6 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 516365.9998 | 204480.9996 | 3098195.9988 | 1226885.9976 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131277848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19998 | 22NDXXXNW652485 | 147273 |  | RAN Only | Integration | 4000041221_350 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 350 | 1100000126 | 473310A - FUFBH SM OD fiber LC OD-LC OD dual 100m | 3 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 909990 | 360356 | 2729969.9999 | 1081068 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131277848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 19999 | 22NDXXXNW652485 | 147274 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131277848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20000 | 22NDXXXNW652485 | 147277 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131287472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20001 | 22NDXXXNW652485 | 147278 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131287472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20002 | 22NDXXXNW652485 | 147279 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131287472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20003 | 22NDXXXNW652485 | 147280 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131287472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20004 | 22NDXXXNW652485 | 147281 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131287472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20005 | 22NDXXXNW652485 | 147282 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 90 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 12244230.0288 | 11661390.027 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131287472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20006 | 22NDXXXNW652485 | 147283 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131287472 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20023 | 22NDXXXNW638467 | 147686 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20024 | 22NDXXXNW638467 | 147687 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20025 | 22NDXXXNW638467 | 147688 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20026 | 22NDXXXNW638467 | 147689 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20027 | 22NDXXXNW638467 | 147690 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20028 | 22NDXXXNW638467 | 147691 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20029 | 22NDXXXNW638467 | 147692 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20030 | 22NDXXXNW638467 | 147693 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20031 | 22NDXXXNW638467 | 147694 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 18 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 7956197.9976 | 3150647.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20032 | 22NDXXXNW638467 | 147695 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20033 | 22NDXXXNW638467 | 147696 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20034 | 22NDXXXNW638467 | 147697 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20035 | 22NDXXXNW638467 | 147698 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20036 | 22NDXXXNW638467 | 147699 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20037 | 22NDXXXNW638467 | 147700 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20038 | 22NDXXXNW638467 | 147701 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20039 | 22NDXXXNW638467 | 147702 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20040 | 22NDXXXNW638467 | 147703 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20041 | 22NDXXXNW638467 | 147704 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580816 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20042 | 22NDXXXNW638509 | 147784 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20043 | 22NDXXXNW638509 | 147785 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20044 | 22NDXXXNW638509 | 147786 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20045 | 22NDXXXNW638509 | 147787 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20046 | 22NDXXXNW638509 | 147788 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20047 | 22NDXXXNW638509 | 147789 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20048 | 22NDXXXNW638509 | 147790 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20049 | 22NDXXXNW638509 | 147791 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20050 | 22NDXXXNW638509 | 147792 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131589968 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20051 | 22NDXXXNW638509 | 147793 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20052 | 22NDXXXNW638509 | 147794 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20053 | 22NDXXXNW638509 | 147795 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20054 | 22NDXXXNW638509 | 147796 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20055 | 22NDXXXNW638509 | 147797 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20056 | 22NDXXXNW638509 | 147798 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20057 | 22NDXXXNW638509 | 147799 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20058 | 22NDXXXNW638509 | 147800 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20059 | 22NDXXXNW638509 | 147801 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20060 | 22NDXXXNW638509 | 147802 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 80 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 10883760.0256 | 10365680.024 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20061 | 22NDXXXNW638509 | 147803 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20062 | 22NDXXXNW638509 | 147804 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20131 | 22NDXXXNW638464 | 148271 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 3 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 2250335.9998 | 891131.9986 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589895 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20132 | 22NDXXXNW638464 | 148272 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 3 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 205685.9995 | 81453.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589895 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20133 | 22NDXXXNW638464 | 148273 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589895 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20134 | 22NDXXXNW638464 | 148274 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589895 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20135 | 22NDXXXNW638464 | 148275 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 8 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 5090584.0022 | 2015871.9984 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589895 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20136 | 22NDXXXNW638464 | 148276 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 4 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1090359.9998 | 431784.0001 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589895 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20137 | 22NDXXXNW638464 | 148277 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589895 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20138 | 22NDXXXNW638464 | 148278 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20139 | 22NDXXXNW638464 | 148279 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20140 | 22NDXXXNW638464 | 148280 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20141 | 22NDXXXNW638464 | 148281 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20142 | 22NDXXXNW638464 | 148282 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 15 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 523095.0027 | 498195.0057 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20143 | 22NDXXXNW638464 | 148283 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20144 | 22NDXXXNW638464 | 148284 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20145 | 22NDXXXNW638464 | 148285 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20146 | 22NDXXXNW638464 | 148286 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20147 | 22NDXXXNW638464 | 148287 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20148 | 22NDXXXNW638464 | 148288 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20149 | 22NDXXXNW638464 | 148289 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 180 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 24488460.0576 | 23322780.054 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20150 | 22NDXXXNW638464 | 148290 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20151 | 22NDXXXNW638464 | 148291 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581127 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20317 | 22NDXXXNW640272 | 150514 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20318 | 22NDXXXNW640272 | 150515 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20319 | 22NDXXXNW640272 | 150516 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20320 | 22NDXXXNW640272 | 150517 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20321 | 22NDXXXNW640272 | 150518 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20322 | 22NDXXXNW640272 | 150519 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20323 | 22NDXXXNW640272 | 150520 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20324 | 22NDXXXNW640272 | 150521 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20325 | 22NDXXXNW640272 | 150522 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20326 | 22NDXXXNW640272 | 150523 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 14 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 6188153.9982 | 2450503.9996 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131446261 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20327 | 22NDXXXNW640272 | 150525 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20328 | 22NDXXXNW640272 | 150526 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20329 | 22NDXXXNW640272 | 150527 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20330 | 22NDXXXNW640272 | 150528 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20331 | 22NDXXXNW640272 | 150529 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20332 | 22NDXXXNW640272 | 150530 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20333 | 22NDXXXNW640272 | 150531 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20334 | 22NDXXXNW640272 | 150532 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20335 | 22NDXXXNW640272 | 150533 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20336 | 22NDXXXNW640272 | 150534 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131443520 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20376 | 22NDXXXNW640178 | 150721 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20377 | 22NDXXXNW640178 | 150722 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20378 | 22NDXXXNW640178 | 150723 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20379 | 22NDXXXNW640178 | 150724 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20380 | 22NDXXXNW640178 | 150725 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20381 | 22NDXXXNW640178 | 150726 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20382 | 22NDXXXNW640178 | 150727 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20383 | 22NDXXXNW640178 | 150728 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20384 | 22NDXXXNW640178 | 150729 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20385 | 22NDXXXNW640178 | 150730 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131157881 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20386 | 22NDXXXNW640178 | 150731 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20387 | 22NDXXXNW640178 | 150732 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20388 | 22NDXXXNW640178 | 150733 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20389 | 22NDXXXNW640178 | 150734 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20390 | 22NDXXXNW640178 | 150735 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20391 | 22NDXXXNW640178 | 150736 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20392 | 22NDXXXNW640178 | 150737 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20393 | 22NDXXXNW640178 | 150738 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20394 | 22NDXXXNW640178 | 150739 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20395 | 22NDXXXNW640178 | 150740 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20396 | 22NDXXXNW640178 | 150741 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20397 | 22NDXXXNW640178 | 150742 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131145901 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20398 | 22NDXXXNW640436 | 150760 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20399 | 22NDXXXNW640436 | 150761 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20400 | 22NDXXXNW640436 | 150762 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20401 | 22NDXXXNW640436 | 150763 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20402 | 22NDXXXNW640436 | 150764 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20403 | 22NDXXXNW640436 | 150765 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20404 | 22NDXXXNW640436 | 150766 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20405 | 22NDXXXNW640436 | 150767 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20406 | 22NDXXXNW640436 | 150768 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20407 | 22NDXXXNW640436 | 150769 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20408 | 22NDXXXNW640436 | 150770 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20409 | 22NDXXXNW640436 | 150772 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 71181.0004 | 67792.9998 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20410 | 22NDXXXNW640436 | 150773 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20411 | 22NDXXXNW640436 | 150774 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20412 | 22NDXXXNW640436 | 150775 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20413 | 22NDXXXNW640436 | 150776 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20414 | 22NDXXXNW640436 | 150777 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20415 | 22NDXXXNW640436 | 150778 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20416 | 22NDXXXNW640436 | 150779 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20417 | 22NDXXXNW640436 | 150780 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20418 | 22NDXXXNW640436 | 150781 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20419 | 22NDXXXNW640436 | 150782 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20420 | 22NDXXXNW640168 | 151004 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20421 | 22NDXXXNW640168 | 151005 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20422 | 22NDXXXNW640168 | 151006 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20423 | 22NDXXXNW640168 | 151007 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20424 | 22NDXXXNW640168 | 151008 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20425 | 22NDXXXNW640168 | 151009 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20426 | 22NDXXXNW640168 | 151010 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20427 | 22NDXXXNW640168 | 151011 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20428 | 22NDXXXNW640168 | 151012 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20429 | 22NDXXXNW640168 | 151013 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445687 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20430 | 22NDXXXNW640168 | 151014 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20431 | 22NDXXXNW640168 | 151015 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20432 | 22NDXXXNW640168 | 151017 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20433 | 22NDXXXNW640168 | 151018 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20434 | 22NDXXXNW640168 | 151019 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20435 | 22NDXXXNW640168 | 151020 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20436 | 22NDXXXNW640168 | 151021 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20437 | 22NDXXXNW640168 | 151022 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20438 | 22NDXXXNW640168 | 151023 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20439 | 22NDXXXNW640168 | 151024 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20440 | 22NDXXXNW640168 | 151026 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445716 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20498 | 22NDXXXNW640244 | 152267 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20499 | 22NDXXXNW640244 | 152268 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20500 | 22NDXXXNW640244 | 152269 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20501 | 22NDXXXNW640244 | 152270 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20502 | 22NDXXXNW640244 | 152271 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20503 | 22NDXXXNW640244 | 152272 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 3 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 817769.9998 | 323838.0001 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20504 | 22NDXXXNW640244 | 152273 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 11 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 4862120.9985 | 1925395.9997 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20505 | 22NDXXXNW640244 | 152274 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20506 | 22NDXXXNW640244 | 152275 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20507 | 22NDXXXNW640244 | 152276 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20508 | 22NDXXXNW640244 | 152277 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20509 | 22NDXXXNW640244 | 152278 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20510 | 22NDXXXNW640244 | 152279 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20511 | 22NDXXXNW640244 | 152280 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 50 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 6802350.016 | 6478550.015 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20512 | 22NDXXXNW640244 | 152281 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20513 | 22NDXXXNW640244 | 152282 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581296 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20537 | 22NDXXXNW640231 | 153022 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20538 | 22NDXXXNW640231 | 153023 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20539 | 22NDXXXNW640231 | 153024 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20540 | 22NDXXXNW640231 | 153025 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20541 | 22NDXXXNW640231 | 153026 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20542 | 22NDXXXNW640231 | 153027 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20543 | 22NDXXXNW640231 | 153028 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20544 | 22NDXXXNW640231 | 153029 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20545 | 22NDXXXNW640231 | 153030 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20546 | 22NDXXXNW640231 | 153031 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131445997 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20547 | 22NDXXXNW640231 | 153032 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20548 | 22NDXXXNW640231 | 153033 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20549 | 22NDXXXNW640231 | 153035 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20550 | 22NDXXXNW640231 | 153036 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20551 | 22NDXXXNW640231 | 153037 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20552 | 22NDXXXNW640231 | 153038 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20553 | 22NDXXXNW640231 | 153039 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20554 | 22NDXXXNW640231 | 153040 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20555 | 22NDXXXNW640231 | 153041 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20556 | 22NDXXXNW640231 | 153042 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20557 | 22NDXXXNW640231 | 153043 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20558 | 22NDXXXNW640231 | 153044 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131441195 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20617 | 22NDXXXNW655195 | 154092 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 3 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 2250335.9998 | 891131.9986 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20618 | 22NDXXXNW655195 | 154093 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 3 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 205685.9995 | 81453.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20619 | 22NDXXXNW655195 | 154094 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20620 | 22NDXXXNW655195 | 154095 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20621 | 22NDXXXNW655195 | 154096 |  | RAN Only | Integration | 4000041221_310 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 310 | 1100000124 | 473098A - AMIA AirScale Subrack | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 7289110 | 2886488 | 7289110 | 2886488 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20622 | 22NDXXXNW655195 | 154097 |  | RAN Only | Integration | 4000041221_370 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 370 | 1100000124 | 473764A - ASIB AirScale Common | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 30228098.9999 | 11970327 | 30228098.9999 | 11970327 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20623 | 22NDXXXNW655195 | 154098 |  | RAN Only | Integration | 4000041221_300 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 300 | 1100000124 | 473096A - ABIA AirScale Capacity | 2 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 21545691 | 8532093.9999 | 43091382.0001 | 17064187.9999 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20624 | 22NDXXXNW655195 | 154099 |  | RAN Only | Integration | 4000041221_410 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 410 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34114367.9999 | 13509289.9993 | 34114367.9999 | 13509289.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20625 | 22NDXXXNW655195 | 154100 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 4 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 2545292.0011 | 1007935.9992 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20626 | 22NDXXXNW655195 | 154102 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 26 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 11492285.9966 | 4550935.9992 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587681 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20627 | 22NDXXXNW655195 | 154103 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20628 | 22NDXXXNW655195 | 154104 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20629 | 22NDXXXNW655195 | 154107 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20630 | 22NDXXXNW655195 | 154108 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 5 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 368104.9987 | 350585.0017 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20631 | 22NDXXXNW655195 | 154109 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 20 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 697460.0036 | 664260.0076 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20632 | 22NDXXXNW655195 | 154110 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20633 | 22NDXXXNW655195 | 154111 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20634 | 22NDXXXNW655195 | 154112 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20635 | 22NDXXXNW655195 | 154113 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20636 | 22NDXXXNW655195 | 154114 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20637 | 22NDXXXNW655195 | 154115 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 12 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 3878220.0018 | 3693611.9961 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20638 | 22NDXXXNW655195 | 154116 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 6 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 1120242.0019 | 1066920.0021 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20639 | 22NDXXXNW655195 | 154118 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 320 | 1300000820 | MCB 63A - MCB 63A | 3 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 795617.9995 | 757745.9993 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581218 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20640 | 22NDXXXNW640361 | 154380 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20641 | 22NDXXXNW640361 | 154381 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20642 | 22NDXXXNW640361 | 154382 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20643 | 22NDXXXNW640361 | 154383 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20644 | 22NDXXXNW640361 | 154384 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20645 | 22NDXXXNW640361 | 154385 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20646 | 22NDXXXNW640361 | 154386 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20647 | 22NDXXXNW640361 | 154387 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20648 | 22NDXXXNW640361 | 154388 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 15 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 6630164.998 | 2625539.9995 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131488668 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20649 | 22NDXXXNW640361 | 154389 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20650 | 22NDXXXNW640361 | 154390 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20651 | 22NDXXXNW640361 | 154391 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20652 | 22NDXXXNW640361 | 154392 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20653 | 22NDXXXNW640361 | 154393 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20654 | 22NDXXXNW640361 | 154394 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20655 | 22NDXXXNW640361 | 154395 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20656 | 22NDXXXNW640361 | 154396 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20657 | 22NDXXXNW640361 | 154397 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131442909 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20717 | 22NDXXXNW638581 | 155561 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131278674 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20718 | 22NDXXXNW638581 | 155562 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131278674 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20719 | 22NDXXXNW638581 | 155563 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131278674 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20720 | 22NDXXXNW638581 | 155564 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131278674 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20721 | 22NDXXXNW638581 | 155565 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131278674 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20722 | 22NDXXXNW638581 | 155566 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131278674 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20723 | 22NDXXXNW638581 | 155568 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131278674 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20724 | 22NDXXXNW638581 | 155569 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131278674 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20725 | 22NDXXXNW638581 | 155570 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20726 | 22NDXXXNW638581 | 155571 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20727 | 22NDXXXNW638581 | 155572 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20728 | 22NDXXXNW638581 | 155573 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20729 | 22NDXXXNW638581 | 155574 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20730 | 22NDXXXNW638581 | 155575 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20731 | 22NDXXXNW638581 | 155576 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20732 | 22NDXXXNW638581 | 155577 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20733 | 22NDXXXNW638581 | 155578 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20734 | 22NDXXXNW638581 | 155579 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20735 | 22NDXXXNW638581 | 155580 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20736 | 22NDXXXNW638581 | 155581 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131291068 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20737 | 22NDXXXNW638538 | 155582 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 5 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3750559.9996 | 1485219.9976 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20738 | 22NDXXXNW638538 | 155583 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 5 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 342809.9992 | 135755.0002 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20739 | 22NDXXXNW638538 | 155584 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20740 | 22NDXXXNW638538 | 155585 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20741 | 22NDXXXNW638538 | 155586 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20742 | 22NDXXXNW638538 | 155587 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 16 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 10181168.0045 | 4031743.9969 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20743 | 22NDXXXNW638538 | 155588 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20744 | 22NDXXXNW638538 | 155589 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 7 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1908129.9996 | 755622.0003 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20745 | 22NDXXXNW638538 | 155590 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 30 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 13260329.996 | 5251079.9991 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20746 | 22NDXXXNW638538 | 155591 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20747 | 22NDXXXNW638538 | 155592 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20748 | 22NDXXXNW638538 | 155593 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20749 | 22NDXXXNW638538 | 155594 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 20 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 697460.0036 | 664260.0076 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20750 | 22NDXXXNW638538 | 155595 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20751 | 22NDXXXNW638538 | 155596 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20752 | 22NDXXXNW638538 | 155597 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20753 | 22NDXXXNW638538 | 155598 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20754 | 22NDXXXNW638538 | 155599 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20755 | 22NDXXXNW638538 | 155600 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 12 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 3878220.0018 | 3693611.9961 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20756 | 22NDXXXNW638538 | 155601 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 6 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 1120242.0019 | 1066920.0021 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20757 | 22NDXXXNW638538 | 155602 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 150 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 20407050.048 | 19435650.045 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20758 | 22NDXXXNW638538 | 155603 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 320 | 1300000820 | MCB 63A - MCB 63A | 4 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 1060823.9993 | 1010327.9991 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20759 | 22NDXXXNW638538 | 155604 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20760 | 22NDXXXNW638539 | 155661 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20761 | 22NDXXXNW638539 | 155662 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20762 | 22NDXXXNW638539 | 155663 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20763 | 22NDXXXNW638539 | 155664 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20764 | 22NDXXXNW638539 | 155665 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20765 | 22NDXXXNW638539 | 155666 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20766 | 22NDXXXNW638539 | 155667 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20767 | 22NDXXXNW638539 | 155668 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20768 | 22NDXXXNW638539 | 155669 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20769 | 22NDXXXNW638539 | 155670 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20770 | 22NDXXXNW638539 | 155671 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20771 | 22NDXXXNW638539 | 155672 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20772 | 22NDXXXNW638539 | 155673 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20773 | 22NDXXXNW638539 | 155674 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20774 | 22NDXXXNW638539 | 155675 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20775 | 22NDXXXNW638539 | 155676 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20776 | 22NDXXXNW638539 | 155677 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20777 | 22NDXXXNW638539 | 155678 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20778 | 22NDXXXNW638539 | 155679 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20779 | 22NDXXXNW638539 | 155680 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20780 | 22NDXXXNW638539 | 155681 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581835 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20781 | 22NDXXXNW638380 | 155682 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20782 | 22NDXXXNW638380 | 155683 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20783 | 22NDXXXNW638380 | 155684 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20784 | 22NDXXXNW638380 | 155685 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20785 | 22NDXXXNW638380 | 155686 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20786 | 22NDXXXNW638380 | 155687 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20787 | 22NDXXXNW638380 | 155688 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20788 | 22NDXXXNW638380 | 155689 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20789 | 22NDXXXNW638380 | 155690 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131278610 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20790 | 22NDXXXNW638380 | 155691 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20791 | 22NDXXXNW638380 | 155692 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20792 | 22NDXXXNW638380 | 155693 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20793 | 22NDXXXNW638380 | 155694 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20794 | 22NDXXXNW638380 | 155695 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20795 | 22NDXXXNW638380 | 155696 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20796 | 22NDXXXNW638380 | 155697 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20797 | 22NDXXXNW638380 | 155698 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20798 | 22NDXXXNW638380 | 155699 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20799 | 22NDXXXNW638380 | 155700 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20800 | 22NDXXXNW638380 | 155701 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20801 | 22NDXXXNW638380 | 155702 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20845 | 22NDXXXNW638382 | 156913 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20846 | 22NDXXXNW638382 | 156914 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20847 | 22NDXXXNW638382 | 156915 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20848 | 22NDXXXNW638382 | 156916 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20849 | 22NDXXXNW638382 | 156917 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20850 | 22NDXXXNW638382 | 156918 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20851 | 22NDXXXNW638382 | 156919 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20852 | 22NDXXXNW638382 | 156920 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20853 | 22NDXXXNW638382 | 156921 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 18 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 7956197.9976 | 3150647.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131589746 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20854 | 22NDXXXNW638382 | 156922 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20855 | 22NDXXXNW638382 | 156923 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20856 | 22NDXXXNW638382 | 156924 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20857 | 22NDXXXNW638382 | 156925 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20858 | 22NDXXXNW638382 | 156926 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20859 | 22NDXXXNW638382 | 156927 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20860 | 22NDXXXNW638382 | 156928 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20861 | 22NDXXXNW638382 | 156929 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20862 | 22NDXXXNW638382 | 156930 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20863 | 22NDXXXNW638382 | 156931 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580023 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20903 | 22NDXXXNW638499 | 158294 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20904 | 22NDXXXNW638499 | 158295 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20905 | 22NDXXXNW638499 | 158296 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20906 | 22NDXXXNW638499 | 158297 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20907 | 22NDXXXNW638499 | 158298 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20908 | 22NDXXXNW638499 | 158299 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20909 | 22NDXXXNW638499 | 158300 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20910 | 22NDXXXNW638499 | 158301 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20911 | 22NDXXXNW638499 | 158302 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 18 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 7956197.9976 | 3150647.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451642 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20912 | 22NDXXXNW638499 | 158303 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20913 | 22NDXXXNW638499 | 158304 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20914 | 22NDXXXNW638499 | 158305 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20915 | 22NDXXXNW638499 | 158306 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20916 | 22NDXXXNW638499 | 158307 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20917 | 22NDXXXNW638499 | 158308 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20918 | 22NDXXXNW638499 | 158309 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20919 | 22NDXXXNW638499 | 158310 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 20920 | 22NDXXXNW638499 | 158312 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131444499 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21023 | 22NDXXXNW642729 | 160475 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130809497 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21024 | 22NDXXXNW642729 | 160476 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130809497 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21025 | 22NDXXXNW642729 | 160477 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130809497 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21026 | 22NDXXXNW642729 | 160478 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130809497 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21027 | 22NDXXXNW642729 | 160479 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130809497 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21028 | 22NDXXXNW642729 | 160480 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 2466935.9999 | 976907.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130809497 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21029 | 22NDXXXNW642729 | 160481 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 9 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 3978098.9988 | 1575323.9997 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130809497 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21030 | 22NDXXXNW642729 | 160482 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21031 | 22NDXXXNW642729 | 160483 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21032 | 22NDXXXNW642729 | 160484 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21033 | 22NDXXXNW642729 | 160485 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21034 | 22NDXXXNW642729 | 160486 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21035 | 22NDXXXNW642729 | 160487 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21036 | 22NDXXXNW642729 | 160488 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 70 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 9523290.0224 | 9069970.021 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21037 | 22NDXXXNW642729 | 160489 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21038 | 22NDXXXNW642729 | 160490 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130784911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21039 | 22NDXXXNW642728 | 160571 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131059093 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21040 | 22NDXXXNW642728 | 160572 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131059093 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21041 | 22NDXXXNW642728 | 160573 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131059093 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21042 | 22NDXXXNW642728 | 160574 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131059093 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21043 | 22NDXXXNW642728 | 160575 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131059093 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21044 | 22NDXXXNW642728 | 160576 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 2466935.9999 | 976907.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131059093 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21045 | 22NDXXXNW642728 | 160577 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 9 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 3978098.9988 | 1575323.9997 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131059093 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21046 | 22NDXXXNW642728 | 160578 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21047 | 22NDXXXNW642728 | 160579 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21048 | 22NDXXXNW642728 | 160580 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21049 | 22NDXXXNW642728 | 160581 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21050 | 22NDXXXNW642728 | 160582 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21051 | 22NDXXXNW642728 | 160583 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21052 | 22NDXXXNW642728 | 160584 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 70 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 9523290.0224 | 9069970.021 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21053 | 22NDXXXNW642728 | 160585 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21054 | 22NDXXXNW642728 | 160586 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131035927 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21071 | 22NDXXXNW639749 | 161623 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21072 | 22NDXXXNW639749 | 161624 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21073 | 22NDXXXNW639749 | 161625 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21074 | 22NDXXXNW639749 | 161626 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21075 | 22NDXXXNW639749 | 161627 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21076 | 22NDXXXNW639749 | 161628 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 2466935.9999 | 976907.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21077 | 22NDXXXNW639749 | 161629 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 9 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 3978098.9988 | 1575323.9997 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21078 | 22NDXXXNW639749 | 161630 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21079 | 22NDXXXNW639749 | 161631 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21080 | 22NDXXXNW639749 | 161632 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21081 | 22NDXXXNW639749 | 161633 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21082 | 22NDXXXNW639749 | 161634 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21083 | 22NDXXXNW639749 | 161635 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21084 | 22NDXXXNW639749 | 161636 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 60 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 8162820.0192 | 7774260.018 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21085 | 22NDXXXNW639749 | 161637 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21086 | 22NDXXXNW639749 | 161638 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440995 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21087 | 22NDXXXNW639768 | 161770 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415652 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21088 | 22NDXXXNW639768 | 161771 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415652 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21089 | 22NDXXXNW639768 | 161772 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415652 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21090 | 22NDXXXNW639768 | 161773 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415652 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21091 | 22NDXXXNW639768 | 161774 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415652 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21092 | 22NDXXXNW639768 | 161775 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 2466935.9999 | 976907.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415652 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21093 | 22NDXXXNW639768 | 161776 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 9 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 3978098.9988 | 1575323.9997 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415652 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21094 | 22NDXXXNW639768 | 161777 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21095 | 22NDXXXNW639768 | 161778 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21096 | 22NDXXXNW639768 | 161779 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21097 | 22NDXXXNW639768 | 161780 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21098 | 22NDXXXNW639768 | 161781 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21099 | 22NDXXXNW639768 | 161782 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21100 | 22NDXXXNW639768 | 161783 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 60 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 8162820.0192 | 7774260.018 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21101 | 22NDXXXNW639768 | 161784 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21102 | 22NDXXXNW639768 | 161785 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21103 | 22NDXXXNW639727 | 162062 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 5 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3750559.9996 | 1485219.9976 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21104 | 22NDXXXNW639727 | 162063 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 5 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 342809.9992 | 135755.0002 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21105 | 22NDXXXNW639727 | 162064 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21106 | 22NDXXXNW639727 | 162065 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21107 | 22NDXXXNW639727 | 162066 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21108 | 22NDXXXNW639727 | 162067 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 18 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 11453814.005 | 4535711.9965 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21109 | 22NDXXXNW639727 | 162068 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21110 | 22NDXXXNW639727 | 162069 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 8 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 6578495.9997 | 2605087.9996 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21111 | 22NDXXXNW639727 | 162070 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 30 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 13260329.996 | 5251079.9991 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415422 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21112 | 22NDXXXNW639727 | 162071 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21113 | 22NDXXXNW639727 | 162072 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21114 | 22NDXXXNW639727 | 162073 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21115 | 22NDXXXNW639727 | 162074 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21116 | 22NDXXXNW639727 | 162075 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 20 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 697460.0036 | 664260.0076 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21117 | 22NDXXXNW639727 | 162076 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21118 | 22NDXXXNW639727 | 162077 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21119 | 22NDXXXNW639727 | 162078 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21120 | 22NDXXXNW639727 | 162079 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21121 | 22NDXXXNW639727 | 162080 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21122 | 22NDXXXNW639727 | 162081 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 12 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 3878220.0018 | 3693611.9961 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21123 | 22NDXXXNW639727 | 162082 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 6 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 1120242.0019 | 1066920.0021 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21124 | 22NDXXXNW639727 | 162083 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 180 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 24488460.0576 | 23322780.054 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21125 | 22NDXXXNW639727 | 162084 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 320 | 1300000820 | MCB 63A - MCB 63A | 3 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 795617.9995 | 757745.9993 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21126 | 22NDXXXNW639727 | 162085 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422033 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21127 | 22NDXXXNW639711 | 162236 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 6 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 4500671.9996 | 1782263.9971 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21128 | 22NDXXXNW639711 | 162237 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 6 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 411371.999 | 162906.0002 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21129 | 22NDXXXNW639711 | 162238 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21130 | 22NDXXXNW639711 | 162239 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 6 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 2460996 | 974556 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21131 | 22NDXXXNW639711 | 162240 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21132 | 22NDXXXNW639711 | 162241 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 18 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 11453814.005 | 4535711.9965 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21133 | 22NDXXXNW639711 | 162242 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21134 | 22NDXXXNW639711 | 162243 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 8 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 2180719.9996 | 863568.0003 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21135 | 22NDXXXNW639711 | 162244 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 30 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 13260329.996 | 5251079.9991 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415313 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21136 | 22NDXXXNW639711 | 162245 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21137 | 22NDXXXNW639711 | 162246 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 4 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 9635836 | 9177172 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21138 | 22NDXXXNW639711 | 162247 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21139 | 22NDXXXNW639711 | 162248 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21140 | 22NDXXXNW639711 | 162249 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 20 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 697460.0036 | 664260.0076 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21141 | 22NDXXXNW639711 | 162250 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21142 | 22NDXXXNW639711 | 162251 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21143 | 22NDXXXNW639711 | 162252 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21144 | 22NDXXXNW639711 | 162253 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21145 | 22NDXXXNW639711 | 162254 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21146 | 22NDXXXNW639711 | 162255 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 12 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 3878220.0018 | 3693611.9961 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21147 | 22NDXXXNW639711 | 162256 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 6 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 1120242.0019 | 1066920.0021 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21148 | 22NDXXXNW639711 | 162257 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 240 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 32651280.0768 | 31097040.072 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21149 | 22NDXXXNW639711 | 162259 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131422140 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21150 | 22NDXXXNW639747 | 162260 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21151 | 22NDXXXNW639747 | 162261 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21152 | 22NDXXXNW639747 | 162262 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21153 | 22NDXXXNW639747 | 162263 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21154 | 22NDXXXNW639747 | 162264 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21155 | 22NDXXXNW639747 | 162265 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21156 | 22NDXXXNW639747 | 162266 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21157 | 22NDXXXNW639747 | 162267 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21158 | 22NDXXXNW639747 | 162268 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415569 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21159 | 22NDXXXNW639747 | 162269 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21160 | 22NDXXXNW639747 | 162270 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21161 | 22NDXXXNW639747 | 162271 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21162 | 22NDXXXNW639747 | 162272 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21163 | 22NDXXXNW639747 | 162273 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21164 | 22NDXXXNW639747 | 162274 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21165 | 22NDXXXNW639747 | 162275 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21166 | 22NDXXXNW639747 | 162276 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21167 | 22NDXXXNW639747 | 162277 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21168 | 22NDXXXNW639747 | 162278 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21169 | 22NDXXXNW639747 | 162279 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21170 | 22NDXXXNW639747 | 162280 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407510 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21196 | 22NDXXXNW639729 | 162331 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21197 | 22NDXXXNW639729 | 162332 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21198 | 22NDXXXNW639729 | 162333 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21199 | 22NDXXXNW639729 | 162334 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21200 | 22NDXXXNW639729 | 162335 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21201 | 22NDXXXNW639729 | 162336 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21202 | 22NDXXXNW639729 | 162337 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21203 | 22NDXXXNW639729 | 162338 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21204 | 22NDXXXNW639729 | 162339 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 15 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 6630164.998 | 2625539.9995 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415439 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21205 | 22NDXXXNW639729 | 162340 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21206 | 22NDXXXNW639729 | 162341 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21207 | 22NDXXXNW639729 | 162342 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21208 | 22NDXXXNW639729 | 162343 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21209 | 22NDXXXNW639729 | 162344 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21210 | 22NDXXXNW639729 | 162345 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21211 | 22NDXXXNW639729 | 162346 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21212 | 22NDXXXNW639729 | 162347 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21213 | 22NDXXXNW639729 | 162348 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21214 | 22NDXXXNW639729 | 162349 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407560 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21215 | 22NDXXXNW639736 | 162354 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 3 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 2250335.9998 | 891131.9986 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21216 | 22NDXXXNW639736 | 162355 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 3 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 205685.9995 | 81453.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21217 | 22NDXXXNW639736 | 162356 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21218 | 22NDXXXNW639736 | 162357 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21219 | 22NDXXXNW639736 | 162358 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 8 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 5090584.0022 | 2015871.9984 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21220 | 22NDXXXNW639736 | 162359 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 4 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 3289247.9999 | 1302543.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21221 | 22NDXXXNW639736 | 162360 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21222 | 22NDXXXNW639736 | 162361 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21223 | 22NDXXXNW639736 | 162362 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21224 | 22NDXXXNW639736 | 162363 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21225 | 22NDXXXNW639736 | 162364 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21226 | 22NDXXXNW639736 | 162365 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 15 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 523095.0027 | 498195.0057 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21227 | 22NDXXXNW639736 | 162366 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21228 | 22NDXXXNW639736 | 162367 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21229 | 22NDXXXNW639736 | 162368 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21230 | 22NDXXXNW639736 | 162369 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21231 | 22NDXXXNW639736 | 162370 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21232 | 22NDXXXNW639736 | 162371 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21233 | 22NDXXXNW639736 | 162372 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 210 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 28569870.0672 | 27209910.063 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21234 | 22NDXXXNW639736 | 162374 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21259 | 22NDXXXNW639901 | 162870 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21260 | 22NDXXXNW639901 | 162871 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21261 | 22NDXXXNW639901 | 162872 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21262 | 22NDXXXNW639901 | 162873 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21263 | 22NDXXXNW639901 | 162874 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21264 | 22NDXXXNW639901 | 162875 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 2466935.9999 | 976907.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21265 | 22NDXXXNW639901 | 162876 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 9 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 3978098.9988 | 1575323.9997 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21266 | 22NDXXXNW639901 | 162877 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21267 | 22NDXXXNW639901 | 162878 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21268 | 22NDXXXNW639901 | 162879 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21269 | 22NDXXXNW639901 | 162880 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21270 | 22NDXXXNW639901 | 162881 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21271 | 22NDXXXNW639901 | 162882 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21272 | 22NDXXXNW639901 | 162883 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 60 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 8162820.0192 | 7774260.018 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21273 | 22NDXXXNW639901 | 162884 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21274 | 22NDXXXNW639901 | 162885 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21301 | 22NDXXXNW652261 | 163400 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 3 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 2250335.9998 | 891131.9986 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21302 | 22NDXXXNW652261 | 163401 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 3 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 205685.9995 | 81453.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21303 | 22NDXXXNW652261 | 163402 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 4 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 904716.0001 | 358268.0001 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21304 | 22NDXXXNW652261 | 163403 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21305 | 22NDXXXNW652261 | 163404 |  | RAN Only | Integration | 4000041221_310 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 310 | 1100000124 | 473098A - AMIA AirScale Subrack | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 7289110 | 2886488 | 7289110 | 2886488 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21306 | 22NDXXXNW652261 | 163405 |  | RAN Only | Integration | 4000041221_370 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 370 | 1100000124 | 473764A - ASIB AirScale Common | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 30228098.9999 | 11970327 | 30228098.9999 | 11970327 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21307 | 22NDXXXNW652261 | 163406 |  | RAN Only | Integration | 4000041221_300 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 300 | 1100000124 | 473096A - ABIA AirScale Capacity | 2 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 21545691 | 8532093.9999 | 43091382.0001 | 17064187.9999 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21308 | 22NDXXXNW652261 | 163407 |  | RAN Only | Integration | 4000041221_410 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 410 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34114367.9999 | 13509289.9993 | 34114367.9999 | 13509289.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21309 | 22NDXXXNW652261 | 163408 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21310 | 22NDXXXNW652261 | 163409 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21311 | 22NDXXXNW652261 | 163410 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 8 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 5090584.0022 | 2015871.9984 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21312 | 22NDXXXNW652261 | 163411 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 4 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 3289247.9999 | 1302543.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21313 | 22NDXXXNW652261 | 163412 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21314 | 22NDXXXNW652261 | 163413 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21315 | 22NDXXXNW652261 | 163414 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21316 | 22NDXXXNW652261 | 163417 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21317 | 22NDXXXNW652261 | 163418 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 5 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 368104.9987 | 350585.0017 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21318 | 22NDXXXNW652261 | 163419 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 20 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 697460.0036 | 664260.0076 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21319 | 22NDXXXNW652261 | 163420 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21320 | 22NDXXXNW652261 | 163421 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21321 | 22NDXXXNW652261 | 163422 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21322 | 22NDXXXNW652261 | 163423 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21323 | 22NDXXXNW652261 | 163424 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21324 | 22NDXXXNW652261 | 163425 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 12 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 3878220.0018 | 3693611.9961 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21325 | 22NDXXXNW652261 | 163426 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 6 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 1120242.0019 | 1066920.0021 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21326 | 22NDXXXNW652261 | 163427 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 210 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 28569870.0672 | 27209910.063 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21327 | 22NDXXXNW652261 | 163428 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 320 | 1300000820 | MCB 63A - MCB 63A | 3 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 795617.9995 | 757745.9993 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131579920 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21392 | 22NDXXXNW639940 | 164455 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415853 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21393 | 22NDXXXNW639940 | 164456 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415853 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21394 | 22NDXXXNW639940 | 164457 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415853 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21395 | 22NDXXXNW639940 | 164458 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415853 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21396 | 22NDXXXNW639940 | 164459 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415853 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21397 | 22NDXXXNW639940 | 164460 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 2466935.9999 | 976907.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415853 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21398 | 22NDXXXNW639940 | 164461 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 9 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 3978098.9988 | 1575323.9997 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415853 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21399 | 22NDXXXNW639940 | 164462 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21400 | 22NDXXXNW639940 | 164463 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21401 | 22NDXXXNW639940 | 164464 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21402 | 22NDXXXNW639940 | 164465 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21403 | 22NDXXXNW639940 | 164466 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21404 | 22NDXXXNW639940 | 164467 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21405 | 22NDXXXNW639940 | 164468 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 60 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 8162820.0192 | 7774260.018 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21406 | 22NDXXXNW639940 | 164469 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21407 | 22NDXXXNW639940 | 164470 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407871 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21408 | 22NDXXXNW639866 | 164525 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21409 | 22NDXXXNW639866 | 164526 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21410 | 22NDXXXNW639866 | 164527 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21411 | 22NDXXXNW639866 | 164528 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21412 | 22NDXXXNW639866 | 164529 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21413 | 22NDXXXNW639866 | 164530 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21414 | 22NDXXXNW639866 | 164531 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21415 | 22NDXXXNW639866 | 164532 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21416 | 22NDXXXNW639866 | 164533 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21417 | 22NDXXXNW639866 | 164534 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451925 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21418 | 22NDXXXNW639866 | 164535 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21419 | 22NDXXXNW639866 | 164536 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21420 | 22NDXXXNW639866 | 164538 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21421 | 22NDXXXNW639866 | 164539 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21422 | 22NDXXXNW639866 | 164540 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21423 | 22NDXXXNW639866 | 164541 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21424 | 22NDXXXNW639866 | 164542 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21425 | 22NDXXXNW639866 | 164543 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21426 | 22NDXXXNW639866 | 164544 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21427 | 22NDXXXNW639866 | 164545 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21428 | 22NDXXXNW639866 | 164546 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21429 | 22NDXXXNW639866 | 164547 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131440805 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21526 | 22NDXXXNW642813 | 165302 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21527 | 22NDXXXNW642813 | 165303 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21528 | 22NDXXXNW642813 | 165304 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21529 | 22NDXXXNW642813 | 165305 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21530 | 22NDXXXNW642813 | 165306 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21531 | 22NDXXXNW642813 | 165307 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21532 | 22NDXXXNW642813 | 165308 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21533 | 22NDXXXNW642813 | 165309 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21534 | 22NDXXXNW642813 | 165310 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21535 | 22NDXXXNW642813 | 165311 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21536 | 22NDXXXNW642813 | 165312 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21537 | 22NDXXXNW642813 | 165313 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21538 | 22NDXXXNW642813 | 165314 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21539 | 22NDXXXNW642813 | 165315 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21540 | 22NDXXXNW642813 | 165316 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21541 | 22NDXXXNW642813 | 165317 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21542 | 22NDXXXNW642813 | 165318 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21543 | 22NDXXXNW642813 | 165319 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21544 | 22NDXXXNW642813 | 165320 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21545 | 22NDXXXNW642813 | 165321 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21546 | 22NDXXXNW642813 | 165322 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21547 | 22NDXXXNW642813 | 165323 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21548 | 22NDXXXNW642813 | 165324 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21549 | 22NDXXXNW642813 | 165325 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785187 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21550 | 22NDXXXNW642811 | 165344 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21551 | 22NDXXXNW642811 | 165345 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21552 | 22NDXXXNW642811 | 165346 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21553 | 22NDXXXNW642811 | 165347 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21554 | 22NDXXXNW642811 | 165348 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21555 | 22NDXXXNW642811 | 165349 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21556 | 22NDXXXNW642811 | 165350 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21557 | 22NDXXXNW642811 | 165351 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21558 | 22NDXXXNW642811 | 165352 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21559 | 22NDXXXNW642811 | 165353 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21560 | 22NDXXXNW642811 | 165354 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21561 | 22NDXXXNW642811 | 165355 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21562 | 22NDXXXNW642811 | 165356 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21563 | 22NDXXXNW642811 | 165357 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21564 | 22NDXXXNW642811 | 165358 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21565 | 22NDXXXNW642811 | 165359 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21566 | 22NDXXXNW642811 | 165360 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21567 | 22NDXXXNW642811 | 165361 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21568 | 22NDXXXNW642811 | 165362 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21569 | 22NDXXXNW642811 | 165363 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21570 | 22NDXXXNW642811 | 165364 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21571 | 22NDXXXNW642811 | 165365 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21572 | 22NDXXXNW642811 | 165366 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21573 | 22NDXXXNW642811 | 165367 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130785172 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21641 | 22NDXXXNW643025 | 172335 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21642 | 22NDXXXNW643025 | 172336 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21643 | 22NDXXXNW643025 | 172337 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21644 | 22NDXXXNW643025 | 172338 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21645 | 22NDXXXNW643025 | 172339 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21646 | 22NDXXXNW643025 | 172340 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21647 | 22NDXXXNW643025 | 172341 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21648 | 22NDXXXNW643025 | 172342 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21649 | 22NDXXXNW643025 | 172343 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21650 | 22NDXXXNW643025 | 172344 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580511 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21651 | 22NDXXXNW643025 | 172345 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580511 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21652 | 22NDXXXNW643025 | 172346 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580511 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21653 | 22NDXXXNW643025 | 172347 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161250FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580511 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21654 | 22NDXXXNW643025 | 172348 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580511 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21655 | 22NDXXXNW643025 | 172349 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580511 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21656 | 22NDXXXNW643025 | 172350 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580511 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21657 | 22NDXXXNW643025 | 172351 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580511 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21750 | 22NDXXXNW640879 | 178733 |  | RAN Only | Integration, Expansion | 4000041323_250 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 45114 | 17865.1439 | 45114 | 17865.1439 |  | 161213FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130519961 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21751 | 22NDXXXNW640879 | 178734 |  | RAN Only | Integration, Expansion | 4000041323_290 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 347438 | 137585.448 | 347438 | 137585.448 |  | 161082FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130519961 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21752 | 22NDXXXNW640879 | 178735 |  | RAN Only | Integration, Expansion | 4000041323_230 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 412080.9999 | 163184.076 | 412080.9999 | 163184.076 |  | 161082FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130519961 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21753 | 22NDXXXNW640879 | 178736 |  | RAN Only | Integration, Expansion | 4000041323_310 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 310 | 1100000124 | 473098A - AMIA AirScale Subrack | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 7323140 | 2899963.4399 | 7323140 | 2899963.4399 |  | 161082FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130519961 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21754 | 22NDXXXNW640879 | 178737 |  | RAN Only | Integration, Expansion | 4000041323_370 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 370 | 1100000124 | 473764A - ASIB AirScale Common | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 30369224 | 12026212.7041 | 30369224 | 12026212.7041 |  | 161213FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130519961 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21755 | 22NDXXXNW640879 | 178738 |  | RAN Only | Integration, Expansion | 4000041323_300 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 300 | 1100000124 | 473096A - ABIA AirScale Capacity | 2 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 21646280.0001 | 8571926.88 | 43292560.0001 | 17143853.7601 |  | 161082FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130519961 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21756 | 22NDXXXNW640879 | 178739 |  | RAN Only | Integration, Expansion | 4000041323_420 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 639293.9997 | 253160.424 | 3835763.9983 | 1518962.544 |  | 161262FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130519961 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21757 | 22NDXXXNW640879 | 178740 |  | RAN Only | Integration, Expansion | 4000041323_380 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 826151 | 327155.7959 | 2478452.9999 | 981467.3878 |  | 161576FDAUCAUCFPRJBABT2022 | 2022-10-24 | 2022-10-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130519961 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21758 | 22NDXXXNW640879 | 178741 |  | RAN Only | Integration, Expansion | 4000041324_210 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 210 | 1300000820 | CP2018IM03 - Basic System Module | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 207475.0003 | 197599.19 | 207475.0003 | 197599.19 |  | 161177FDAUCAUCFPRJBABT2022 | 2022-09-12 | 2022-09-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130469669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041324 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21759 | 22NDXXXNW640879 | 178742 |  | RAN Only | Integration, Expansion | 4000041324_220 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 5 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73964 | 70443.3136 | 369820 | 352216.568 |  | 161114FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130469669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041324 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21760 | 22NDXXXNW640879 | 178743 |  | RAN Only | Integration, Expansion | 4000041324_230 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35035.9998 | 33368.2862 | 175179.9989 | 166841.4312 |  | 161114FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130469669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041324 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21761 | 22NDXXXNW640879 | 178744 |  | RAN Only | Integration, Expansion | 4000041324_250 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 81172.9997 | 77309.1654 | 81172.9997 | 77309.1654 |  | 161114FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130469669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041324 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21762 | 22NDXXXNW640879 | 178745 |  | RAN Only | Integration, Expansion | 4000041324_260 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 86023.0004 | 81928.3049 | 86023.0004 | 81928.3049 |  | 161056FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130469669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041324 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21763 | 22NDXXXNW640879 | 178746 |  | RAN Only | Integration, Expansion | 4000041324_270 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 81172.9997 | 77309.1654 | 81172.9997 | 77309.1654 |  | 161214FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130469669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041324 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21764 | 22NDXXXNW640879 | 178747 |  | RAN Only | Integration, Expansion | 4000041324_280 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 81172.9997 | 77309.1654 | 81172.9997 | 77309.1654 |  | 161214FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130469669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041324 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21765 | 22NDXXXNW640879 | 178748 |  | RAN Only | Integration, Expansion | 4000041324_300 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 210 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136682.9997 | 130176.8893 | 28703429.937 | 27337146.7488 |  | 161177FDAUCAUCFPRJBABT2022 | 2022-09-12 | 2022-09-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130469669 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041324 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21794 | 22NDXXXNW642841 | 181365 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21795 | 22NDXXXNW642841 | 181366 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21796 | 22NDXXXNW642841 | 181367 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21797 | 22NDXXXNW642841 | 181368 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21798 | 22NDXXXNW642841 | 181369 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21799 | 22NDXXXNW642841 | 181370 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21800 | 22NDXXXNW642841 | 181371 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21801 | 22NDXXXNW642841 | 181372 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21802 | 22NDXXXNW642841 | 181373 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21803 | 22NDXXXNW642841 | 181374 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21804 | 22NDXXXNW642841 | 181375 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 19 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 8398208.9975 | 3325683.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596937 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21805 | 22NDXXXNW642841 | 181377 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21806 | 22NDXXXNW642841 | 181378 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21807 | 22NDXXXNW642841 | 181379 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21808 | 22NDXXXNW642841 | 181380 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161250FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21809 | 22NDXXXNW642841 | 181381 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21810 | 22NDXXXNW642841 | 181382 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21811 | 22NDXXXNW642841 | 181383 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21812 | 22NDXXXNW642841 | 181384 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21813 | 22NDXXXNW642841 | 181385 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 21851 | 22NDXXXNW642766 | 182477 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21852 | 22NDXXXNW642766 | 182478 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21853 | 22NDXXXNW642766 | 182479 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21854 | 22NDXXXNW642766 | 182480 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21855 | 22NDXXXNW642766 | 182481 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21856 | 22NDXXXNW642766 | 182482 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21857 | 22NDXXXNW642766 | 182483 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21858 | 22NDXXXNW642766 | 182484 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21859 | 22NDXXXNW642766 | 182485 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596558 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21860 | 22NDXXXNW642766 | 182486 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21861 | 22NDXXXNW642766 | 182487 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21862 | 22NDXXXNW642766 | 182488 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21863 | 22NDXXXNW642766 | 182489 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21864 | 22NDXXXNW642766 | 182490 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21865 | 22NDXXXNW642766 | 182491 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161250FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21866 | 22NDXXXNW642766 | 182492 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21867 | 22NDXXXNW642766 | 182493 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21868 | 22NDXXXNW642766 | 182494 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21869 | 22NDXXXNW642766 | 182495 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21870 | 22NDXXXNW642766 | 182496 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21871 | 22NDXXXNW642766 | 182497 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581071 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21903 | 22NDXXXNW642724 | 182550 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21904 | 22NDXXXNW642724 | 182551 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21905 | 22NDXXXNW642724 | 182552 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21906 | 22NDXXXNW642724 | 182553 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21907 | 22NDXXXNW642724 | 182554 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21908 | 22NDXXXNW642724 | 182555 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21909 | 22NDXXXNW642724 | 182556 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21910 | 22NDXXXNW642724 | 182557 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21911 | 22NDXXXNW642724 | 182558 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596449 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21912 | 22NDXXXNW642724 | 182559 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21913 | 22NDXXXNW642724 | 182560 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21914 | 22NDXXXNW642724 | 182561 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21915 | 22NDXXXNW642724 | 182562 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161250FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21916 | 22NDXXXNW642724 | 182563 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21917 | 22NDXXXNW642724 | 182564 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21918 | 22NDXXXNW642724 | 182565 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21919 | 22NDXXXNW642724 | 182566 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21920 | 22NDXXXNW642724 | 182567 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21921 | 22NDXXXNW642724 | 182568 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581085 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21922 | 22NDXXXNW642756 | 182637 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21923 | 22NDXXXNW642756 | 182638 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21924 | 22NDXXXNW642756 | 182639 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21925 | 22NDXXXNW642756 | 182640 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 3 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1230498 | 487278 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21926 | 22NDXXXNW642756 | 182641 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21927 | 22NDXXXNW642756 | 182642 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21928 | 22NDXXXNW642756 | 182643 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21929 | 22NDXXXNW642756 | 182644 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21930 | 22NDXXXNW642756 | 182645 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596526 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21931 | 22NDXXXNW642756 | 182646 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21932 | 22NDXXXNW642756 | 182647 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21933 | 22NDXXXNW642756 | 182648 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21934 | 22NDXXXNW642756 | 182649 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21935 | 22NDXXXNW642756 | 182650 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21936 | 22NDXXXNW642756 | 182651 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21937 | 22NDXXXNW642756 | 182652 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21938 | 22NDXXXNW642756 | 182653 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21939 | 22NDXXXNW642756 | 182654 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21940 | 22NDXXXNW642756 | 182655 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21941 | 22NDXXXNW642756 | 182656 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21942 | 22NDXXXNW642756 | 182657 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581052 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21943 | 22NDXXXNW642695 | 182832 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21944 | 22NDXXXNW642695 | 182833 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21945 | 22NDXXXNW642695 | 182834 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21946 | 22NDXXXNW642695 | 182835 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21947 | 22NDXXXNW642695 | 182836 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21948 | 22NDXXXNW642695 | 182837 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21949 | 22NDXXXNW642695 | 182838 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21950 | 22NDXXXNW642695 | 182839 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21951 | 22NDXXXNW642695 | 182840 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596342 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21952 | 22NDXXXNW642695 | 182841 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21953 | 22NDXXXNW642695 | 182842 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21954 | 22NDXXXNW642695 | 182843 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21955 | 22NDXXXNW642695 | 182844 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21956 | 22NDXXXNW642695 | 182845 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21957 | 22NDXXXNW642695 | 182846 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21958 | 22NDXXXNW642695 | 182847 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21959 | 22NDXXXNW642695 | 182848 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21960 | 22NDXXXNW642695 | 182849 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21961 | 22NDXXXNW642695 | 182850 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21962 | 22NDXXXNW642695 | 182851 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21963 | 22NDXXXNW642695 | 182852 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581108 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21964 | 22NDXXXNW642732 | 182853 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21965 | 22NDXXXNW642732 | 182854 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21966 | 22NDXXXNW642732 | 182855 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21967 | 22NDXXXNW642732 | 182856 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21968 | 22NDXXXNW642732 | 182857 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21969 | 22NDXXXNW642732 | 182858 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21970 | 22NDXXXNW642732 | 182859 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21971 | 22NDXXXNW642732 | 182860 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21972 | 22NDXXXNW642732 | 182861 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21973 | 22NDXXXNW642732 | 182862 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21974 | 22NDXXXNW642732 | 182863 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 20 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 8840219.9974 | 3500719.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279190 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21975 | 22NDXXXNW642732 | 182864 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21976 | 22NDXXXNW642732 | 182865 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21977 | 22NDXXXNW642732 | 182866 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21978 | 22NDXXXNW642732 | 182867 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21979 | 22NDXXXNW642732 | 182868 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21980 | 22NDXXXNW642732 | 182869 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21981 | 22NDXXXNW642732 | 182870 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21982 | 22NDXXXNW642732 | 182871 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21983 | 22NDXXXNW642732 | 182872 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21984 | 22NDXXXNW642732 | 182873 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21985 | 22NDXXXNW642732 | 182874 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21986 | 22NDXXXNW642710 | 182995 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21987 | 22NDXXXNW642710 | 182996 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21988 | 22NDXXXNW642710 | 182997 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21989 | 22NDXXXNW642710 | 182998 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21990 | 22NDXXXNW642710 | 182999 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21991 | 22NDXXXNW642710 | 183000 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21992 | 22NDXXXNW642710 | 183001 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21993 | 22NDXXXNW642710 | 183002 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21994 | 22NDXXXNW642710 | 183003 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21995 | 22NDXXXNW642710 | 183004 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21996 | 22NDXXXNW642710 | 183005 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596372 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21997 | 22NDXXXNW642710 | 183006 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21998 | 22NDXXXNW642710 | 183007 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 21999 | 22NDXXXNW642710 | 183009 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22000 | 22NDXXXNW642710 | 183010 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22001 | 22NDXXXNW642710 | 183011 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22002 | 22NDXXXNW642710 | 183012 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22003 | 22NDXXXNW642710 | 183013 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22004 | 22NDXXXNW642710 | 183014 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22005 | 22NDXXXNW642710 | 183015 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22006 | 22NDXXXNW642710 | 183016 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22007 | 22NDXXXNW642710 | 183017 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22008 | 22NDXXXNW642710 | 183018 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22009 | 22NDXXXNW642752 | 183019 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22010 | 22NDXXXNW642752 | 183020 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22011 | 22NDXXXNW642752 | 183021 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22012 | 22NDXXXNW642752 | 183022 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22013 | 22NDXXXNW642752 | 183023 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22014 | 22NDXXXNW642752 | 183024 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22015 | 22NDXXXNW642752 | 183025 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22016 | 22NDXXXNW642752 | 183026 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22017 | 22NDXXXNW642752 | 183027 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22018 | 22NDXXXNW642752 | 183028 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22019 | 22NDXXXNW642752 | 183029 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131346891 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22020 | 22NDXXXNW642752 | 183030 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22021 | 22NDXXXNW642752 | 183031 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22022 | 22NDXXXNW642752 | 183032 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22023 | 22NDXXXNW642752 | 183033 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22024 | 22NDXXXNW642752 | 183034 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22025 | 22NDXXXNW642752 | 183035 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22026 | 22NDXXXNW642752 | 183036 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22027 | 22NDXXXNW642752 | 183037 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22028 | 22NDXXXNW642752 | 183038 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22029 | 22NDXXXNW642752 | 183039 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22030 | 22NDXXXNW642752 | 183040 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22031 | 22NDXXXNW642752 | 183041 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22032 | 22NDXXXNW642752 | 183042 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131378748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22070 | 22NDXXXNW642726 | 184122 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22071 | 22NDXXXNW642726 | 184123 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22072 | 22NDXXXNW642726 | 184124 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22073 | 22NDXXXNW642726 | 184125 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22074 | 22NDXXXNW642726 | 184126 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22075 | 22NDXXXNW642726 | 184127 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22076 | 22NDXXXNW642726 | 184128 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22077 | 22NDXXXNW642726 | 184129 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22078 | 22NDXXXNW642726 | 184130 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22079 | 22NDXXXNW642726 | 184131 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22080 | 22NDXXXNW642726 | 184132 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 19 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 8398208.9975 | 3325683.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131279152 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22081 | 22NDXXXNW642726 | 184133 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22082 | 22NDXXXNW642726 | 184134 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22083 | 22NDXXXNW642726 | 184135 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22084 | 22NDXXXNW642726 | 184136 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22085 | 22NDXXXNW642726 | 184137 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22086 | 22NDXXXNW642726 | 184138 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22087 | 22NDXXXNW642726 | 184139 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22088 | 22NDXXXNW642726 | 184140 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22089 | 22NDXXXNW642726 | 184141 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 160 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 21767520.0512 | 20731360.048 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22090 | 22NDXXXNW642726 | 184142 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22091 | 22NDXXXNW642726 | 184143 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22092 | 22NDXXXNW642713 | 184263 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22093 | 22NDXXXNW642713 | 184264 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22094 | 22NDXXXNW642713 | 184265 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22095 | 22NDXXXNW642713 | 184266 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22096 | 22NDXXXNW642713 | 184267 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22097 | 22NDXXXNW642713 | 184268 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22098 | 22NDXXXNW642713 | 184269 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22099 | 22NDXXXNW642713 | 184270 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22100 | 22NDXXXNW642713 | 184271 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22101 | 22NDXXXNW642713 | 184272 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22102 | 22NDXXXNW642713 | 184273 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22103 | 22NDXXXNW642713 | 184274 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22104 | 22NDXXXNW642713 | 184276 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22105 | 22NDXXXNW642713 | 184277 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22106 | 22NDXXXNW642713 | 184278 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22107 | 22NDXXXNW642713 | 184279 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22108 | 22NDXXXNW642713 | 184280 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22109 | 22NDXXXNW642713 | 184281 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22110 | 22NDXXXNW642713 | 184282 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22111 | 22NDXXXNW642713 | 184283 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22112 | 22NDXXXNW642713 | 184284 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22113 | 22NDXXXNW642713 | 184285 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22114 | 22NDXXXNW642713 | 184286 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130958454 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22115 | 22NDXXXNW642670 | 184291 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22116 | 22NDXXXNW642670 | 184292 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22117 | 22NDXXXNW642670 | 184293 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22118 | 22NDXXXNW642670 | 184294 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22119 | 22NDXXXNW642670 | 184295 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22120 | 22NDXXXNW642670 | 184296 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22121 | 22NDXXXNW642670 | 184297 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22122 | 22NDXXXNW642670 | 184298 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22123 | 22NDXXXNW642670 | 184299 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22124 | 22NDXXXNW642670 | 184300 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22125 | 22NDXXXNW642670 | 184301 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131157905 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22126 | 22NDXXXNW642670 | 184302 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22127 | 22NDXXXNW642670 | 184303 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22128 | 22NDXXXNW642670 | 184304 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22129 | 22NDXXXNW642670 | 184305 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22130 | 22NDXXXNW642670 | 184306 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22131 | 22NDXXXNW642670 | 184307 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22132 | 22NDXXXNW642670 | 184308 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22133 | 22NDXXXNW642670 | 184309 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22134 | 22NDXXXNW642670 | 184310 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22135 | 22NDXXXNW642670 | 184311 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22136 | 22NDXXXNW642670 | 184312 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22137 | 22NDXXXNW642670 | 184313 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131146008 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22160 | 22NDXXXNW640611 | 185618 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22161 | 22NDXXXNW640611 | 185619 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22162 | 22NDXXXNW640611 | 185620 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22163 | 22NDXXXNW640611 | 185621 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22164 | 22NDXXXNW640611 | 185622 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22165 | 22NDXXXNW640611 | 185623 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22166 | 22NDXXXNW640611 | 185624 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 3 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 817769.9998 | 323838.0001 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22167 | 22NDXXXNW640611 | 185625 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 8 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 3536087.9989 | 1400287.9998 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22168 | 22NDXXXNW640611 | 185627 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22169 | 22NDXXXNW640611 | 185628 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22170 | 22NDXXXNW640611 | 185629 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22171 | 22NDXXXNW640611 | 185630 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22172 | 22NDXXXNW640611 | 185631 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22173 | 22NDXXXNW640611 | 185632 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22174 | 22NDXXXNW640611 | 185633 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 60 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 8162820.0192 | 7774260.018 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22175 | 22NDXXXNW640611 | 185634 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22176 | 22NDXXXNW640611 | 185635 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 1111154.9999 | 1058264.0003 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131581701 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22208 | 22NDXXXNW639901 | 185882 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22209 | 22NDXXXNW639901 | 185946 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130960782 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22234 | 22NDXXXNW642584 | 186707 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22235 | 22NDXXXNW642584 | 186708 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22236 | 22NDXXXNW642584 | 186709 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22237 | 22NDXXXNW642584 | 186710 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22238 | 22NDXXXNW642584 | 186711 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22239 | 22NDXXXNW642584 | 186712 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22240 | 22NDXXXNW642584 | 186713 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22241 | 22NDXXXNW642584 | 186714 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22242 | 22NDXXXNW642584 | 186715 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22243 | 22NDXXXNW642584 | 186716 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416097 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22244 | 22NDXXXNW642584 | 186717 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22245 | 22NDXXXNW642584 | 186718 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22246 | 22NDXXXNW642584 | 186719 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22247 | 22NDXXXNW642584 | 186720 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22248 | 22NDXXXNW642584 | 186721 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22249 | 22NDXXXNW642584 | 186722 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22250 | 22NDXXXNW642584 | 186723 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22251 | 22NDXXXNW642584 | 186724 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161299FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22252 | 22NDXXXNW642584 | 186725 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22253 | 22NDXXXNW642584 | 186726 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22254 | 22NDXXXNW642584 | 186727 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22255 | 22NDXXXNW642584 | 186728 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22256 | 22NDXXXNW642584 | 186729 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131406645 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22257 | 22NDXXXNW640436 | 186945 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22258 | 22NDXXXNW640436 | 187017 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130960958 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22281 | 22NDXXXNW642713 | 187080 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22282 | 22NDXXXNW642713 | 187142 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130961942 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22283 | 22NDXXXNW642570 | 187213 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22284 | 22NDXXXNW642570 | 187214 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22285 | 22NDXXXNW642570 | 187215 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22286 | 22NDXXXNW642570 | 187216 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22287 | 22NDXXXNW642570 | 187217 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22288 | 22NDXXXNW642570 | 187218 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22289 | 22NDXXXNW642570 | 187219 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22290 | 22NDXXXNW642570 | 187220 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22291 | 22NDXXXNW642570 | 187221 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22292 | 22NDXXXNW642570 | 187222 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131595910 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22293 | 22NDXXXNW642570 | 187223 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22294 | 22NDXXXNW642570 | 187224 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22295 | 22NDXXXNW642570 | 187226 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22296 | 22NDXXXNW642570 | 187227 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22297 | 22NDXXXNW642570 | 187228 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22298 | 22NDXXXNW642570 | 187229 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22299 | 22NDXXXNW642570 | 187230 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161299FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22300 | 22NDXXXNW642570 | 187231 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22301 | 22NDXXXNW642570 | 187232 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22302 | 22NDXXXNW642570 | 187233 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE