1.11 AOP 2022 Integration Wo Battle-6 | 22303 | 22NDXXXNW642570 | 187234 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22304 | 22NDXXXNW642570 | 187235 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583918 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22305 | 22NDXXXNW642571 | 187321 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22306 | 22NDXXXNW642571 | 187322 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22307 | 22NDXXXNW642571 | 187323 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22308 | 22NDXXXNW642571 | 187324 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22309 | 22NDXXXNW642571 | 187325 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22310 | 22NDXXXNW642571 | 187326 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22311 | 22NDXXXNW642571 | 187327 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22312 | 22NDXXXNW642571 | 187328 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22313 | 22NDXXXNW642571 | 187329 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22314 | 22NDXXXNW642571 | 187330 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131157883 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22315 | 22NDXXXNW642571 | 187331 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22316 | 22NDXXXNW642571 | 187332 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22317 | 22NDXXXNW642571 | 187333 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22318 | 22NDXXXNW642571 | 187334 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22319 | 22NDXXXNW642571 | 187335 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22320 | 22NDXXXNW642571 | 187336 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22321 | 22NDXXXNW642571 | 187337 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22322 | 22NDXXXNW642571 | 187338 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161299FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22323 | 22NDXXXNW642571 | 187339 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22324 | 22NDXXXNW642571 | 187340 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22325 | 22NDXXXNW642571 | 187341 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22326 | 22NDXXXNW642571 | 187342 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131143809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22327 | 22NDXXXNW642582 | 187344 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22328 | 22NDXXXNW642582 | 187345 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22329 | 22NDXXXNW642582 | 187346 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22330 | 22NDXXXNW642582 | 187347 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22331 | 22NDXXXNW642582 | 187348 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22332 | 22NDXXXNW642582 | 187349 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22333 | 22NDXXXNW642582 | 187350 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22334 | 22NDXXXNW642582 | 187351 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22335 | 22NDXXXNW642582 | 187352 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22336 | 22NDXXXNW642582 | 187353 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 23 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10166252.997 | 4025827.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596002 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22337 | 22NDXXXNW642582 | 187354 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22338 | 22NDXXXNW642582 | 187355 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22339 | 22NDXXXNW642582 | 187357 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 310 | 1300000820 | CP5040SI05 - RF cable management | 2 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 3913804.0006 | 3727505.9997 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22340 | 22NDXXXNW642582 | 187358 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22341 | 22NDXXXNW642582 | 187359 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22342 | 22NDXXXNW642582 | 187360 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22343 | 22NDXXXNW642582 | 187361 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161299FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22344 | 22NDXXXNW642582 | 187362 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22345 | 22NDXXXNW642582 | 187363 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22346 | 22NDXXXNW642582 | 187364 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22347 | 22NDXXXNW642582 | 187365 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22348 | 22NDXXXNW642582 | 187366 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131580911 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22373 | 22NDXXXNW639901 | 190195 |  | RAN Only | Integration | 4000041222_210 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 210 | 1300000820 | CP2018IM03 - Basic System Module | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 206511.0001 | 196681 | 206511.0001 | 196681 |  | 161765FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-29 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22403 | 22NDXXXNW639016 | 190917 |  | RAN Only | Integration, Expansion | 4000041323_240 | 4000041323 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 753614.0004 | 298431.1433 | 1507228.0007 | 596862.2867 |  | 161393FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130810662 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22404 | 22NDXXXNW639016 | 190918 |  | RAN Only | Integration, Expansion | 4000041323_260 | 4000041323 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68882.0006 | 27277.272 | 137764.0011 | 54554.544 |  | 161393FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130810662 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22405 | 22NDXXXNW639016 | 190919 |  | RAN Only | Integration, Expansion | 4000041323_270 | 4000041323 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 227235 | 89985.06 | 454470 | 179970.12 |  | 161658FDAUCAUCFPRJBABT2022 | 2022-11-10 | 2022-11-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130810662 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22406 | 22NDXXXNW639016 | 190920 |  | RAN Only | Integration, Expansion | 4000041323_230 | 4000041323 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 412080.9999 | 163184.076 | 824161.9998 | 326368.152 |  | 161082FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130810662 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22407 | 22NDXXXNW639016 | 190921 |  | RAN Only | Integration, Expansion | 4000041323_420 | 4000041323 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 2 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 639293.9997 | 253160.424 | 1278587.9994 | 506320.848 |  | 161262FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130810662 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22408 | 22NDXXXNW639016 | 190922 |  | RAN Only | Integration, Expansion | 4000041323_330 | 4000041323 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 1 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 273863 | 108449.748 | 273863 | 108449.748 |  | 161311FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130810662 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22409 | 22NDXXXNW639016 | 190923 |  | RAN Only | Integration, Expansion | 4000041324_310 | 4000041324 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1966037.9999 | 1872454.5914 | 1966037.9999 | 1872454.5914 |  | 161263FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786279 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22410 | 22NDXXXNW639016 | 190924 |  | RAN Only | Integration, Expansion | 4000041324_220 | 4000041324 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73964 | 70443.3136 | 739640 | 704433.136 |  | 161114FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786279 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22411 | 22NDXXXNW639016 | 190925 |  | RAN Only | Integration, Expansion | 4000041324_230 | 4000041324 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35035.9998 | 33368.2862 | 175179.9989 | 166841.4312 |  | 161114FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786279 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22412 | 22NDXXXNW639016 | 190926 |  | RAN Only | Integration, Expansion | 4000041324_280 | 4000041324 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 81172.9997 | 77309.1654 | 81172.9997 | 77309.1654 |  | 161214FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786279 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22413 | 22NDXXXNW639016 | 190927 |  | RAN Only | Integration, Expansion | 4000041324_360 | 4000041324 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 324693.0001 | 309237.6133 | 1298772.0006 | 1236950.4531 |  | 161518FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786279 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22414 | 22NDXXXNW639016 | 190929 |  | RAN Only | Integration, Expansion | 4000041324_300 | 4000041324 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 55 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136682.9997 | 130176.8893 | 7517564.9835 | 7159728.9104 |  | 161177FDAUCAUCFPRJBABT2022 | 2022-09-12 | 2022-09-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786279 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22415 | 22NDXXXNW639016 | 190930 |  | RAN Only | Integration, Expansion | 4000041324_320 | 4000041324 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 266445.0001 | 253762.2184 | 266445.0001 | 253762.2184 |  | 161518FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786279 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22416 | 22NDXXXNW639016 | 190931 |  | RAN Only | Integration, Expansion | 4000041324_190 | 4000041324 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1116342.0001 | 1063204.1206 | 1116342.0001 | 1063204.1206 |  | 161483FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786279 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22482 | 22NDXXXNW643076 | 192428 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22483 | 22NDXXXNW643076 | 192429 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22484 | 22NDXXXNW643076 | 192430 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22485 | 22NDXXXNW643076 | 192431 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22486 | 22NDXXXNW643076 | 192432 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22487 | 22NDXXXNW643076 | 192433 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22488 | 22NDXXXNW643076 | 192434 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22489 | 22NDXXXNW643076 | 192435 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22490 | 22NDXXXNW643076 | 192436 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 24 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 10608263.9968 | 4200863.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587433 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22491 | 22NDXXXNW643076 | 192437 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22492 | 22NDXXXNW643076 | 192438 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22493 | 22NDXXXNW643076 | 192439 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22494 | 22NDXXXNW643076 | 192440 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22495 | 22NDXXXNW643076 | 192441 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22496 | 22NDXXXNW643076 | 192442 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22497 | 22NDXXXNW643076 | 192443 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161299FDAUCAUCFPRJBABT2022 | 2022-09-21 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22498 | 22NDXXXNW643076 | 192444 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22499 | 22NDXXXNW643076 | 192445 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22500 | 22NDXXXNW643076 | 192446 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22501 | 22NDXXXNW643076 | 192447 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22502 | 22NDXXXNW643076 | 192448 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580004 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22552 | 22NDXXXNW642851 | 193857 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22553 | 22NDXXXNW642851 | 193858 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22554 | 22NDXXXNW642851 | 193859 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22555 | 22NDXXXNW642851 | 193860 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22556 | 22NDXXXNW642851 | 193861 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22557 | 22NDXXXNW642851 | 193864 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22558 | 22NDXXXNW642851 | 193865 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22559 | 22NDXXXNW642851 | 193866 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22560 | 22NDXXXNW642851 | 193867 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 13 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 5746142.9983 | 2275467.9996 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597072 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22561 | 22NDXXXNW642851 | 193869 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580062 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22562 | 22NDXXXNW642851 | 193870 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580062 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22563 | 22NDXXXNW642851 | 193871 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580062 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22564 | 22NDXXXNW642851 | 193872 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580062 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22565 | 22NDXXXNW642851 | 193873 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161624FDAUCAUCFPRJBABT2022 | 2022-10-27 | 2022-11-01 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580062 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22566 | 22NDXXXNW642851 | 193874 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580062 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22567 | 22NDXXXNW642851 | 193875 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580062 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22568 | 22NDXXXNW642851 | 193876 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 140 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 19046580.0448 | 18139940.042 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580062 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22569 | 22NDXXXNW642844 | 193879 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22570 | 22NDXXXNW642844 | 193880 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22571 | 22NDXXXNW642844 | 193881 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22572 | 22NDXXXNW642844 | 193882 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22573 | 22NDXXXNW642844 | 193883 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22574 | 22NDXXXNW642844 | 193886 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22575 | 22NDXXXNW642844 | 193887 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22576 | 22NDXXXNW642844 | 193888 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22577 | 22NDXXXNW642844 | 193889 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 20 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 8840219.9974 | 3500719.9994 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596978 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 3. SO NOT MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22578 | 22NDXXXNW642844 | 193891 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22579 | 22NDXXXNW642844 | 193892 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22580 | 22NDXXXNW642844 | 193893 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22581 | 22NDXXXNW642844 | 193894 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22582 | 22NDXXXNW642844 | 193895 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161624FDAUCAUCFPRJBABT2022 | 2022-10-27 | 2022-11-01 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22583 | 22NDXXXNW642844 | 193896 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22584 | 22NDXXXNW642844 | 193897 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22585 | 22NDXXXNW642844 | 193898 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 160 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 21767520.0512 | 20731360.048 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22586 | 22NDXXXNW642844 | 193900 |  | RAN Only | Integration | 4000041222_190 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 2 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1111154.9999 | 1058264.0003 | 2222309.9997 | 2116528.0006 |  | 161101FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580405 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 22587 | 22NDXXXNW642850 | 193990 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 1500223.9999 | 594087.999 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597048 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22588 | 22NDXXXNW642850 | 193991 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 137123.9997 | 54302.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597048 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22589 | 22NDXXXNW642850 | 193992 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597048 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22590 | 22NDXXXNW642850 | 193993 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597048 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22591 | 22NDXXXNW642850 | 193994 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597048 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22592 | 22NDXXXNW642850 | 193995 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 6 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 3817938.0017 | 1511903.9988 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597048 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22593 | 22NDXXXNW642850 | 193996 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 3 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 2466935.9999 | 976907.9998 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597048 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22594 | 22NDXXXNW642850 | 193997 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 8 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 3536087.9989 | 1400287.9998 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597048 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22595 | 22NDXXXNW642850 | 193999 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580418 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22596 | 22NDXXXNW642850 | 194000 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580418 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22597 | 22NDXXXNW642850 | 194001 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 174365.0009 | 166065.0019 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580418 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22598 | 22NDXXXNW642850 | 194002 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580418 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22599 | 22NDXXXNW642850 | 194003 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580418 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22600 | 22NDXXXNW642850 | 194004 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580418 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22601 | 22NDXXXNW642850 | 194005 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 70 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 9523290.0224 | 9069970.021 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580418 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22602 | 22NDXXXNW642850 | 194006 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580418 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22603 | 22NDXXXNW642829 | 194121 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22604 | 22NDXXXNW642829 | 194122 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22605 | 22NDXXXNW642829 | 194123 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22606 | 22NDXXXNW642829 | 194124 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22607 | 22NDXXXNW642829 | 194125 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22608 | 22NDXXXNW642829 | 194126 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22609 | 22NDXXXNW642829 | 194127 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22610 | 22NDXXXNW642829 | 194128 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22611 | 22NDXXXNW642829 | 194129 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22612 | 22NDXXXNW642829 | 194130 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 6 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 822312 | 325635.9999 | 4933871.9998 | 1953815.9997 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22613 | 22NDXXXNW642829 | 194131 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596796 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22614 | 22NDXXXNW642829 | 194132 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22615 | 22NDXXXNW642829 | 194133 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22616 | 22NDXXXNW642829 | 194135 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22617 | 22NDXXXNW642829 | 194136 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22618 | 22NDXXXNW642829 | 194137 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22619 | 22NDXXXNW642829 | 194138 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22620 | 22NDXXXNW642829 | 194139 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161624FDAUCAUCFPRJBABT2022 | 2022-10-27 | 2022-11-01 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22621 | 22NDXXXNW642829 | 194140 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22622 | 22NDXXXNW642829 | 194141 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22623 | 22NDXXXNW642829 | 194142 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 120 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 16325640.0384 | 15548520.036 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580438 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22624 | 22NDXXXNW642908 | 194169 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 4 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297043.9995 | 3000447.9997 | 1188175.9981 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22625 | 22NDXXXNW642908 | 194170 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 4 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27151 | 274247.9994 | 108604.0001 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22626 | 22NDXXXNW642908 | 194171 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22627 | 22NDXXXNW642908 | 194172 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 4 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162426 | 1640664 | 649704 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22628 | 22NDXXXNW642908 | 194173 |  | RAN Only | Integration | 4000041221_280 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 280 | 1100001510 | 472509A - FTSF Sync Cable F | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34658.0002 | 13725 | 34658.0002 | 13725 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22629 | 22NDXXXNW642908 | 194176 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 14 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 636323.0003 | 251983.9998 | 8908522.0039 | 3527775.9973 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22630 | 22NDXXXNW642908 | 194177 |  | RAN Only | Integration | 4000041221_320 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 320 | 1100000126 | 473288A - FUFAS MM OD fiber LC OD-LC OD dual 2m | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 112260.9999 | 44455 | 112260.9999 | 44455 |  | 161062FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22631 | 22NDXXXNW642908 | 194178 |  | RAN Only | Integration | 4000041221_330 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 330 | 1100000126 | 473304A - FUFBB MM OD fiber LC OD-LC OD dual 50m | 6 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 272589.9999 | 107946 | 1635539.9997 | 647676.0002 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22632 | 22NDXXXNW642908 | 194179 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 22 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 9724241.9971 | 3850791.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587249 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22633 | 22NDXXXNW642908 | 194181 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22634 | 22NDXXXNW639901 | 194182 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 71181.0004 | 67792.9998 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130954364 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22635 | 22NDXXXNW642908 | 194183 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22636 | 22NDXXXNW642908 | 194184 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 73620.9997 | 70117.0003 | 736209.9974 | 701170.0034 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22637 | 22NDXXXNW642908 | 194185 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22638 | 22NDXXXNW642908 | 194186 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22639 | 22NDXXXNW642908 | 194187 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161624FDAUCAUCFPRJBABT2022 | 2022-10-27 | 2022-11-01 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22640 | 22NDXXXNW642908 | 194188 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 8 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 307800.9997 | 2585480.0012 | 2462407.9974 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22641 | 22NDXXXNW642908 | 194189 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 4 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 177820.0003 | 746828.0013 | 711280.0014 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22642 | 22NDXXXNW642908 | 194190 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 100 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 129571.0003 | 13604700.032 | 12957100.03 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22643 | 22NDXXXNW642908 | 194191 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 320 | 1300000820 | MCB 63A - MCB 63A | 2 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 252581.9998 | 530411.9996 | 505163.9996 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131580446 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22673 | 22NDXXXNW639016 | 214064 |  | RAN Only | Integration, Expansion | 4000041412_30 | 4000041412 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 30 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 3 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 45513.9999 | 18023.544 | 45513.9999 | 18023.544 |  | 161103FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130815267 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041412 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22674 | 22NDXXXNW639016 | 214065 |  | RAN Only | Integration, Expansion | 4000041412_70 | 4000041412 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 70 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 3 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 350521.9996 | 138806.7117 | 350521.9996 | 138806.7117 |  | 161077FDAUCAUCFPRJBABT2022REV | 2022-09-08 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130815267 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041412 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1358 | 22NDXXXNW638380 | 214584 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000703963 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161581FDAUCAUCFPRJBABT2022 | 2022-10-24 | 2022-10-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131285664 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1359 | 22NDXXXNW638382 | 214585 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000703965 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161581FDAUCAUCFPRJBABT2022 | 2022-10-24 | 2022-10-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596821 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1360 | 22NDXXXNW638467 | 214613 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704050 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596950 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1361 | 22NDXXXNW638499 | 214619 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704082 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131447058 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1362 | 22NDXXXNW638509 | 214622 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704092 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131596981 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1363 | 22NDXXXNW638539 | 214634 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704122 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131597104 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1366 | 22NDXXXNW638581 | 214665 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704164 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131285683 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1371 | 22NDXXXNW639729 | 214823 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704189 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416169 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1372 | 22NDXXXNW639747 | 214828 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704207 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416207 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1373 | 22NDXXXNW639749 | 214830 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704209 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131447222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1375 | 22NDXXXNW639768 | 214839 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704228 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416259 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1376 | 22NDXXXNW639866 | 214840 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704230 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131447229 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1378 | 22NDXXXNW639901 | 214855 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704265 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131007492 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1379 | 22NDXXXNW639940 | 214872 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704304 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416315 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1383 | 22NDXXXNW640168 | 214892 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704344 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131447464 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1384 | 22NDXXXNW640178 | 214898 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704354 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131144608 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1387 | 22NDXXXNW640231 | 214933 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704407 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131447690 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1389 | 22NDXXXNW640244 | 214943 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704420 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131597465 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1392 | 22NDXXXNW640272 | 214958 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704448 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131447767 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1396 | 22NDXXXNW640361 | 215014 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704537 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131447956 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1397 | 22NDXXXNW640362 | 215015 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704538 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131447970 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1398 | 22NDXXXNW640397 | 215033 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704573 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597654 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1399 | 22NDXXXNW640401 | 215035 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704577 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131448703 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1402 | 22NDXXXNW640436 | 215051 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704612 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1131007546 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1404 | 22NDXXXNW640611 | 215091 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704622 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131597815 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1405 | 22NDXXXNW642570 | 215487 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704637 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131597973 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1406 | 22NDXXXNW642571 | 215488 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704638 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131144619 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1407 | 22NDXXXNW642582 | 215499 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704649 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131598122 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1408 | 22NDXXXNW642584 | 215501 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704651 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416399 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1411 | 22NDXXXNW642670 | 215578 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704737 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131144670 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1412 | 22NDXXXNW642695 | 215600 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704762 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131598825 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1413 | 22NDXXXNW642710 | 215610 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704777 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131598838 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1414 | 22NDXXXNW642713 | 215612 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704780 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131007570 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1415 | 22NDXXXNW642724 | 215619 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704791 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131598862 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1416 | 22NDXXXNW642726 | 215621 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704793 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131285890 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1417 | 22NDXXXNW642728 | 215623 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704795 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131046390 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1418 | 22NDXXXNW642729 | 215624 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704796 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130754814 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1419 | 22NDXXXNW642732 | 215626 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704799 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131285898 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1422 | 22NDXXXNW642752 | 215642 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704819 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131345361 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1423 | 22NDXXXNW642756 | 215646 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704823 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131598900 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1424 | 22NDXXXNW642766 | 215654 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704833 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131598914 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1426 | 22NDXXXNW642811 | 215693 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704878 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130761699 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1427 | 22NDXXXNW642813 | 215695 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704880 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130761706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1429 | 22NDXXXNW642829 | 215708 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704896 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599030 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1430 | 22NDXXXNW642841 | 215716 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704908 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599083 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.3 AOP 2022 Capacity Expansion | 1431 | 22NDXXXNW642844 | 215718 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704911 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599097 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.3 AOP 2022 Capacity Expansion | 1432 | 22NDXXXNW642850 | 215723 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704917 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599142 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1433 | 22NDXXXNW642851 | 215724 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704918 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599153 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.3 AOP 2022 Capacity Expansion | 1435 | 22NDXXXNW642908 | 215775 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704975 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599419 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1438 | 22NDXXXNW643025 | 215814 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000705024 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1440 | 22NDXXXNW643076 | 215860 |  | RAN Only | Integration | 4000041231_420 | 4000041231 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000705075 | 420 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 3 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036 | 1326032.9996 | 525107.9999 |  | 161095FDAUCAUCFPRJBABT2022 | 2022-09-06 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599678 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 616 | 22NDXXXNW640879 | 217249 |  | RAN Only | Integration, Expansion | 4000041240_120 | 4000041240 |  |  | KKNo3688 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 120 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 750111.9999 | 297044.3519 | 750111.9999 | 297044.3519 |  | 161410FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130520429 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 617 | 22NDXXXNW640879 | 217250 |  | RAN Only | Integration, Expansion | 4000041240_130 | 4000041240 |  |  | KKNo3688 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 130 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 68561.9998 | 27150.5523 | 68561.9998 | 27150.5523 |  | 161653FDAUCAUCFPRJBABT2022 | 2022-11-10 | 2022-11-15 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130520429 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 618 | 22NDXXXNW640879 | 217251 |  | RAN Only | Integration, Expansion | 4000041240_140 | 4000041240 |  |  | KKNo3688 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 140 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 226179 | 89566.884 | 452358 | 179133.768 |  | 161663FDAUCAUCFPRJBABT2022 | 2022-11-16 | 2022-11-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130520429 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 619 | 22NDXXXNW640879 | 217252 |  | RAN Only | Integration, Expansion | 4000041240_110 | 4000041240 |  |  | KKNo3688 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 110 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 410166 | 162425.736 | 410166 | 162425.736 |  | 161410FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130520429 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 620 | 22NDXXXNW640879 | 217253 |  | RAN Only | Integration, Expansion | 4000041240_180 | 4000041240 |  |  | KKNo3688 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 180 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34114367.9999 | 13509289.7287 | 34114367.9999 | 13509289.7287 |  | 161410FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130520429 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 621 | 22NDXXXNW640879 | 217256 |  | RAN Only | Integration, Expansion | 4000041240_200 | 4000041240 |  |  | KKNo3688 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 200 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 9 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 442010.9999 | 175036.356 | 3978098.9988 | 1575327.2036 |  | 161585FDAUCAUCFPRJBABT2022 | 2022-10-24 | 2022-10-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130520429 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 622 | 22NDXXXNW640879 | 217257 |  | RAN Only | Integration, Expansion | 4000041241_120 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 120 | 1300000820 | CP2018IM01 - Basic RF Module | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 68333.9997 | 71181.0004 | 68333.9997 |  | 161430FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 623 | 22NDXXXNW640879 | 217259 |  | RAN Only | Integration, Expansion | 4000041241_130 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 130 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34873.0002 | 33477.9998 | 174365.0009 | 167389.9989 |  | 161515FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 624 | 22NDXXXNW640879 | 217260 |  | RAN Only | Integration, Expansion | 4000041241_140 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 140 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 77564.16 | 80795.9997 | 77564.16 |  | 161479FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 625 | 22NDXXXNW640879 | 217261 |  | RAN Only | Integration, Expansion | 4000041241_150 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 150 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 80795.9997 | 77564.16 | 80795.9997 | 77564.16 |  | 161479FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 626 | 22NDXXXNW640879 | 217262 |  | RAN Only | Integration, Expansion | 4000041241_160 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 160 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 85623.0003 | 82198.08 | 85623.0003 | 82198.08 |  | 161479FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 627 | 22NDXXXNW640879 | 217263 |  | RAN Only | Integration, Expansion | 4000041241_220 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 220 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 323185.0001 | 310257.5998 | 1292740.0006 | 1241030.3993 |  | 161515FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 628 | 22NDXXXNW640879 | 217264 |  | RAN Only | Integration, Expansion | 4000041241_210 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 210 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 186707.0003 | 179238.7202 | 373414.0007 | 358477.4404 |  | 161515FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 629 | 22NDXXXNW640879 | 217265 |  | RAN Only | Integration, Expansion | 4000041241_180 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 180 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 70 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 136047.0003 | 130605.1203 | 9523290.0224 | 9142358.4238 |  | 161541FDAUCAUCFPRJBABT2022 | 2022-10-19 | 2022-10-24 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 630 | 22NDXXXNW640879 | 217266 |  | RAN Only | Integration, Expansion | 4000041241_200 | 4000041241 |  |  | KKNo3688 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000711878 | 200 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 265205.9998 | 254597.7599 | 265205.9998 | 254597.7599 |  | 161515FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130447299 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1441 | 22ND012NW033957 | 302317 |  | RAN Only | Integration, Expansion | 4000041470_1250 | 4000041470 |  |  | KKNo3644 | 5. SVC | AOP 2022 Capacity Expansion | AOP 2022 MOCN Expansion | BTS | 1000691248 | 1250 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01BIR0084 | COTMANE_TB |  |  |  | 01BIR0084 | COTMANE_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 3482AOP2022MOCNEXPAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 52797439.1951 | 83250456 | 52797439.1951 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/RE_%20Endorsement%20request_AOP%202022%20Capacity%20Expansion_Relinguish_48%20sites_20230522.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41470 SVC 30% | TOP PO 4_41470 SVC 85% | TOP PO 4_41470 SVC 55% | TOP PO 4_41231 HW 15%,PO 4_41232 IM 15% | TOP PO 4_41231 HW 40%,PO 4_41232 IM 40% | TOP PO 4_41231 HW 25%,PO 4_41232 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130612106 | [5 empty] | NO NEED CA |  |  |  |  | 2023-06-02 |  | 2023-06-21 |  | 171103 | 171103FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3644AUCAUCEKK2023_NOK (DONE) | 2023-06-13 |  |  |  | 1. RESERVATION DONE |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; READY TO HO | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0648731 | 2023-06-15 | 2023_Q2 EXP plan P06 Ready RR | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22679 | 22NDXXXNW638380 | 331779 |  | RAN Only | Integration | 4000041335_540 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 540 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130010583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22680 | 22NDXXXNW638380 | 331780 |  | RAN Only | Integration | 4000041335_540 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 540 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130010583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22681 | 22NDXXXNW638380 | 331781 |  | RAN Only | Integration | 4000041335_540 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 540 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130010583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22682 | 22NDXXXNW638380 | 331782 |  | RAN Only | Integration | 4000041335_540 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 540 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130010583 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22683 | 22NDXXXNW638382 | 331786 |  | RAN Only | Integration | 4000041335_560 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 560 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995263 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22684 | 22NDXXXNW638382 | 331787 |  | RAN Only | Integration | 4000041335_560 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 560 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995263 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22685 | 22NDXXXNW638382 | 331788 |  | RAN Only | Integration | 4000041335_560 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 560 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995263 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22701 | 22NDXXXNW638464 | 332079 |  | RAN Only | Integration | 4000041335_1380 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 1380 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130001327 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22702 | 22NDXXXNW638464 | 332080 |  | RAN Only | Integration | 4000041335_1380 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 1380 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130001327 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22703 | 22NDXXXNW638464 | 332081 |  | RAN Only | Integration | 4000041335_1380 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 1380 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130001327 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22704 | 22NDXXXNW638464 | 332082 |  | RAN Only | Integration | 4000041335_1380 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 1380 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130001327 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22705 | 22NDXXXNW638467 | 332090 |  | RAN Only | Integration | 4000041335_1410 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 1410 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130001329 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22706 | 22NDXXXNW638467 | 332091 |  | RAN Only | Integration | 4000041335_1410 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 1410 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130001329 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22707 | 22NDXXXNW638467 | 332092 |  | RAN Only | Integration | 4000041335_1410 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 1410 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130001329 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22708 | 22NDXXXNW638499 | 332198 |  | RAN Only | Integration | 4000041335_1730 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 1730 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130423463 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22709 | 22NDXXXNW638499 | 332199 |  | RAN Only | Integration | 4000041335_1730 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 1730 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130423463 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22710 | 22NDXXXNW638499 | 332200 |  | RAN Only | Integration | 4000041335_1730 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704082 | 1730 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01SGI0038 | TIRO_ST |  |  |  | 01SGI0038 | TIRO_ST | [12 empty] | 2023-01-13 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 173AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130423463 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638499 | 171051FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-01 |  | 2023-06-21 |  | 171051 | 171051FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603047 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22711 | 22NDXXXNW638509 | 332232 |  | RAN Only | Integration | 4000041335_1830 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 1830 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130009398 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22712 | 22NDXXXNW638509 | 332233 |  | RAN Only | Integration | 4000041335_1830 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 1830 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130009398 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22713 | 22NDXXXNW638509 | 332234 |  | RAN Only | Integration | 4000041335_1830 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 1830 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130009398 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22714 | 22NDXXXNW638509 | 332235 |  | RAN Only | Integration | 4000041335_1830 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704092 | 1830 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01JHO0030 | KEUTAPANG_JHO_ST |  |  |  | 01JHO0030 | KEUTAPANG_JHO_ST | [12 empty] | 2022-12-23 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 183AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130009398 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638509 | 171057FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171057 | 171057FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599309 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22721 | 22NDXXXNW638538 | 332336 |  | RAN Only | Integration | 4000041335_2120 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 2120 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22722 | 22NDXXXNW638538 | 332337 |  | RAN Only | Integration | 4000041335_2120 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 2120 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22723 | 22NDXXXNW638538 | 332338 |  | RAN Only | Integration | 4000041335_2120 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 2120 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010888 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22724 | 22NDXXXNW638539 | 332339 |  | RAN Only | Integration | 4000041335_2130 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 2130 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010767 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22725 | 22NDXXXNW638539 | 332340 |  | RAN Only | Integration | 4000041335_2130 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 2130 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010767 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22726 | 22NDXXXNW638539 | 332341 |  | RAN Only | Integration | 4000041335_2130 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 2130 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010767 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22727 | 22NDXXXNW638539 | 332342 |  | RAN Only | Integration | 4000041335_2130 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 2130 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010767 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22745 | 22NDXXXNW638581 | 332496 |  | RAN Only | Integration | 4000041335_2550 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 2550 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010708 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22746 | 22NDXXXNW638581 | 332497 |  | RAN Only | Integration | 4000041335_2550 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 2550 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010708 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22747 | 22NDXXXNW638581 | 332498 |  | RAN Only | Integration | 4000041335_2550 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 2550 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010708 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22748 | 22NDXXXNW638581 | 332499 |  | RAN Only | Integration | 4000041335_2550 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 2550 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130010708 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22749 | 22NDXXXNW639711 | 332523 |  | RAN Only | Integration | 4000041335_2620 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 2620 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008513 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22750 | 22NDXXXNW639711 | 332524 |  | RAN Only | Integration | 4000041335_2620 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 2620 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008513 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22751 | 22NDXXXNW639711 | 332525 |  | RAN Only | Integration | 4000041335_2620 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 2620 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008513 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22752 | 22NDXXXNW639711 | 332526 |  | RAN Only | Integration | 4000041335_2620 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704171 | 2620 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008513 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22753 | 22NDXXXNW639727 | 332584 |  | RAN Only | Integration | 4000041335_2780 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 2780 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008477 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22754 | 22NDXXXNW639727 | 332585 |  | RAN Only | Integration | 4000041335_2780 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 2780 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008477 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22755 | 22NDXXXNW639727 | 332586 |  | RAN Only | Integration | 4000041335_2780 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 2780 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008477 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22756 | 22NDXXXNW639727 | 332587 |  | RAN Only | Integration | 4000041335_2780 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704187 | 2780 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008477 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22757 | 22NDXXXNW639729 | 332591 |  | RAN Only | Integration | 4000041335_2800 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 2800 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129927848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22758 | 22NDXXXNW639729 | 332592 |  | RAN Only | Integration | 4000041335_2800 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 2800 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129927848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22759 | 22NDXXXNW639729 | 332593 |  | RAN Only | Integration | 4000041335_2800 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704189 | 2800 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KBJ0059 | AJIJAHE_KARO_PL |  |  |  | 02KBJ0059 | AJIJAHE_KARO_PL | [12 empty] | 2023-03-03 |  |  |  | 2023-03-09 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 280AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2009-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129927848 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639729 | 171086FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171086 | 171086FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541640 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22760 | 22NDXXXNW639736 | 332615 |  | RAN Only | Integration | 4000041335_2870 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 2870 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22761 | 22NDXXXNW639736 | 332616 |  | RAN Only | Integration | 4000041335_2870 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 2870 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22762 | 22NDXXXNW639736 | 332617 |  | RAN Only | Integration | 4000041335_2870 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 2870 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22763 | 22NDXXXNW639736 | 332618 |  | RAN Only | Integration | 4000041335_2870 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704196 | 2870 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130008538 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22764 | 22NDXXXNW639747 | 332657 |  | RAN Only | Integration | 4000041335_2980 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 2980 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011228 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22765 | 22NDXXXNW639747 | 332658 |  | RAN Only | Integration | 4000041335_2980 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 2980 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011228 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22766 | 22NDXXXNW639747 | 332659 |  | RAN Only | Integration | 4000041335_2980 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 2980 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011228 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22767 | 22NDXXXNW639747 | 332660 |  | RAN Only | Integration | 4000041335_2980 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 2980 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011228 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22768 | 22NDXXXNW639749 | 332664 |  | RAN Only | Integration | 4000041335_3000 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 3000 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011359 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22769 | 22NDXXXNW639749 | 332665 |  | RAN Only | Integration | 4000041335_3000 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 3000 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011359 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22770 | 22NDXXXNW639749 | 332666 |  | RAN Only | Integration | 4000041335_3000 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 3000 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011359 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22775 | 22NDXXXNW639768 | 332737 |  | RAN Only | Integration | 4000041335_3190 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 3190 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011256 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22776 | 22NDXXXNW639768 | 332738 |  | RAN Only | Integration | 4000041335_3190 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 3190 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011256 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22777 | 22NDXXXNW639768 | 332739 |  | RAN Only | Integration | 4000041335_3190 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704228 | 3190 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KBJ0024 | KUTA_RAKYAT_TB |  |  |  | 02KBJ0024 | KUTA_RAKYAT_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-03-13 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 319AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%2013-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIA%20CJ_WJ_EJ_BN_KALISUMAPA_SUMATERA.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130011256 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639768 | 171093FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171093 | 171093FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0541684 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22778 | 22NDXXXNW639866 | 332744 |  | RAN Only | Integration | 4000041335_3210 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 3210 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417269 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22779 | 22NDXXXNW639866 | 332745 |  | RAN Only | Integration | 4000041335_3210 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 3210 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417269 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22780 | 22NDXXXNW639866 | 332746 |  | RAN Only | Integration | 4000041335_3210 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 3210 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417269 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22781 | 22NDXXXNW639866 | 332747 |  | RAN Only | Integration | 4000041335_3210 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704230 | 3210 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KIS0094 | SUMBUT_UMBUT_CM |  |  |  | 02KIS0094 | SUMBUT_UMBUT_CM | [12 empty] | 2023-01-27 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 321AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417269 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639866 | 171095FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171095 | 171095FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606245 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22798 | 22NDXXXNW639901 | 332879 |  | RAN Only | Integration | 4000041335_3560 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 3560 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130383382 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22799 | 22NDXXXNW639901 | 332880 |  | RAN Only | Integration | 4000041335_3560 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 3560 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130383382 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22800 | 22NDXXXNW639901 | 332881 |  | RAN Only | Integration | 4000041335_3560 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704265 | 3560 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KIS0015 | TERUSAN_MT |  |  |  | 02KIS0015 | TERUSAN_MT | [12 empty] | 2023-01-27 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 356AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130383382 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639901 | 171107FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171107 | 171107FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606279 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22805 | 22NDXXXNW639940 | 333021 |  | RAN Only | Integration | 4000041335_3950 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 3950 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130383710 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22806 | 22NDXXXNW639940 | 333022 |  | RAN Only | Integration | 4000041335_3950 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 3950 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130383710 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22807 | 22NDXXXNW639940 | 333023 |  | RAN Only | Integration | 4000041335_3950 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704304 | 3950 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130383710 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22817 | 22NDXXXNW640168 | 333166 |  | RAN Only | Integration | 4000041335_4350 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 4350 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386175 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22818 | 22NDXXXNW640168 | 333167 |  | RAN Only | Integration | 4000041335_4350 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 4350 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386175 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22819 | 22NDXXXNW640168 | 333168 |  | RAN Only | Integration | 4000041335_4350 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 4350 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386175 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22820 | 22NDXXXNW640168 | 333169 |  | RAN Only | Integration | 4000041335_4350 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704344 | 4350 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LGS0032 | ALUE_BU_TUHA_CM |  |  |  | 01LGS0032 | ALUE_BU_TUHA_CM | [12 empty] | 2022-11-04 |  |  |  | 2023-05-22 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 435AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2022-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386175 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640168 | 171115FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171115 | 171115FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606356 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22821 | 22NDXXXNW640178 | 333206 |  | RAN Only | Integration | 4000041335_4450 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 4450 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386484 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22822 | 22NDXXXNW640178 | 333207 |  | RAN Only | Integration | 4000041335_4450 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 4450 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386484 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22823 | 22NDXXXNW640178 | 333208 |  | RAN Only | Integration | 4000041335_4450 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 4450 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386484 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22824 | 22NDXXXNW640178 | 333209 |  | RAN Only | Integration | 4000041335_4450 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704354 | 4450 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LGS0019 | SEUNEUBOK_RAMBONG_CM |  |  |  | 01LGS0019 | SEUNEUBOK_RAMBONG_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 445AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386484 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640178 | 171116FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171116 | 171116FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606362 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22836 | 22NDXXXNW640231 | 333395 |  | RAN Only | Integration | 4000041335_4980 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 4980 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22837 | 22NDXXXNW640231 | 333396 |  | RAN Only | Integration | 4000041335_4980 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 4980 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22838 | 22NDXXXNW640231 | 333397 |  | RAN Only | Integration | 4000041335_4980 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 4980 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22839 | 22NDXXXNW640231 | 333398 |  | RAN Only | Integration | 4000041335_4980 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704407 | 4980 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LHK0084 | CEMPEDAK_MT |  |  |  | 01LHK0084 | CEMPEDAK_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 498AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386926 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640231 | 171121FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171121 | 171121FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606400 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22851 | 22NDXXXNW640244 | 333444 |  | RAN Only | Integration | 4000041335_5110 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 5110 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130414338 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22852 | 22NDXXXNW640244 | 333445 |  | RAN Only | Integration | 4000041335_5110 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 5110 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130414338 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22853 | 22NDXXXNW640244 | 333446 |  | RAN Only | Integration | 4000041335_5110 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704420 | 5110 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LHK0046 | TUNONG_KRUENG_MT |  |  |  | 01LHK0046 | TUNONG_KRUENG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-05 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 511AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130414338 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640244 | 171125FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171125 | 171125FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606407 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22863 | 22NDXXXNW640272 | 333533 |  | RAN Only | Integration | 4000041335_5390 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 5390 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130384559 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22864 | 22NDXXXNW640272 | 333534 |  | RAN Only | Integration | 4000041335_5390 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 5390 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130384559 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22865 | 22NDXXXNW640272 | 333535 |  | RAN Only | Integration | 4000041335_5390 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704448 | 5390 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LGS0010 | SIMPANG_ULIM_PL |  |  |  | 01LGS0010 | SIMPANG_ULIM_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 539AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130384559 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640272 | 171130FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171130 | 171130FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606422 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22884 | 22NDXXXNW640361 | 333848 |  | RAN Only | Integration | 4000041335_6280 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 6280 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130423064 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22885 | 22NDXXXNW640361 | 333849 |  | RAN Only | Integration | 4000041335_6280 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 6280 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130423064 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22886 | 22NDXXXNW640361 | 333850 |  | RAN Only | Integration | 4000041335_6280 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704537 | 6280 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LSW0025 | UTEUNBAYI_TB |  |  |  | 01LSW0025 | UTEUNBAYI_TB | [12 empty] | 2023-03-31 |  |  |  | 2023-04-18 |  | 2023-05-10 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230515_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130423064 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640361 | 171137FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171137 | 171137FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603289 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22887 | 22NDXXXNW640362 | 333851 |  | RAN Only | Integration | 4000041335_6290 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 6290 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130009036 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22888 | 22NDXXXNW640362 | 333852 |  | RAN Only | Integration | 4000041335_6290 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 6290 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130009036 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22889 | 22NDXXXNW640362 | 333853 |  | RAN Only | Integration | 4000041335_6290 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704538 | 6290 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01BIR0042 | MEUNASAH_CAPA_TB |  |  |  | 01BIR0042 | MEUNASAH_CAPA_TB | [12 empty] | 2022-11-04 |  |  |  | 2023-05-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 629AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130009036 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640362 | 171138FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171138 | 171138FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599270 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22894 | 22NDXXXNW640395 | 333975 |  | RAN Only | Integration, Expansion | 4000041335_6620 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 6620 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414320 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22895 | 22NDXXXNW640395 | 333976 |  | RAN Only | Integration, Expansion | 4000041335_6620 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 6620 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414320 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22896 | 22NDXXXNW640395 | 333977 |  | RAN Only | Integration, Expansion | 4000041335_6620 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 6620 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414320 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22897 | 22NDXXXNW640395 | 333978 |  | RAN Only | Integration, Expansion | 4000041335_6620 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 6620 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414320 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22898 | 22NDXXXNW640397 | 333983 |  | RAN Only | Integration | 4000041335_6640 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 6640 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414198 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22899 | 22NDXXXNW640397 | 333984 |  | RAN Only | Integration | 4000041335_6640 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 6640 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414198 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22900 | 22NDXXXNW640397 | 333985 |  | RAN Only | Integration | 4000041335_6640 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 6640 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414198 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22901 | 22NDXXXNW640397 | 333986 |  | RAN Only | Integration | 4000041335_6640 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 6640 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414198 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22902 | 22NDXXXNW640401 | 333999 |  | RAN Only | Integration | 4000041335_6680 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 6680 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414087 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22903 | 22NDXXXNW640401 | 334000 |  | RAN Only | Integration | 4000041335_6680 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 6680 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414087 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22904 | 22NDXXXNW640401 | 334001 |  | RAN Only | Integration | 4000041335_6680 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 6680 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414087 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22905 | 22NDXXXNW640401 | 334002 |  | RAN Only | Integration | 4000041335_6680 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 6680 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414087 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22920 | 22NDXXXNW640436 | 334137 |  | RAN Only | Integration | 4000041335_7030 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 7030 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22921 | 22NDXXXNW640436 | 334138 |  | RAN Only | Integration | 4000041335_7030 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 7030 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22922 | 22NDXXXNW640436 | 334139 |  | RAN Only | Integration | 4000041335_7030 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 7030 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22923 | 22NDXXXNW640436 | 334140 |  | RAN Only | Integration | 4000041335_7030 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 7030 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130416913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22928 | 22NDXXXNW640611 | 334175 |  | RAN Only | Integration | 4000041335_7130 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 7130 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22929 | 22NDXXXNW640611 | 334176 |  | RAN Only | Integration | 4000041335_7130 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 7130 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22930 | 22NDXXXNW640611 | 334177 |  | RAN Only | Integration | 4000041335_7130 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704622 | 7130 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PYB0024 | DESA_HURABA_MT |  |  |  | 02PYB0024 | DESA_HURABA_MT | [12 empty] | 2023-04-21 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 713AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1129995552 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMADINA%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640611 | 171151FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171151 | 171151FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0540538 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22935 | 22NDXXXNW642570 | 334230 |  | RAN Only | Integration | 4000041335_7280 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 7280 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22936 | 22NDXXXNW642570 | 334231 |  | RAN Only | Integration | 4000041335_7280 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 7280 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22937 | 22NDXXXNW642570 | 334232 |  | RAN Only | Integration | 4000041335_7280 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 7280 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22938 | 22NDXXXNW642570 | 334233 |  | RAN Only | Integration | 4000041335_7280 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704637 | 7280 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02RAP0068 | CINTA_MAKMUR_MT |  |  |  | 02RAP0068 | CINTA_MAKMUR_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 728AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385488 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642570 | 171153FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171153 | 171153FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614578 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22939 | 22NDXXXNW642571 | 334234 |  | RAN Only | Integration | 4000041335_7290 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 7290 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385939 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22940 | 22NDXXXNW642571 | 334235 |  | RAN Only | Integration | 4000041335_7290 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 7290 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385939 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22941 | 22NDXXXNW642571 | 334236 |  | RAN Only | Integration | 4000041335_7290 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 7290 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385939 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22942 | 22NDXXXNW642571 | 334237 |  | RAN Only | Integration | 4000041335_7290 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704638 | 7290 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02RAP0073 | SEI_PINANG_RAP_MT |  |  |  | 02RAP0073 | SEI_PINANG_RAP_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 729AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385939 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642571 | 171154FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171154 | 171154FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614579 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22943 | 22NDXXXNW642582 | 334278 |  | RAN Only | Integration | 4000041335_7400 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 7400 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385874 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22944 | 22NDXXXNW642582 | 334279 |  | RAN Only | Integration | 4000041335_7400 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 7400 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385874 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22945 | 22NDXXXNW642582 | 334280 |  | RAN Only | Integration | 4000041335_7400 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 7400 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385874 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22946 | 22NDXXXNW642582 | 334281 |  | RAN Only | Integration | 4000041335_7400 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704649 | 7400 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02RAP0074 | BAGAN_BILAH_MT |  |  |  | 02RAP0074 | BAGAN_BILAH_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-03 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 740AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130385874 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642582 | 171155FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171155 | 171155FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-19 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614590 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22947 | 22NDXXXNW642584 | 334286 |  | RAN Only | Integration | 4000041335_7420 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 7420 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386407 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22948 | 22NDXXXNW642584 | 334287 |  | RAN Only | Integration | 4000041335_7420 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 7420 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386407 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22949 | 22NDXXXNW642584 | 334288 |  | RAN Only | Integration | 4000041335_7420 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 7420 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386407 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22950 | 22NDXXXNW642584 | 334289 |  | RAN Only | Integration | 4000041335_7420 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 7420 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130386407 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22958 | 22NDXXXNW642670 | 334602 |  | RAN Only | Integration | 4000041335_8280 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 8280 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415324 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22959 | 22NDXXXNW642670 | 334603 |  | RAN Only | Integration | 4000041335_8280 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 8280 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415324 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22960 | 22NDXXXNW642670 | 334604 |  | RAN Only | Integration | 4000041335_8280 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 8280 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415324 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22961 | 22NDXXXNW642670 | 334605 |  | RAN Only | Integration | 4000041335_8280 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704737 | 8280 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMS0008 | SIMARIMBUN2_CM |  |  |  | 02PMS0008 | SIMARIMBUN2_CM | [12 empty] | 2023-02-24 |  |  |  | 2023-02-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 828AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_28-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415324 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642670 | 171159FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171159 | 171159FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614675 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22962 | 22NDXXXNW642695 | 334698 |  | RAN Only | Integration | 4000041335_8530 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 8530 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415832 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22963 | 22NDXXXNW642695 | 334699 |  | RAN Only | Integration | 4000041335_8530 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 8530 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415832 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22964 | 22NDXXXNW642695 | 334700 |  | RAN Only | Integration | 4000041335_8530 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 8530 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415832 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22965 | 22NDXXXNW642695 | 334701 |  | RAN Only | Integration | 4000041335_8530 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704762 | 8530 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0073 | BRIDGESTONE_SUMATERA_MT |  |  |  | 02PMR0073 | BRIDGESTONE_SUMATERA_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-28 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 853AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415832 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642695 | 171160FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171160 | 171160FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614692 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22966 | 22NDXXXNW642710 | 334753 |  | RAN Only | Integration | 4000041335_8680 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 8680 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415435 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22967 | 22NDXXXNW642710 | 334754 |  | RAN Only | Integration | 4000041335_8680 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 8680 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415435 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22968 | 22NDXXXNW642710 | 334755 |  | RAN Only | Integration | 4000041335_8680 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 8680 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415435 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22969 | 22NDXXXNW642710 | 334756 |  | RAN Only | Integration | 4000041335_8680 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704777 | 8680 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0083 | SERBELAWAN2_EB |  |  |  | 02PMR0083 | SERBELAWAN2_EB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 868AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415435 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642710 | 171161FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171161 | 171161FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614696 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22970 | 22NDXXXNW642713 | 334764 |  | RAN Only | Integration | 4000041335_8710 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 8710 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415196 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22971 | 22NDXXXNW642713 | 334765 |  | RAN Only | Integration | 4000041335_8710 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 8710 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415196 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22972 | 22NDXXXNW642713 | 334766 |  | RAN Only | Integration | 4000041335_8710 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 8710 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415196 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22973 | 22NDXXXNW642713 | 334767 |  | RAN Only | Integration | 4000041335_8710 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704780 | 8710 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMS0006 | TAMAN_BEO_RINDAM_GT |  |  |  | 02PMS0006 | TAMAN_BEO_RINDAM_GT | [12 empty] | 2023-04-07 |  |  |  | 2023-03-01 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 871AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_01-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415196 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642713 | 171162FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171162 | 171162FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603331 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22974 | 22NDXXXNW642724 | 334803 |  | RAN Only | Integration | 4000041335_8820 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 8820 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415810 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22975 | 22NDXXXNW642724 | 334804 |  | RAN Only | Integration | 4000041335_8820 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 8820 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415810 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22976 | 22NDXXXNW642724 | 334805 |  | RAN Only | Integration | 4000041335_8820 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704791 | 8820 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0060 | DOLOK_KAHEAN_PL |  |  |  | 02PMR0060 | DOLOK_KAHEAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 882AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415810 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642724 | 171163FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171163 | 171163FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614704 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22977 | 22NDXXXNW642726 | 334809 |  | RAN Only | Integration | 4000041335_8840 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 8840 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951333 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22978 | 22NDXXXNW642726 | 334810 |  | RAN Only | Integration | 4000041335_8840 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 8840 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951333 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22979 | 22NDXXXNW642726 | 334811 |  | RAN Only | Integration | 4000041335_8840 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 8840 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951333 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22980 | 22NDXXXNW642728 | 334815 |  | RAN Only | Integration | 4000041335_8860 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 8860 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951306 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22981 | 22NDXXXNW642728 | 334816 |  | RAN Only | Integration | 4000041335_8860 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 8860 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951306 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22982 | 22NDXXXNW642728 | 334817 |  | RAN Only | Integration | 4000041335_8860 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704795 | 8860 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02BGE0020 | DOLOK_NAULI_PORSEA_PL |  |  |  | 02BGE0020 | DOLOK_NAULI_PORSEA_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 886AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951306 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642728 | 171165FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171165 | 171165FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559047 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22983 | 22NDXXXNW642729 | 334818 |  | RAN Only | Integration | 4000041335_8870 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 8870 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951254 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22984 | 22NDXXXNW642729 | 334819 |  | RAN Only | Integration | 4000041335_8870 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 8870 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951254 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22985 | 22NDXXXNW642729 | 334820 |  | RAN Only | Integration | 4000041335_8870 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704796 | 8870 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL |  |  |  | 02BGE0014 | LUMBAN_SITORUS_PATANE_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-26 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 887AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1129951254 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642729 | 171166FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171166 | 171166FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559048 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22986 | 22NDXXXNW642732 | 334827 |  | RAN Only | Integration | 4000041335_8900 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 8900 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415084 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22987 | 22NDXXXNW642732 | 334828 |  | RAN Only | Integration | 4000041335_8900 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 8900 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415084 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22988 | 22NDXXXNW642732 | 334829 |  | RAN Only | Integration | 4000041335_8900 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 8900 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415084 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22995 | 22NDXXXNW642752 | 334894 |  | RAN Only | Integration | 4000041335_9100 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 9100 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415259 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22996 | 22NDXXXNW642752 | 334895 |  | RAN Only | Integration | 4000041335_9100 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 9100 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415259 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22997 | 22NDXXXNW642752 | 334896 |  | RAN Only | Integration | 4000041335_9100 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 9100 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415259 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22998 | 22NDXXXNW642752 | 334897 |  | RAN Only | Integration | 4000041335_9100 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704819 | 9100 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0084 | MEKAR_MULIA_PL |  |  |  | 02PMR0084 | MEKAR_MULIA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-17 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 910AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130415259 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642752 | 171170FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171170 | 171170FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614717 | 2023-03-24 | 2023_Q2 INT PAC P04 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 22999 | 22NDXXXNW642756 | 334910 |  | RAN Only | Integration | 4000041335_9140 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 9140 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415770 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23000 | 22NDXXXNW642756 | 334911 |  | RAN Only | Integration | 4000041335_9140 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 9140 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415770 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23001 | 22NDXXXNW642756 | 334912 |  | RAN Only | Integration | 4000041335_9140 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 9140 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415770 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23002 | 22NDXXXNW642756 | 334913 |  | RAN Only | Integration | 4000041335_9140 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704823 | 9140 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0064 | KARANG_BANGUN_PL |  |  |  | 02PMR0064 | KARANG_BANGUN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-05-03 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 914AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415770 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642756 | 171171FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171171 | 171171FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614721 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23003 | 22NDXXXNW642766 | 334944 |  | RAN Only | Integration | 4000041335_9240 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 9240 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415790 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23004 | 22NDXXXNW642766 | 334945 |  | RAN Only | Integration | 4000041335_9240 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 9240 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415790 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23005 | 22NDXXXNW642766 | 334946 |  | RAN Only | Integration | 4000041335_9240 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 9240 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415790 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23006 | 22NDXXXNW642766 | 334947 |  | RAN Only | Integration | 4000041335_9240 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704833 | 9240 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PMR0055 | DUSUN7_MENCIRIN_ST |  |  |  | 02PMR0055 | DUSUN7_MENCIRIN_ST | [12 empty] | 2023-02-24 |  |  |  | 2023-05-19 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 924AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2019-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130415790 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642766 | 171172FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171172 | 171172FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614726 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23010 | 22NDXXXNW642811 | 335113 |  | RAN Only | Integration | 4000041335_9690 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 9690 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414436 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23011 | 22NDXXXNW642811 | 335114 |  | RAN Only | Integration | 4000041335_9690 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 9690 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414436 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23012 | 22NDXXXNW642811 | 335115 |  | RAN Only | Integration | 4000041335_9690 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 9690 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414436 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23013 | 22NDXXXNW642811 | 335116 |  | RAN Only | Integration | 4000041335_9690 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 9690 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414436 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23014 | 22NDXXXNW642813 | 335121 |  | RAN Only | Integration | 4000041335_9710 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 9710 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414550 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23015 | 22NDXXXNW642813 | 335122 |  | RAN Only | Integration | 4000041335_9710 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 9710 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414550 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23016 | 22NDXXXNW642813 | 335123 |  | RAN Only | Integration | 4000041335_9710 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 9710 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414550 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23017 | 22NDXXXNW642813 | 335124 |  | RAN Only | Integration | 4000041335_9710 | 4000041335 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 9710 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414550 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23022 | 22NDXXXNW642829 | 335184 |  | RAN Only | Integration | 4000041335_9870 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 9870 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417012 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23023 | 22NDXXXNW642829 | 335185 |  | RAN Only | Integration | 4000041335_9870 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 9870 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417012 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23024 | 22NDXXXNW642829 | 335186 |  | RAN Only | Integration | 4000041335_9870 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 9870 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417012 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23025 | 22NDXXXNW642829 | 335187 |  | RAN Only | Integration | 4000041335_9870 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704896 | 9870 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02TRT0021 | PARBAJUJULU_EB |  |  |  | 02TRT0021 | PARBAJUJULU_EB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 987AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417012 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642829 | 171177FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171177 | 171177FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23026 | 22NDXXXNW642841 | 335226 |  | RAN Only | Integration | 4000041335_9990 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 9990 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417236 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23027 | 22NDXXXNW642841 | 335227 |  | RAN Only | Integration | 4000041335_9990 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 9990 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417236 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23028 | 22NDXXXNW642841 | 335228 |  | RAN Only | Integration | 4000041335_9990 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 9990 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130417236 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23029 | 22NDXXXNW642844 | 335235 |  | RAN Only | Integration | 4000041336_30 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 30 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413481 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23030 | 22NDXXXNW642844 | 335236 |  | RAN Only | Integration | 4000041336_30 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 30 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413481 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23031 | 22NDXXXNW642844 | 335237 |  | RAN Only | Integration | 4000041336_30 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704911 | 30 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL |  |  |  | 02TRT0009 | SIBORONG_BORONG_PANIARAN_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1002AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413481 | [5 empty] | NEED CA | 22NDXXXNW642844 | 171001FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171001 | 171001FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614778 | 2023-06-15 | 2023_Q3 INT plan P07 waiting CL | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23032 | 22NDXXXNW642850 | 335253 |  | RAN Only | Integration | 4000041336_90 | 4000041336 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 90 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413588 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23033 | 22NDXXXNW642850 | 335254 |  | RAN Only | Integration | 4000041336_90 | 4000041336 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 90 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413588 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23034 | 22NDXXXNW642850 | 335255 |  | RAN Only | Integration | 4000041336_90 | 4000041336 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704917 | 90 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02TRT0015 | HUTATORUAN_TARUTUNG_PL |  |  |  | 02TRT0015 | HUTATORUAN_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1008AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413588 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642850 | 171002FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171002 | 171002FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614784 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23035 | 22NDXXXNW642851 | 335256 |  | RAN Only | Integration | 4000041336_100 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 100 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413626 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23036 | 22NDXXXNW642851 | 335257 |  | RAN Only | Integration | 4000041336_100 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 100 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413626 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23037 | 22NDXXXNW642851 | 335258 |  | RAN Only | Integration | 4000041336_100 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704918 | 100 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02TRT0008 | TDPARDEDE_TARUTUNG_PL |  |  |  | 02TRT0008 | TDPARDEDE_TARUTUNG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-18 |  | 2023-05-25 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1009AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413626 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642851 | 171003FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171003 | 171003FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614785 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23042 | 22NDXXXNW642908 | 335463 |  | RAN Only | Integration | 4000041336_670 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 670 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23043 | 22NDXXXNW642908 | 335464 |  | RAN Only | Integration | 4000041336_670 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 670 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23044 | 22NDXXXNW642908 | 335465 |  | RAN Only | Integration | 4000041336_670 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 670 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23045 | 22NDXXXNW642908 | 335466 |  | RAN Only | Integration | 4000041336_670 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704975 | 670 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02TRT0024 | PARBUBU_PEA_TB |  |  |  | 02TRT0024 | PARBUBU_PEA_TB | [12 empty] | 2023-04-28 |  |  |  | 2023-04-14 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1066AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130413748 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642908 | 171005FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171005 | 171005FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0614851 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23053 | 22NDXXXNW643025 | 335642 |  | RAN Only | Integration | 4000041336_1160 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 1160 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130387385 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23054 | 22NDXXXNW643025 | 335643 |  | RAN Only | Integration | 4000041336_1160 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 1160 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130387385 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23055 | 22NDXXXNW643025 | 335644 |  | RAN Only | Integration | 4000041336_1160 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 1160 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130387385 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23059 | 22NDXXXNW643076 | 335830 |  | RAN Only | Integration | 4000041336_1670 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 1670 | 4100000512 | SB1 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 1 Technology - with No Power Requirements | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 83250456 | 29187609.8734 | 83250456 | 29187609.8734 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130009046 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23060 | 22NDXXXNW643076 | 335831 |  | RAN Only | Integration | 4000041336_1670 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 1670 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130009046 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23061 | 22NDXXXNW643076 | 335832 |  | RAN Only | Integration | 4000041336_1670 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 1670 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130009046 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23062 | 22NDXXXNW643076 | 335833 |  | RAN Only | Integration | 4000041336_1670 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705075 | 1670 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02TBT0005 | PELITA_BAJENIS_TB |  |  |  | 02TBT0005 | PELITA_BAJENIS_TB | [12 empty] | 2023-02-03 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1166AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130009046 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643076 | 171011FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171011 | 171011FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0559097 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23111 | 22NDXXXNW655195 | 336741 |  | RAN Only | Integration | 4000041336_5130 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 5130 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130387219 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23112 | 22NDXXXNW655195 | 336742 |  | RAN Only | Integration | 4000041336_5130 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 5130 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130387219 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23113 | 22NDXXXNW655195 | 336743 |  | RAN Only | Integration | 4000041336_5130 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 5130 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130387219 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23114 | 22NDXXXNW655195 | 336744 |  | RAN Only | Integration | 4000041336_5130 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705421 | 5130 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130387219 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23131 | 22NDXXXNW652261 | 337064 |  | RAN Only | Integration | 4000041336_6290 | 4000041336 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 6290 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414869 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23132 | 22NDXXXNW652261 | 337065 |  | RAN Only | Integration | 4000041336_6290 | 4000041336 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 6290 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414869 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23133 | 22NDXXXNW652261 | 337066 |  | RAN Only | Integration | 4000041336_6290 | 4000041336 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 6290 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414869 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23134 | 22NDXXXNW652261 | 337067 |  | RAN Only | Integration | 4000041336_6290 | 4000041336 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705537 | 6290 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130414869 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23144 | 22NDXXXNW652485 | 337186 |  | RAN Only | Integration | 4000041336_6680 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 6680 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130001340 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23145 | 22NDXXXNW652485 | 337187 |  | RAN Only | Integration | 4000041336_6680 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 6680 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130001340 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23146 | 22NDXXXNW652485 | 337188 |  | RAN Only | Integration | 4000041336_6680 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 6680 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130001340 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23178 | 22NDXXXNW639016 | 338008 |  | RAN Only | Integration, Expansion | 4000041340_440 | 4000041340 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 440 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130490035 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041340 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23179 | 22NDXXXNW639016 | 338009 |  | RAN Only | Integration, Expansion | 4000041340_440 | 4000041340 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 440 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130490035 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041340 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23180 | 22NDXXXNW639016 | 338010 |  | RAN Only | Integration, Expansion | 4000041340_440 | 4000041340 |  |  | KKNo3586 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 440 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 2 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130490035 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041340 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23207 | 22NDXXXNW640879 | 339514 |  | RAN Only | Integration, Expansion | 4000041340_5720 | 4000041340 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 5720 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130339592 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041340 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23208 | 22NDXXXNW640879 | 339515 |  | RAN Only | Integration, Expansion | 4000041340_5720 | 4000041340 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 5720 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130339592 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041340 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23209 | 22NDXXXNW640879 | 339516 |  | RAN Only | Integration, Expansion | 4000041340_5720 | 4000041340 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000711878 | 5720 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 2 | NS | 02MDN0440 | PERUMNAS_MARTUBUNG_CM |  |  |  | 02MDN0440 | PERUMNAS_MARTUBUNG_CM | [12 empty] | 2023-04-21 |  |  |  | 2022-10-07 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2556AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-October-2022_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_SUMATERA_KALISUMAPA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41240 HW 15%,PO 4_41324 IM 15%,PO 4_41241 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41240 HW 40%,PO 4_41324 IM 40%,PO 4_41241 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41240 HW 25%,PO 4_41324 IM 25%,PO 4_41241 IM 25% |  | AOP2022PAC020 | 2022-11-25 | 2022-11-25 | [9 empty] | 1130339592 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DMEDAN%20INNER%202%2D9&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640879 | 171077FDAUCAUCFPRJSSAC2023 | 4000041340 |  | 2023-06-02 |  | 2023-06-21 |  | 171077 | 171077FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 |  |  |  |  | NIR |  | SMP-WO-0614179 | 2022-11-25 | 2022_Q4 INT PAC P11 | 2. SO DONE
1.12 AOP 2022 MOCN Expansion | 102 | 22NDXXXNW655195 | 367702 |  | RAN Only | Integration | 4000042573_10 | 4000042573 |  |  | KKNo3688 | 1. HW | AOP 2022 MOCN Expansion | AOP 2022 MOCN Integration | BTS | 1000705421 | 10 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 4 |  | NAT | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 529464.0004 | 209667.9996 | 2117856.0016 | 838671.9984 |  | 161818FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131649790 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.12 AOP 2022 MOCN Expansion | 103 | 22NDXXXNW652261 | 367746 |  | RAN Only | Integration | 4000042573_10 | 4000042573 |  |  | KKNo3586 | 1. HW | AOP 2022 MOCN Expansion | AOP 2022 MOCN Integration | BTS | 1000705537 | 10 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 2 |  | NAT | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 529464.0004 | 209667.9996 | 1058928.0008 | 419335.9992 |  | 161818FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131649818 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.12 AOP 2022 MOCN Expansion | 104 | 22NDXXXNW655195 | 369075 |  | RAN Only | Integration | 4000042573_30 | 4000042573 |  |  | KKNo3688 | 1. HW | AOP 2022 MOCN Expansion | AOP 2022 MOCN Integration | BTS | 1000705421 | 30 | 1100000126 | 473537A - FUTEY SM OD fiber LC OD-LC OD dual 80m | 2 |  | NAT | NS | 01LSW0009 | PULO_BARAT_TB |  |  |  | 01LSW0009 | PULO_BARAT_TB | [12 empty] | 2023-04-07 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1512AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 722515 | 286116 | 1445030.0001 | 572232.0001 |  | 161818FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131649790 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW655195 | 171033FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171033 | 171033FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606763 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.12 AOP 2022 MOCN Expansion | 105 | 22NDXXXNW652261 | 369099 |  | RAN Only | Integration | 4000042573_30 | 4000042573 |  |  | KKNo3586 | 1. HW | AOP 2022 MOCN Expansion | AOP 2022 MOCN Integration | BTS | 1000705537 | 30 | 1100000126 | 473537A - FUTEY SM OD fiber LC OD-LC OD dual 80m | 1 |  | NAT | NS | 02KIS0042 | MESJIDPULAURAKYAT_PL |  |  |  | 02KIS0042 | MESJIDPULAURAKYAT_PL | [12 empty] | 2023-02-03 |  |  |  | 2023-04-28 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1628AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 722515 | 286116 | 722515 | 286116 |  | 161818FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2028-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_42573 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_42573 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_42573 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131649818 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652261 | 171040FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171040 | 171040FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606798 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23253 | 22NDXXXNW642811 | 392483 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23254 | 22NDXXXNW642811 | 392484 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704878 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 02KPD0016 | SIPODANG_MT |  |  |  | 02KPD0016 | SIPODANG_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-04-12 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 969AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807444 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642811 | 171174FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171174 | 171174FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614750 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23255 | 22NDXXXNW642813 | 392485 |  | RAN Only | Integration | 4000041221_250 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 250 | 1100000308 | 471408A - FTCR OD Cable RJ45 CAT5E 15m | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 44904.0001 | 17781.9999 | 44904.0001 | 17781.9999 |  | 161820FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23256 | 22NDXXXNW642813 | 392486 |  | RAN Only | Integration | 4000041221_290 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704880 | 290 | 1100000875 | 472839A - FSAH EAC cable HDMI-D37 15m | 1 |  | NS Area 1 | NS | 02KPD0014 | BUKIT_PATUPANGAN_MT |  |  |  | 02KPD0014 | BUKIT_PATUPANGAN_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-05-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 971AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 345823.0002 | 136945.9997 | 345823.0002 | 136945.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130807493 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642813 | 171175FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171175 | 171175FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614752 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23258 | 22NDXXXNW639016 | 406437 |  | RAN Only | Integration, Expansion | 4000041368_170 | 4000041368 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705754 | 170 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | SS Area 4 | NS | 02STB0027 | SEILITUR_TASIK_CM |  |  |  | 02STB0027 | SEILITUR_TASIK_CM | [12 empty] | 2022-12-23 |  |  |  | 2023-02-07 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2028AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 189243.0003 | 180235.0334 | 378486.0006 | 360470.0667 |  | 161171FDAUCAUCFPRJBABT2022 | 2022-09-12 | 2022-09-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_07-Feb-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_%20_CJWJ_%20_EJBN_%20_KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41412 HW 15%,PO 4_41324 IM 15%,PO 4_41368 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41412 HW 40%,PO 4_41324 IM 40%,PO 4_41368 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41412 HW 25%,PO 4_41324 IM 25%,PO 4_41368 IM 25% |  | AOP2022PAC035 | 2023-02-27 | 2023-02-27 | [9 empty] | 1130786615 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639016 | 171060FDAUCAUCFPRJSSAC2023 | 4000041368 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-02 |  | 2023-06-21 |  | 171060 | 171060FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 |  |  |  |  | NIR |  | SMP-WO-0599791 | 2023-02-27 | 2023_Q1 INT PAC P02 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23259 | 22NDXXXNW640436 | 419716 |  | RAN Only | Integration | 4000041222_210 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704612 | 210 | 1300000820 | CP2018IM03 - Basic System Module | 2 |  | NS Area 1 | NS | 01LGS0021 | KETAPANG_MAMEH_TB |  |  |  | 01LGS0021 | KETAPANG_MAMEH_TB | [12 empty] | 2023-02-24 |  |  |  | 2023-04-18 |  | 2023-04-18 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 703AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 206511.0001 | 196681 | 413022.0001 | 393361.9999 |  | 161765FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-29 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230510_008.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC052 | 2023-05-30 | 2023-05-30 | [9 empty] | 1130954203 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640436 | 171148FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171148 | 171148FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606526 | 2023-05-30 | 2023_Q2 INT PAC P05 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23272 | 22NDXXXNW642726 | 422448 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704793 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0143 | PERTAMINA_SIBAGANDING_PL |  |  |  | 02PMR0143 | PERTAMINA_SIBAGANDING_PL | [12 empty] | 2022-11-11 |  |  |  | 2023-02-23 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 884AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_23-Feb-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289809 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642726 | 171164FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171164 | 171164FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0559045 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23273 | 22NDXXXNW638380 | 422490 |  | RAN Only | Integration | 4000041222_200 | 4000041222 |  |  | KKNo3586 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703963 | 200 | 1300000820 | CP2018IM01 - Basic RF Module | 2 |  | NS Area 1 | NS | 01NAD0009 | ULEE_LHEU_MT |  |  |  | 01NAD0009 | ULEE_LHEU_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 054AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 67792.9998 | 142362.0007 | 135585.9996 |  | 161419FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131288651 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638380 | 170998FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-01 |  | 2023-06-21 |  | 170998 | 170998FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599348 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23274 | 22NDXXXNW642732 | 422499 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704799 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL |  |  |  | 02PMR0074 | MARUBUN_I_MARUBUN_JAYA_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-03-02 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 890AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/RFC-%20RAN_%20_02-Mar-2023_%20_Phase%202022%20MOCN_%20_TOMAHAWK_%20_Capacity_%20_HN_%20_NOKIA__CJWJ__EJBN__KALISUMAPA_%20_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1131289383 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIANTAR%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642732 | 171167FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171167 | 171167FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614705 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23275 | 22NDXXXNW652485 | 422583 |  | RAN Only | Integration | 4000041319_420 | 4000041319 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705576 | 420 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | CJ Area 10 | NS | 01JHO0003 | LHOK_NGA_EP |  |  |  | 01JHO0003 | LHOK_NGA_EP | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1667AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37952519.9995 | 15029198 | 37952519.9995 | 15029198 |  | 161320FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131283443 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652485 | 171044FDAUCAUCFPRJSSAC2023 | 4000041319 |  | 2023-06-01 |  | 2023-06-21 |  | 171044 | 171044FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599283 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23276 | 22NDXXXNW638581 | 422592 |  | RAN Only | Integration | 4000041319_420 | 4000041319 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704164 | 420 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | CJ Area 10 | NS | 01NAD0003 | STASIUN_BANDAACEH_TB |  |  |  | 01NAD0003 | STASIUN_BANDAACEH_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 255AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37952519.9995 | 15029198 | 37952519.9995 | 15029198 |  | 161320FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131283436 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638581 | 171078FDAUCAUCFPRJSSAC2023 | 4000041319 |  | 2023-06-02 |  | 2023-06-21 |  | 171078 | 171078FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599341 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23287 | 22NDXXXNW642584 | 423217 |  | RAN Only | Integration | 4000041373_150 | 4000041373 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704651 | 150 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | EJ Area 12 | NS | 02RAP0043 | DANAU_BALAI_RAP1_MT |  |  |  | 02RAP0043 | DANAU_BALAI_RAP1_MT | [12 empty] | 2023-02-24 |  |  |  | 2023-03-15 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 742AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 38289454.9997 | 15162624.1799 | 38289454.9997 | 15162624.1799 |  | 161078FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416319 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DRANTAU%20PRAPAT%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642584 | 171156FDAUCAUCFPRJSSAC2023 | 4000041373 |  | 2023-06-02 |  | 2023-06-21 |  | 171156 | 171156FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614592 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1450 | 22NDXXXNW639711 | 423381 |  | RAN Only | Integration | 4000041228_320 | 4000041228 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704171 | 320 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | EJ Area 12 | NS | 02KBJ0053 | RAYA_BRASTAGI_CM |  |  |  | 02KBJ0053 | RAYA_BRASTAGI_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 262AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.2161 | 35887295.9999 | 14211369.2161 |  | 161257FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131415976 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639711 | 171079FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171079 | 171079FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541615 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1451 | 22NDXXXNW639727 | 423386 |  | RAN Only | Integration | 4000041228_320 | 4000041228 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704187 | 320 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | EJ Area 12 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 35887295.9999 | 14211369.2161 | 35887295.9999 | 14211369.2161 |  | 161257FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1452 | 22NDXXXNW639727 | 423387 |  | RAN Only | Integration | 4000041228_330 | 4000041228 |  |  | KKNo3688 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704187 | 330 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | EJ Area 12 | NS | 02KBJ0043 | KENANGAN_GUNDALING_PL |  |  |  | 02KBJ0043 | KENANGAN_GUNDALING_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-04-05 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 278AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34114367.9999 | 13509289.7287 | 34114367.9999 | 13509289.7287 |  | 161428FDAUCAUCFPRJBABT2022 | 2022-10-07 | 2022-10-11 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2005-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41228 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41228 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41228 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416037 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639727 | 171084FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171084 | 171084FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541638 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 631 | 22NDXXXNW639736 | 423389 |  | RAN Only | Integration | 4000041249_180 | 4000041249 |  |  | KKNo3586 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000704196 | 180 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | CJ Area 10 | NS | 02KBJ0061 | MIKI_HOTEL_PL |  |  |  | 02KBJ0061 | MIKI_HOTEL_PL | [12 empty] | 2023-01-13 |  |  |  | 2023-03-21 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 287AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34114367.9999 | 13509289.7287 | 34114367.9999 | 13509289.7287 |  | 161412FDAUCAUCFPRJBABT2022 | 2022-10-07 | 2022-10-11 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/_Ready%20For%20Commercial%20-%20RAN_21-Mar-2023__Phase%202022%20MOCN__TOMAHAWK__Capacity__HN__NOKIA__CJWJ__EJBN__KALISUMAPA__SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41249 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41249 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41249 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416170 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639736 | 171087FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171087 | 171087FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541647 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23288 | 22NDXXXNW639747 | 423393 |  | RAN Only | Integration | 4000041373_160 | 4000041373 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704207 | 160 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | EJ Area 12 | NS | 02KBJ0054 | LAU_GUMBA_ST |  |  |  | 02KBJ0054 | LAU_GUMBA_ST | [12 empty] | 2023-03-31 |  |  |  | 2023-03-15 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 298AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 36374929 | 14404471.8846 | 36374929 | 14404471.8846 |  | 161255FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2015-Mar-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41373 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41373 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41373 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131416308 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639747 | 171089FDAUCAUCFPRJSSAC2023 | 4000041373 |  | 2023-06-02 |  | 2023-06-21 |  | 171089 | 171089FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541658 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 632 | 22NDXXXNW639940 | 423451 |  | RAN Only | Integration | 4000041253_120 | 4000041253 |  |  | KKNo3586 | 3. IM | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000704304 | 120 | 1300000820 | CP2018IM01 - Basic RF Module | 1 |  | EJ Area 12 | NS | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL |  |  |  | 02KIS0091 | PULAURAKYAT_TUAASAHAN_PL | [12 empty] | 2023-01-27 |  |  |  | 2023-04-14 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 395AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 71181.0004 | 68333.9997 | 71181.0004 | 68333.9997 |  | 161279FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2014-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15%,PO 4_41253 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40%,PO 4_41253 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25%,PO 4_41253 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407665 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKISARAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639940 | 171109FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171109 | 171109FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606319 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23291 | 22NDXXXNW640401 | 423605 |  | RAN Only | Integration | 4000041417_170 | 4000041417 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704577 | 170 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | KL Area 15 | NS | 01BIR0082 | COTTUNONG_TB |  |  |  | 01BIR0082 | COTTUNONG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 668AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 38289454.9997 | 15162624.1799 | 38289454.9997 | 15162624.1799 |  | 161073FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41417 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41417 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41417 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451382 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640401 | 171142FDAUCAUCFPRJSSAC2023 | 4000041417 |  | 2023-06-02 |  | 2023-06-21 |  | 171142 | 171142FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603307 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23294 | 22NDXXXNW639749 | 423840 |  | RAN Only | Integration | 4000041319_420 | 4000041319 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704209 | 420 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | CJ Area 10 | NS | 02KBJ0010 | PERBESI_ST |  |  |  | 02KBJ0010 | PERBESI_ST | [12 empty] | 2023-02-17 |  |  |  | 2023-04-18 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 300AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37952519.9995 | 15029198 | 37952519.9995 | 15029198 |  | 161320FDAUCAUCFPRJBABT2022 | 2022-09-22 | 2022-09-28 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230531_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41319 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41319 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41319 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131451232 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DKABANJAHE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639749 | 171091FDAUCAUCFPRJSSAC2023 | 4000041319 |  | 2023-06-02 |  | 2023-06-21 |  | 171091 | 171091FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0541660 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1455 | 22NDXXXNW640395 | 423960 |  | RAN Only | Integration, Expansion | 4000041234_310 | 4000041234 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704571 | 310 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 2 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959357.7762 | 37776156 | 14959357.7762 |  | 161472FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131599729 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23299 | 22NDXXXNW642841 | 423978 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704908 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 02PDS0035 | SIMIRIK_PADANG_PL |  |  |  | 02PDS0035 | SIMIRIK_PADANG_PL | [12 empty] | 2023-04-28 |  |  |  | 2023-04-13 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 999AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_13-APR-2023_Phase%202022%20MOCN_TOMAHAWK_Capacity_HN_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131583964 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D5&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW642841 | 171178FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171178 | 171178FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO NOT AVAILABLE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO NOT MATCH; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0614776 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO MATCH
1.11 AOP 2022 Integration Wo Battle-6 | 23301 | 22NDXXXNW640395 | 424090 |  | RAN Only | Integration, Expansion | 4000041221_410 | 4000041221 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704571 | 410 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 1 | NS | 01BIR0081 | GULUMPANG_TB |  |  |  | 01BIR0081 | GULUMPANG_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 662AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34114367.9999 | 13509289.9993 | 34114367.9999 | 13509289.9993 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41234 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41234 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41234 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131595722 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640395 | 171140FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171140 | 171140FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603297 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23302 | 22NDXXXNW638382 | 424097 |  | RAN Only | Integration | 4000041367_180 | 4000041367 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000703965 | 180 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | SS Area 4 | NS | 01NAD0071 | BATOH1_MT |  |  |  | 01NAD0071 | BATOH1_MT | [12 empty] | 2022-12-23 |  |  |  | 2023-04-18 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 056AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 38289454.9997 | 15162624.1799 | 38289454.9997 | 15162624.1799 |  | 161076FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2018-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576670 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638382 | 170999FDAUCAUCFPRJSSAC2023 | 4000041367 |  | 2023-06-01 |  | 2023-06-21 |  | 170999 | 170999FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0594298 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23307 | 22NDXXXNW638464 | 424361 |  | RAN Only | Integration | 4000041367_180 | 4000041367 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704047 | 180 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | SS Area 4 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 38289454.9997 | 15162624.1799 | 38289454.9997 | 15162624.1799 |  | 161076FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576683 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 | 4000041367 |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.3 AOP 2022 Capacity Expansion | 1456 | 22NDXXXNW638464 | 424362 |  | RAN Only | Integration | 4000041231_390 | 4000041231 |  |  | KKNo3586 | 1. HW | AOP 2022 Capacity Expansion | AOP 2022 MOCN Integration | BTS | 1000704047 | 390 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 1 | NS | 01JHO0055 | MEUNASAH_KRUENG_PL |  |  |  | 01JHO0055 | MEUNASAH_KRUENG_PL | [12 empty] | 2022-10-28 |  |  |  | 2023-05-02 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 138AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34114367.9999 | 13509289.9993 | 34114367.9999 | 13509289.9993 |  | 161402FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2002-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41367 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41367 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41367 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131596913 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638464 | 171024FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-01 |  | 2023-06-21 |  | 171024 | 171024FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599320 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23308 | 22NDXXXNW638467 | 424363 |  | RAN Only | Integration | 4000041367_180 | 4000041367 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704050 | 180 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | SS Area 4 | NS | 01JHO0026 | LEU_UE1_PL |  |  |  | 01JHO0026 | LEU_UE1_PL | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 141AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 38289454.9997 | 15162624.1799 | 38289454.9997 | 15162624.1799 |  | 161076FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131576694 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D4&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638467 | 171026FDAUCAUCFPRJSSAC2023 | 4000041367 |  | 2023-06-01 |  | 2023-06-21 |  | 171026 | 171026FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599306 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23309 | 22NDXXXNW640397 | 424375 |  | RAN Only | Integration | 4000041367_180 | 4000041367 |  |  | KKNo3586 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704573 | 180 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | SS Area 4 | NS | 01BIR0063 | LAMKUTA_TB |  |  |  | 01BIR0063 | LAMKUTA_TB | [12 empty] | 2023-01-13 |  |  |  | 2023-04-03 |  | 2023-05-16 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 664AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 38289454.9997 | 15162624.1799 | 38289454.9997 | 15162624.1799 |  | 161076FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2003-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230522_003.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41367 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41367 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41367 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131577166 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DLOKSUMAWE%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW640397 | 171141FDAUCAUCFPRJSSAC2023 | 4000041367 |  | 2023-06-02 |  | 2023-06-21 |  | 171141 | 171141FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3586AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603299 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23310 | 22NDXXXNW638538 | 424402 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590117 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.14 AOP 2022 Relinquish Add 900 MHz | 634 | 22NDXXXNW638538 | 424403 |  | RAN Only | Integration | 4000041237_190 | 4000041237 |  |  | KKNo3688 | 1. HW | AOP 2022 Relinquish Add 900 MHz | AOP 2022 MOCN Integration | BTS | 1000704121 | 190 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 34114367.9999 | 13509289.7287 | 34114367.9999 | 13509289.7287 |  | 161408FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131599992 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 |  |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23311 | 22NDXXXNW638538 | 424404 |  | RAN Only | Integration | 4000041222_330 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704121 | 330 | 1300000401 | ODI-065R17M18JJJJ-GQV (WITH AISG0.5+SBT) - Penta Band Antenna Large (include SBT + AISG Cable 0,5 meter) | 3 |  | NS Area 1 | NS | 01NAD0004 | AJEUN_TB |  |  |  | 01NAD0004 | AJEUN_TB | [12 empty] | 2022-10-07 |  |  |  | 2023-04-12 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 212AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 10121760 | 9639964.0001 | 30365279.9999 | 28919892.0002 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/%5BReady%20For%20Commercial%20-%20RAN%5D%20%5B12-APR-2023%5D.eml | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41237 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41237 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41237 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131581885 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638538 | 171067FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-02 |  | 2023-06-21 |  | 171067 | 171067FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599342 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23312 | 22NDXXXNW638539 | 424405 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704122 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 01NAD0008 | LAMBUNG_TB |  |  |  | 01NAD0008 | LAMBUNG_TB | [12 empty] | 2022-12-23 |  |  |  | 2023-05-10 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 213AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2010-MAY-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230606_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131590126 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638539 | 171068FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-02 |  | 2023-06-21 |  | 171068 | 171068FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599347 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23314 | 22NDXXXNW643025 | 424726 |  | RAN Only | Integration | 4000041221_390 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705024 | 390 | 1100001340 | 474198A - AREA AirScale RFM 6T6R B3 480W | 1 |  | NS Area 1 | NS | 02LMP0003 | RAYATEBING_KISARAN_PL |  |  |  | 02LMP0003 | RAYATEBING_KISARAN_PL | [12 empty] | 2023-02-24 |  |  |  | 2023-04-17 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1115AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-05-30 | 2023-05-30 |  |  | IDR | 37776156 | 14959358 | 37776156 | 14959358 |  | 161467FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2017-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_001.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41231 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41231 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41231 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131587347 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DTEBING%20TINGGI%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW643025 | 171008FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-01 |  | 2023-06-21 |  | 171008 | 171008FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED CLUSTER ACCEPTANCE CERTIFICATE; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0606641 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23378 | 22NDXXXNW652483 | 156463 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705574 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 4 |  | NS Area 1 | NS | 01NAD0047 | NEUSU_EP |  |  |  | 01NAD0047 | NEUSU_EP | [12 empty] | 2022-08-26 |  |  |  | 2023-05-31 |  | 2023-05-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1665AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-13 | 2023-06-13 |  |  | IDR | 516365.9998 | 204480.9996 | 2065463.9992 | 817923.9984 |  | 161819FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2031-May-2023%20Phase%202022%20MOCN%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130846362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652483 | 171289FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-13 |  | 2023-06-21 |  | 171289 | 171289FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-20 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599394 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23379 | 22NDXXXNW652483 | 156464 |  | RAN Only | Integration | 4000041221_360 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705574 | 360 | 1100000126 | 473537A - FUTEY SM OD fiber LC OD-LC OD dual 80m | 2 |  | NS Area 1 | NS | 01NAD0047 | NEUSU_EP |  |  |  | 01NAD0047 | NEUSU_EP | [12 empty] | 2022-08-26 |  |  |  | 2023-05-31 |  | 2023-05-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1665AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-13 | 2023-06-13 |  |  | IDR | 704643 | 279039 | 1409286 | 558078 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2031-May-2023%20Phase%202022%20MOCN%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130846362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652483 | 171289FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-13 |  | 2023-06-21 |  | 171289 | 171289FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-20 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599394 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23380 | 22NDXXXNW652483 | 156465 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705574 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 12 |  | NS Area 1 | NS | 01NAD0047 | NEUSU_EP |  |  |  | 01NAD0047 | NEUSU_EP | [12 empty] | 2022-08-26 |  |  |  | 2023-05-31 |  | 2023-05-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1665AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-13 | 2023-06-13 |  |  | IDR | 442010.9999 | 175036 | 5304131.9984 | 2100431.9996 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2031-May-2023%20Phase%202022%20MOCN%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130846362 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652483 | 171289FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-13 |  | 2023-06-21 |  | 171289 | 171289FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-20 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599394 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23381 | 22NDXXXNW652483 | 156466 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705574 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01NAD0047 | NEUSU_EP |  |  |  | 01NAD0047 | NEUSU_EP | [12 empty] | 2022-08-26 |  |  |  | 2023-05-31 |  | 2023-05-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1665AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-13 | 2023-06-13 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2031-May-2023%20Phase%202022%20MOCN%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130845494 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652483 | 171289FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-13 |  | 2023-06-21 |  | 171289 | 171289FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-20 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0599394 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23445 | 22NDXXXNW652483 | 337181 |  | RAN Only | Integration | 4000041336_6660 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705574 | 6660 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 01NAD0047 | NEUSU_EP |  |  |  | 01NAD0047 | NEUSU_EP | [12 empty] | 2022-08-26 |  |  |  | 2023-05-31 |  | 2023-05-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1665AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-13 | 2023-06-13 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2031-May-2023%20Phase%202022%20MOCN%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130001243 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652483 | 171289FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-13 |  | 2023-06-21 |  | 171289 | 171289FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-20 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599394 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23446 | 22NDXXXNW652483 | 337182 |  | RAN Only | Integration | 4000041336_6660 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705574 | 6660 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01NAD0047 | NEUSU_EP |  |  |  | 01NAD0047 | NEUSU_EP | [12 empty] | 2022-08-26 |  |  |  | 2023-05-31 |  | 2023-05-31 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1665AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-13 | 2023-06-13 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/Ready%20For%20Commercial%20-%20RAN%20%2031-May-2023%20Phase%202022%20MOCN%20AOP%202022%20RAN%20Tomahawk%20Q1%20Expansion%20Capacity%20NOKIA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_009.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130001243 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D3&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW652483 | 171289FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-13 |  | 2023-06-21 |  | 171289 | 171289FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-20 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0599394 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE
1.11 AOP 2022 Integration Wo Battle-6 | 23537 | 22NDXXXNW638523 | 157526 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 9 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 750111.9999 | 297043.9995 | 6751007.9993 | 2673395.9957 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23538 | 22NDXXXNW638523 | 157527 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 9 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 68561.9998 | 27151 | 617057.9985 | 244359.0003 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23539 | 22NDXXXNW638523 | 157528 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 10 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 226179 | 89567 | 2261790.0002 | 895670.0002 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23540 | 22NDXXXNW638523 | 157529 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 9 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 410166 | 162426 | 3691494 | 1461834 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23541 | 22NDXXXNW638523 | 157530 |  | RAN Only | Integration | 4000041221_300 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 300 | 1100000124 | 473096A - ABIA AirScale Capacity | 5 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 21545691 | 8532093.9999 | 107728455.0002 | 42660469.9997 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23542 | 22NDXXXNW638523 | 157531 |  | RAN Only | Integration | 4000041221_410 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 410 | 1100001340 | 474840A - ARDA AirScale RFM 6T6R B8 360W | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 34114367.9999 | 13509289.9993 | 34114367.9999 | 13509289.9993 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23543 | 22NDXXXNW638523 | 157532 |  | RAN Only | Integration | 4000041221_420 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 50 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 636323.0003 | 251983.9998 | 31816150.014 | 12599199.9903 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23544 | 22NDXXXNW638523 | 157533 |  | RAN Only | Integration | 4000041221_380 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 25 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 822312 | 325635.9999 | 20557799.9991 | 8140899.9987 |  | 161200FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23545 | 22NDXXXNW638523 | 157534 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 118 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 442010.9999 | 175036 | 52157297.9844 | 20654247.9963 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414966 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23546 | 22NDXXXNW638523 | 157535 |  | RAN Only | Integration | 4000041222_340 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 340 | 1300000401 | MB4B/QMF-65/DB-17/18.5DE-NT-IN-43 - Mobi Antenna (HoS) | 3 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 41187369.9999 | 39226850.9999 | 123562109.9997 | 117680552.9996 |  | 161201FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23547 | 22NDXXXNW638523 | 157536 |  | RAN Only | Integration | 4000041222_290 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 290 | 1300000007 | CP5012M01S - AntennaMountingSTD(IncludeBoom) | 3 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 2408959 | 2294293 | 7226877 | 6882879 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23548 | 22NDXXXNW638523 | 157538 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 310 | 1300000820 | CP5040SI05 - RF cable management | 4 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 1956902.0003 | 1863752.9998 | 7827608.0011 | 7455011.9994 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23549 | 22NDXXXNW638523 | 157539 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 45 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 34873.0002 | 33213.0004 | 1569285.0081 | 1494585.0171 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23550 | 22NDXXXNW638523 | 157540 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23551 | 22NDXXXNW638523 | 157541 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23552 | 22NDXXXNW638523 | 157542 |  | RAN Only | Integration | 4000041222_260 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 260 | 1300000820 | CP2018IM15 - Label G1800 | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 85623.0003 | 81547 | 85623.0003 | 81547 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23553 | 22NDXXXNW638523 | 157543 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23554 | 22NDXXXNW638523 | 157544 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161624FDAUCAUCFPRJBABT2022 | 2022-10-27 | 2022-11-01 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23555 | 22NDXXXNW638523 | 157545 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 36 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 323185.0001 | 307800.9997 | 11634660.0054 | 11080835.9883 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23556 | 22NDXXXNW638523 | 157546 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 18 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 186707.0003 | 177820.0003 | 3360726.0058 | 3200760.0063 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23557 | 22NDXXXNW638523 | 157547 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 540 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 136047.0003 | 129571.0003 | 73465380.1728 | 69968340.162 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23558 | 22NDXXXNW638523 | 157548 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 320 | 1300000820 | MCB 63A - MCB 63A | 10 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 265205.9998 | 252581.9998 | 2652059.9982 | 2525819.9978 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131407222 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23685 | 22NDXXXNW650234 | 180988 |  | RAN Only | Integration | 4000041221_240 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 750111.9999 | 297043.9995 | 750111.9999 | 297043.9995 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23686 | 22NDXXXNW650234 | 180989 |  | RAN Only | Integration | 4000041221_260 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 68561.9998 | 27151 | 68561.9998 | 27151 |  | 161060FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23687 | 22NDXXXNW650234 | 180990 |  | RAN Only | Integration | 4000041221_270 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 226179 | 89567 | 452358 | 179134 |  | 161061FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23688 | 22NDXXXNW650234 | 180991 |  | RAN Only | Integration | 4000041221_230 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 410166 | 162426 | 820332 | 324852 |  | 161059FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23689 | 22NDXXXNW650234 | 180992 |  | RAN Only | Integration | 4000041221_310 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 310 | 1100000124 | 473098A - AMIA AirScale Subrack | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 7289110 | 2886488 | 7289110 | 2886488 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23690 | 22NDXXXNW650234 | 180993 |  | RAN Only | Integration | 4000041221_370 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 370 | 1100000124 | 473764A - ASIB AirScale Common | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 30228098.9999 | 11970327 | 30228098.9999 | 11970327 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23691 | 22NDXXXNW650234 | 180994 |  | RAN Only | Integration | 4000041221_300 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 300 | 1100000124 | 473096A - ABIA AirScale Capacity | 3 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 21545691 | 8532093.9999 | 64637073.0001 | 25596281.9998 |  | 161804FDAUCAUCFPRJBABT2022REV | 2022-11-28 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23692 | 22NDXXXNW650234 | 180995 |  | RAN Only | Integration | 4000041221_400 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 35887295.9999 | 14211369.0004 | 35887295.9999 | 14211369.0004 |  | 161418FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23693 | 22NDXXXNW650234 | 180996 |  | RAN Only | Integration | 4000041221_430 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 430 | 1100001034 | 475338A - AOSI 10Gbs SFP+ 1310nm 1.4km SM I-temp | 20 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 516365.9998 | 204480.9996 | 10327319.996 | 4089619.992 |  | 161819FDAUCAUCFPRJBABT2022 | 2022-11-23 | 2022-11-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23694 | 22NDXXXNW650234 | 180997 |  | RAN Only | Integration | 4000041221_340 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 340 | 1100000126 | 473308A - FUFBF SM OD fiber LC OD-LC OD dual 50m | 10 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 449774 | 178111 | 4497740.0005 | 1781109.9999 |  | 161989FDAUCAUCFPRJBABT2022 | 2022-12-07 | 2022-12-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23695 | 22NDXXXNW650234 | 180998 |  | RAN Only | Integration | 4000041221_440 | 4000041221 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 440 | 1200000321 | SR001015.T - SBTS Incremental 20W Power LTU | 21 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 442010.9999 | 175036 | 9282230.9972 | 3675755.9993 |  | 161063FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131576337 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041221 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23696 | 22NDXXXNW650234 | 181001 |  | RAN Only | Integration | 4000041222_310 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 1956902.0003 | 1863752.9998 | 1956902.0003 | 1863752.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23697 | 22NDXXXNW650234 | 181002 |  | RAN Only | Integration | 4000041222_220 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 5 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 73620.9997 | 70117.0003 | 368104.9987 | 350585.0017 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23698 | 22NDXXXNW650234 | 181003 |  | RAN Only | Integration | 4000041222_230 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 10 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 34873.0002 | 33213.0004 | 348730.0018 | 332130.0038 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23699 | 22NDXXXNW650234 | 181004 |  | RAN Only | Integration | 4000041222_240 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 240 | 1300000820 | CP2018IM12 - Label G900 | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161064FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23700 | 22NDXXXNW650234 | 181005 |  | RAN Only | Integration | 4000041222_250 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 250 | 1300000820 | CP2018IM14 - Label L900 | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161065FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23701 | 22NDXXXNW650234 | 181006 |  | RAN Only | Integration | 4000041222_270 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 270 | 1300000820 | CP2018IM16 - Label L1800 | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161468FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23702 | 22NDXXXNW650234 | 181007 |  | RAN Only | Integration | 4000041222_280 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 80795.9997 | 76949.9997 | 80795.9997 | 76949.9997 |  | 161624FDAUCAUCFPRJBABT2022 | 2022-10-27 | 2022-11-01 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23703 | 22NDXXXNW650234 | 181008 |  | RAN Only | Integration | 4000041222_360 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 4 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 323185.0001 | 307800.9997 | 1292740.0006 | 1231203.9987 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23704 | 22NDXXXNW650234 | 181009 |  | RAN Only | Integration | 4000041222_350 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 186707.0003 | 177820.0003 | 373414.0007 | 355640.0007 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23705 | 22NDXXXNW650234 | 181010 |  | RAN Only | Integration | 4000041222_300 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 50 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 136047.0003 | 129571.0003 | 6802350.016 | 6478550.015 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 23706 | 22NDXXXNW650234 | 181011 |  | RAN Only | Integration | 4000041222_320 | 4000041222 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 265205.9998 | 252581.9998 | 265205.9998 | 252581.9998 |  | 161066FDAUCAUCFPRJBABT2022 | 2022-08-26 | 2022-08-30 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1131583706 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041222 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24032 | 22NDXXXNW639022 | 191562 |  | RAN Only | Integration, Expansion | 4000041323_240 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 240 | 1100001382 | 470316A - EMHA FLEXI EDGE MECHANICAL 3U UNIT | 2 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 753614.0004 | 298431.1433 | 1507228.0007 | 596862.2867 |  | 161393FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130966393 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24033 | 22NDXXXNW639022 | 191563 |  | RAN Only | Integration, Expansion | 4000041323_260 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 260 | 1100001382 | 471524A - FMHA FLEXI SIDE COVER 3U | 2 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 68882.0006 | 27277.272 | 137764.0011 | 54554.544 |  | 161393FDAUCAUCFPRJBABT2022 | 2022-10-10 | 2022-10-12 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130966393 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24034 | 22NDXXXNW639022 | 191564 |  | RAN Only | Integration, Expansion | 4000041323_270 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 270 | 1100000046 | 471649A - FPKA Flexi Pole Kit | 2 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 227235 | 89985.06 | 454470 | 179970.12 |  | 161658FDAUCAUCFPRJBABT2022 | 2022-11-10 | 2022-11-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130966393 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24035 | 22NDXXXNW639022 | 191565 |  | RAN Only | Integration, Expansion | 4000041323_230 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 230 | 1100000300 | 470149A - FMFA FLEXI MOUNTING KIT FLOOR/WALL/POLE | 2 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 412080.9999 | 163184.076 | 824161.9998 | 326368.152 |  | 161262FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130966393 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24036 | 22NDXXXNW639022 | 191566 |  | RAN Only | Integration, Expansion | 4000041323_400 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 400 | 1100001340 | 474800A - ARGA AirScale RFM 6T6R B1 480W | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 36054841.9994 | 14277717.4321 | 36054841.9994 | 14277717.4321 |  | 161213FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130966393 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24037 | 22NDXXXNW639022 | 191567 |  | RAN Only | Integration, Expansion | 4000041323_420 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 420 | 1100001034 | 475336A - AOME 10G SFP+ 850nm 300m MM I-temp | 2 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 639293.9997 | 253160.424 | 1278587.9994 | 506320.848 |  | 161262FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130966393 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24038 | 22NDXXXNW639022 | 191568 |  | RAN Only | Integration, Expansion | 4000041323_380 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 380 | 1100000126 | 473905A - FUFDD MM OD fiber LC OD-LC OD dual 80m | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 826151 | 327155.7959 | 826151 | 327155.7959 |  | 161576FDAUCAUCFPRJBABT2022 | 2022-10-24 | 2022-10-27 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130966393 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041323 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24039 | 22NDXXXNW639022 | 191570 |  | RAN Only | Integration, Expansion | 4000041324_310 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 310 | 1300000820 | CP5040SI05 - RF cable management | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 1966037.9999 | 1872454.5914 | 1966037.9999 | 1872454.5914 |  | 161263FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24040 | 22NDXXXNW639022 | 191571 |  | RAN Only | Integration, Expansion | 4000041324_220 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 220 | 1300000820 | CP2018IM08 - Power DC cable NYY 2*16 sqmm | 10 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 73964 | 70443.3136 | 739640 | 704433.136 |  | 161114FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24041 | 22NDXXXNW639022 | 191572 |  | RAN Only | Integration, Expansion | 4000041324_230 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 230 | 1300000820 | CP2018IM09 - Grounding cable NYAF 16mm2 Yellow/Green | 5 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 35035.9998 | 33368.2862 | 175179.9989 | 166841.4312 |  | 161114FDAUCAUCFPRJBABT2022 | 2022-09-09 | 2022-09-14 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24042 | 22NDXXXNW639022 | 191573 |  | RAN Only | Integration, Expansion | 4000041324_280 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 280 | 1300000820 | CP2018IM18 - Label L2100 | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 81172.9997 | 77309.1654 | 81172.9997 | 77309.1654 |  | 161214FDAUCAUCFPRJBABT2022 | 2022-09-17 | 2022-09-21 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24043 | 22NDXXXNW639022 | 191574 |  | RAN Only | Integration, Expansion | 4000041324_360 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 360 | 1300000725 | RFJ743MDR - Jumper 7M 43MDR, 1xWPS | 2 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 324693.0001 | 309237.6133 | 649386.0003 | 618475.2266 |  | 161518FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24044 | 22NDXXXNW639022 | 191575 |  | RAN Only | Integration, Expansion | 4000041324_350 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 350 | 1300000725 | RFJ343M43M - Jumper 3M 43M43M, 2xWPS | 2 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 187578.0001 | 178649.2872 | 375156.0002 | 357298.5745 |  | 161518FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24045 | 22NDXXXNW639022 | 191576 |  | RAN Only | Integration, Expansion | 4000041324_300 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 300 | 1300000820 | CP5012MA18 - Mat 2x16 power cable and clamp for RRH | 60 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 136682.9997 | 130176.8893 | 8200979.982 | 7810613.3568 |  | 161263FDAUCAUCFPRJBABT2022 | 2022-09-20 | 2022-09-23 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24046 | 22NDXXXNW639022 | 191577 |  | RAN Only | Integration, Expansion | 4000041324_320 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 320 | 1300000820 | MCB 63A - MCB 63A | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 266445.0001 | 253762.2184 | 266445.0001 | 253762.2184 |  | 161518FDAUCAUCFPRJBABT2022 | 2022-10-17 | 2022-10-20 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24047 | 22NDXXXNW639022 | 191578 |  | RAN Only | Integration, Expansion | 4000041324_190 | 4000041324 |  |  | KKNo3688 | 3. IM | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 190 | 1300000820 | 092687A - 085415A DC terminal 2P seal assy | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 1116342.0001 | 1063204.1206 | 1116342.0001 | 1063204.1206 |  | 161483FDAUCAUCFPRJBABT2022 | 2022-10-14 | 2022-10-19 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130954609 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041324 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24088 | 22NDXXXNW638523 | 332282 |  | RAN Only | Integration | 4000041335_1970 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 1970 | 4100000512 | SB4 - New Site or New Technology on Existing Site - Without Antenna/AAU Installation - with 2 Technologies - with No Power Requirements | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 104340815.0001 | 36581889.7388 | 104340815.0001 | 36581889.7388 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416988 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24089 | 22NDXXXNW638523 | 332283 |  | RAN Only | Integration | 4000041335_1970 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 1970 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416988 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24090 | 22NDXXXNW638523 | 332284 |  | RAN Only | Integration | 4000041335_1970 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 1970 | 4100000512 | BTSS321 - Antennas Swap (Antenna, Bracket & Jumpers) for Disposal without PIM testing 1 Sector Site | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 14871605.0002 | 5213984.7132 | 14871605.0002 | 5213984.7132 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416988 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24091 | 22NDXXXNW638523 | 332285 |  | RAN Only | Integration | 4000041335_1970 | 4000041335 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 1970 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 1 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1130416988 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041335 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24159 | 22NDXXXNW650234 | 336912 |  | RAN Only | Integration | 4000041336_5740 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 5740 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130387400 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24160 | 22NDXXXNW650234 | 336913 |  | RAN Only | Integration | 4000041336_5740 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 5740 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130387400 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24161 | 22NDXXXNW650234 | 336914 |  | RAN Only | Integration | 4000041336_5740 | 4000041336 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705482 | 5740 | 4100000512 | BTSS454 - BBU/RRU/Filter/Module Dismantle for Redeployment | 1 |  | NS Area 1 | NS | 02PDS0016 | TANO_BATO_TB |  |  |  | 02PDS0016 | TANO_BATO_TB | [12 empty] | 2022-11-25 |  |  |  | 2023-04-04 |  | 2023-05-30 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 1573AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 5733695.0001 | 2010233.4669 | 5733695.0001 | 2010233.4669 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_004.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41336 SVC 30% | TOP PO 4_41336 SVC 85% | TOP PO 4_41336 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41222 IM 25% |  | 0 | 0 | 0 | [9 empty] | 1130387400 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DSIDEMPUAN%2D1&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW650234 | 171191FDAUCAUCFPRJSSAC2023 | 4000041336 |  | 2023-06-09 |  | 2023-06-21 |  | 171191 | 171191FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0615061 |  | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24166 | 22NDXXXNW639022 | 338021 |  | RAN Only | Integration, Expansion | 4000041340_500 | 4000041340 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 500 | 4100000512 | SB27 - Expansion on Existing Site and Existing Technology With Hardware Change - Without Antenna/AAU Installation - with No Power Requirements | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 72844301.0002 | 25539211.9306 | 72844301.0002 | 25539211.9306 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130488170 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041340 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24167 | 22NDXXXNW639022 | 338022 |  | RAN Only | Integration, Expansion | 4000041340_500 | 4000041340 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 500 | 4100000512 | BTSS517 - 3rd Party Project Management | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 10201888.9999 | 3576782.2833 | 10201888.9999 | 3576782.2833 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130488170 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041340 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24168 | 22NDXXXNW639022 | 338023 |  | RAN Only | Integration, Expansion | 4000041340_500 | 4000041340 |  |  | KKNo3688 | 5. SVC | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000705760 | 500 | 4100000512 | BTSS452 - Decommissioning and Removal of BTS for Redeployment | 1 |  | NS Area 2 | NS | 02STB0077 | PEKAN_GEBANG_CM |  |  |  | 02STB0077 | PEKAN_GEBANG_CM | [12 empty] | 2023-03-31 |  |  |  | 2023-01-19 |  | 2023-05-27 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 2034AOP2022MOCNINTAREA2NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 23229344 | 8144208.0067 | 23229344 | 8144208.0067 | [7 empty] | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/_Ready%20For%20Commercial%20-%20RAN_%20_19-January-2023_%20_Phase%202022%20MOCN_%20_Capacity_%20_HN_%20_NOKIA_CJWJ_EJBN_KALISUMAPA_SUMATERA_.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230605_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41340 SVC 30% | TOP PO 4_41340 SVC 85% | TOP PO 4_41340 SVC 55% | TOP PO 4_41323 HW 15%,PO 4_41324 IM 15% | TOP PO 4_41323 HW 40%,PO 4_41324 IM 40% | TOP PO 4_41323 HW 25%,PO 4_41324 IM 25% |  | AOP2022PAC043 | 2023-03-24 | 2023-03-24 | [9 empty] | 1130488170 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW639022 | 171195FDAUCAUCFPRJSSAC2023 | 4000041340 | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F02%2E%20MOCN%20FAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBINJAI%2D2&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | 2023-06-09 |  | 2023-06-21 |  | 171195 | 171195FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 0. NO NEED | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST |  | 0 | 0.3 | 0.55 | 0.15 | [6 empty] | SMP-WO-0551995 | 2023-03-24 | 2023_Q1 INT PAC P03 | 2. SO DONE | koreksi kolom remarks Mat
1.11 AOP 2022 Integration Wo Battle-6 | 24224 | 22NDXXXNW638523 | 423258 |  | RAN Only | Integration | 4000041323_310 | 4000041323 |  |  | KKNo3688 | 1. HW | AOP 2022 Integration Wo Battle-6 | AOP 2022 MOCN Integration | BTS | 1000704106 | 310 | 1100000124 | 473098A - AMIA AirScale Subrack | 1 |  | NS Area 2 | NS | 01NAD0100 | LHOKBANGKA_RUKOH_TB |  |  |  | 01NAD0100 | LHOKBANGKA_RUKOH_TB | [12 empty] | 2022-10-21 |  |  |  | 2023-04-04 |  | 2023-05-24 |  |  |  | NO NEED TO CHECK CR |  | 1. RESERVATION DONE |  | 197AOP2022MOCNINTAREA1NOKATPSSAC2023 | SSAC | 2023-06-07 | 2023-06-07 |  |  | IDR | 7323140 | 2899963.4399 | 7323140 | 2899963.4399 |  | 161082FDAUCAUCFPRJBABT2022 | 2022-09-07 | 2022-09-13 |  |  |  | NO NEED | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/RFC_RELEASE/HWI/Ready%20For%20Commercial%20-%20RAN%2004-APR-2023%20Phase%202022%20MOCN%20TOMAHAWK%20Capacity%20HN%20NOKIACJWJEJBNKALISUMAPA%20SUMATERA.msg | [7 empty] | https://ppm.indosat.com/ran_2022/MOCN/NOK/Documents/ENDORSE/ATP%20Endorse%20Approved_20230529_002.msg |  |  |  |  | Mix Mat dan SVC | TOP PO 4_41335 SVC 30% | TOP PO 4_41335 SVC 85% | TOP PO 4_41335 SVC 55% | TOP PO 4_41221 HW 15%,PO 4_41323 HW 15%,PO 4_41222 IM 15% | TOP PO 4_41221 HW 40%,PO 4_41323 HW 40%,PO 4_41222 IM 40% | TOP PO 4_41221 HW 25%,PO 4_41323 HW 25%,PO 4_41222 IM 25% |  | AOP2022PAC054 | 0 | 0 | [9 empty] | 1131414853 |  |  |  |  | https://ppm.indosat.com/NPO-PROJECT/NPO-Dashboard/Documents/Forms/AllItems.aspx?RootFolder=%2FNPO%2DPROJECT%2FNPO%2DDashboard%2FDocuments%2F03%2E%20Nokia%2F03%2E%20Acceptance%20Report%2F01%2E%20Cluster%20Report%2F04%2E%202022%2F01%2E%20MOCN%20PAC%2F01%2E%20Sumatera%2FNC%5FIOH%5FMC%2DBANDA%20ACEH%2D6&FolderCTID=0x012000FE6BD622D130854FAB6A8033BC0A3067&View={30EE0225-5284-4A7D-8044-20B3E6BEB0FF} | NEED CA | 22NDXXXNW638523 | 171194FDAUCAUCFPRJSSAC2023 | 4000041323 |  | 2023-06-09 |  | 2023-06-21 |  | 171194 | 171194FDAUCAUCFPRJSSAC2023 |  |  |  | No Delay | 3688AUCAUCEKK2023_NOK (DONE) | 2023-06-16 |  |  |  | 1. RESERVATION DONE; PS STATUS IGNORE due to INT AND RAN ONLY |  |  | 2. BABT RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 8. BAST SSAC RECEIVED; SO DONE; NEED PAC TO HO (INCL IN 44 PO CN) | 6. BAMP FOR PAC CREATION | 5. BAMG FOR FAC CREATION; NEED PAC RECEIVED; NEED PUNCHLIST; NEED CLUSTER OPTIM CERTIFICATE |  | 0.5 | 0.15 | 0.25 | 0.1 | [6 empty] | SMP-WO-0603058 | 2023-06-15 | 2023_Q2 INT plan P06 Ready PAC Acc1 | 2. SO DONE | koreksi kolom remarks Mat